## Remaining
XXX001.8E Client Project Phase 1A Flowlines | [17 empty] | Hours Remaining as of: | 2015-08-21
# | Group | Original | Approved |  |  |  | Pending |  |  |  | Approved |  |  |  | Current | Actuals as of | Week of | Total to | Hours | Error Check
Code | Discipline | Budget | Changes | CN-001 | CN-00X | CN-00X | Changes | CN-00X | CN-00X | CN-00X | Non Scope | CN-00X | CN-00X | CN-00X | Forecast | 2015-08-14 | 2015-08-21 | 2015-08-21 | Remaining
01. | Project Management | 2601 | 0 | 792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2601 | 1016.75 | 60.5 | 1077.25 | 1523.75 | 0
200 | Project Management | 1306 | 0 | 240 |  |  | 0 |  |  |  | 0 |  |  |  | 1306 | 393 | 0 | 393 | 913 | 0
210 | Project Engineer | 636 | 0 | 272 |  |  | 0 |  |  |  | 0 |  |  |  | 636 | 320.5 | 40 | 360.5 | 275.5 | 0
240 | Quality Assurance | 136 | 0 | 40 |  |  | 0 |  |  |  | 0 |  |  |  | 136 | 55.5 | 5 | 60.5 | 75.5 | 0
290 | Project Administration | 483 | 0 | 240 |  |  | 0 |  |  |  | 0 |  |  |  | 483 | 247.75 | 15.5 | 263.25 | 219.75 | 0
390 | Regulatory Affairs | 40 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 40 | 0 | 0 | 0 | 40 | 0
|  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
02. | Project Controls | 1438.5 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1438.5 | 727.75 | 24.5 | 752.25 | 686.25 | 0
230 | Project Controls | 1041.5 | 0 | 260 |  |  | 0 |  |  |  | 0 |  |  |  | 1041.5 | 463.5 | 24 | 487.5 | 554 | 0
250 | Estimating | 397 | 0 | 40 |  |  | 0 |  |  |  | 0 |  |  |  | 397 | 264.25 | 0.5 | 264.75 | 132.25 | 0
|  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
03. | Document Control | 806 | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 806 | 180 | 9 | 189 | 617 | 0
280 | Document Control | 806 | 0 | 280 |  |  | 0 |  |  |  | 0 |  |  |  | 806 | 180 | 9 | 189 | 617 | 0
|  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
04. | Process Engineering & Design | 981.5 | 0 | 737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981.5 | 512 | 33.5 | 545.5 | 436 | 0
310 | Process Engineering | 701.5 | 0 | 689 |  |  | 0 |  |  |  | 0 |  |  |  | 701.5 | 407 | 33.5 | 440.5 | 261 | 0
410 | P&ID Design & Drafting | 280 | 0 | 48 |  |  | 0 |  |  |  | 0 |  |  |  | 280 | 105 | 0 | 105 | 175 | 0
|  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
05. | Mechanical & Stress Engineering | 1045 | 0 | 776.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1045 | 167.5 | 0 | 165 | 880 | 0
320 | Mechanical Engineering | 0 | 0 | 616.5 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
321 | Stress Engineering | 1045 | 0 | 160 |  |  | 0 |  |  |  | 0 |  |  |  | 1045 | 165 | 0 | 165 | 880 | 0
|  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
06. | Electrical Engineering & Design | 0 | 0 | 705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | Electrical Engineering | 0 | 0 | 228 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
430 | Electrical Design | 0 | 0 | 477 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
07. | Instrumentation & Controls | 0 | 0 | 578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
340 | Instrumentation Engineering | 0 | 0 | 578 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
440 | Instrumentation Design | 0 | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
350 | Controls Engineering | 0 | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
450 | Controls Design | 0 | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
06. | Structural Engineering & Design | 4644 | 0 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4644 | 1254 | 120 | 1374 | 3270 | 0
360 | Structural Engineering | 2134 | 0 | 255 |  |  | 0 |  |  |  | 0 |  |  |  | 2134 | 631 | 60 | 691 | 1443 | 0
460 | Structural Design | 2510 | 0 | 263 |  |  | 0 |  |  |  | 0 |  |  |  | 2510 | 623 | 60 | 683 | 1827 | 0
|  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
07. | Piping Design & EAS | 204 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 79.5 | 11 | 90.5 | 113.5 | 0
420 | Piping Design | 0 | 0 | 800 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
490 | Eng. Application Services | 204 | 0 | 80 |  |  | 0 |  |  |  | 0 |  |  |  | 204 | 79.5 | 11 | 90.5 | 113.5 | 0
|  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
08. | Pipeline Engineering & Design | 7079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7079 | 1453.5 | 66 | 1522 | 5557 | 0
370 | Pipeline Engineering | 1613 | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 1613 | 181.5 | 5.5 | 187 | 1426 | 0
470 | Pipeline Design | 5466 | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 5466 | 1274.5 | 60.5 | 1335 | 4131 | 0
|  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
09. | Civil Engineering & Design | 503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 503 | 235.5 | 7 | 242.5 | 260.5 | 0
380 | Civil - Earthworks Engineering | 237 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 237 | 151.5 | 7 | 158.5 | 78.5 | 0
480 | Civil - Earthworks Design | 266 | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 266 | 84 | 0 | 84 | 182 | 0
|  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0
12. | Procurement & Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0
510 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0
550 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0
Grand Total |  | 19302 | 0 | 5566.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19302 | 5626.5 | 331.5 | 5958 | 13344

## Timesheet (hidden)
XXX001.8E Client Project Phase 1A Flowlines
Timesheet Report (From PCS)
| As of: | 2015-08-21
 | time axis 2015-05-01 to 2016-06-24
| 01. | Project Management | 0.75 | 11.5 | 11.5 | 12.5 | 24.5 | 73.5 | 86.5 | 83.5 | 102 | 86.25 | 82.5 | 110.5 | 82.5 | 73.5 | 86 | 89.25 | 60.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 200 | Project Management | 0 | 11 | 9 | 8 | 18 | 30 | 30 | 30 | 30 | 26 | 35 | 35 | 35 | 39 | 27 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 210 | Project Engineer | 0 | 0 | 0 | 0 | 0 | 28 | 24 | 28 | 38.5 | 33 | 40 | 40.5 | 12.5 | 0 | 36 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 240 | Quality Assurance | 0 | 0 | 0 | 0 | 0 | 4 | 12.5 | 5 | 7 | 5 | 4 | 7 | 4 | 2 | 3 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 290 | Project Administration | 0.75 | 0.5 | 2.5 | 4.5 | 6.5 | 11.5 | 20 | 20.5 | 26.5 | 22.25 | 3.5 | 28 | 31 | 32.5 | 20 | 17.25 | 15.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 390 | Regulatory Affairs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 02. | Project Controls | 0 | 5 | 14 | 11 | 23.5 | 44 | 42 | 55 | 57 | 46 | 49 | 68.5 | 37.25 | 90 | 113 | 72.5 | 24.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 230 | Project Controls | 0 | 5 | 14 | 11 | 23.5 | 33 | 32 | 45 | 57 | 46 | 44 | 49 | 6 | 39 | 32 | 27 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 250 | Estimating | 0 | 0 | 0 | 0 | 0 | 11 | 10 | 10 | 0 | 0 | 5 | 19.5 | 31.25 | 51 | 81 | 45.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 03. | Document Control | 0 | 0 | 0 | 0 | 8 | 10 | 8 | 15 | 10 | 14 | 20 | 20 | 20 | 20 | 20 | 15 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 280 | Document Control | 0 | 0 | 0 | 0 | 8 | 10 | 8 | 15 | 10 | 14 | 20 | 20 | 20 | 20 | 20 | 15 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 04. | Process Engineering & Design | 21 | 42.5 | 51 | 9 | 15 | 76 | 89 | 63.5 | 27 | 7.25 | 34.5 | 26.5 | 20.25 | 3 | 11.5 | 15 | 33.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 310 | Process Engineering | 21 | 42.5 | 51 | 9 | 15 | 38 | 42 | 43.5 | 27 | 7.25 | 34.5 | 26.5 | 20.25 | 3 | 11.5 | 15 | 33.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 410 | P&ID Design & Drafting | 0 | 0 | 0 | 0 | 0 | 38 | 47 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 05. | Mechanical & Stress Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 35 | 0 | 0 | 1 | 18 | 10 | 27 | 21 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 320 | Mechanical Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 321 | Stress Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 35 | 0 | 0 | 1 | 18 | 10 | 27 | 21 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 06. | Electrical Engineering & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 330 | Electrical Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 430 | Electrical Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 07. | Instrumentation & Controls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 340 | Instrumentation Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 440 | Instrumentation Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 350 | Controls Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 450 | Controls Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 06. | Structural Engineering & Design | 0 | 0 | 0 | 27 | 36 | 57 | 104 | 79 | 111 | 124 | 130 | 120 | 112 | 120 | 114 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 360 | Structural Engineering | 0 | 0 | 0 | 7 | 12 | 33 | 34 | 35 | 63 | 76 | 85 | 60 | 52 | 60 | 54 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 460 | Structural Design | 0 | 0 | 0 | 20 | 24 | 24 | 70 | 44 | 48 | 48 | 45 | 60 | 60 | 60 | 60 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 07. | Piping Design & EAS | 0 | 0 | 0 | 0 | 0 | 4 | 2.5 | 1 | 4.5 | 3 | 2 | 10 | 7 | 9.5 | 5.5 | 30.5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 420 | Piping Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 490 | Eng. Application Services | 0 | 0 | 0 | 0 | 0 | 4 | 2.5 | 1 | 4.5 | 3 | 2 | 10 | 7 | 9.5 | 5.5 | 30.5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08. | Pipeline Engineering & Design | 0 | 0 | 57.5 | 39.5 | 71 | 93 | 108 | 79 | 126 | 93.5 | 109 | 128.5 | 147 | 138.5 | 106 | 159.5 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 370 | Pipeline Engineering | 0 | 0 | 0 | 0 | 9 | 13 | 16 | 19 | 18 | 19 | 19 | 13 | 19 | 10 | 11.5 | 15 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 470 | Pipeline Design | 0 | 0 | 57.5 | 39.5 | 62 | 80 | 92 | 60 | 108 | 74.5 | 90 | 115.5 | 128 | 128.5 | 94.5 | 144.5 | 60.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 09. | Civil Engineering & Design | 0 | 8 | 0 | 0.5 | 15.5 | 28.5 | 27.5 | 43 | 33.5 | 19 | 20 | 9 | 8 | 8 | 8 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 380 | Civil - Earthworks Engineering | 0 | 0 | 0 | 0 | 15 | 15 | 22.5 | 19 | 16 | 6 | 18 | 9 | 8 | 8 | 8 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 480 | Civil - Earthworks Design | 0 | 8 | 0 | 0.5 | 0.5 | 13.5 | 5 | 24 | 17.5 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12. | Procurement & Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 21.75 | 67 | 134 | 99.5 | 193.5 | 386 | 505.5 | 454 | 471 | 393 | 448 | 511 | 444 | 489.5 | 485 | 523.75 | 331.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Cummulative | 21.75 | 88.75 | 222.75 | 322.25 | 515.75 | 901.75 | 1407.25 | 1861.25 | 2332.25 | 2725.25 | 3173.25 | 3684.25 | 4128.25 | 4617.75 | 5102.75 | 5626.5 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958 | 5958
|  | Project Management Team | 0.75 | 16.5 | 25.5 | 23.5 | 56 | 127.5 | 136.5 | 153.5 | 169 | 146.25 | 151.5 | 199 | 139.75 | 183.5 | 219 | 176.75 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Engineering & Design | 21 | 50.5 | 108.5 | 76 | 137.5 | 258.5 | 369 | 300.5 | 302 | 246.75 | 296.5 | 312 | 304.25 | 306 | 266 | 347 | 237.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Error | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Paste |  | Time Charged
Here -> |  |  | 2015-05-01: May-01-2015; 2015-05-08: May-08-2015; 2015-05-15: May-15-2015; 2015-05-22: May-22-2015; 2015-05-29: May-29-2015; 2015-06-05: Jun-05-2015; 2015-06-12: Jun-12-2015; 2015-06-19: Jun-19-2015; 2015-06-26: Jun-26-2015; 2015-07-03: Jul-03-2015; 2015-07-10: Jul-10-2015; 2015-07-17: Jul-17-2015; 2015-07-24: Jul-24-2015; 2015-07-31: Jul-31-2015; 2015-08-07: Aug-07-2015; 2015-08-14: Aug-14-2015; 2015-08-21: Aug-21-2015; 2015-08-28: Grand Total
| 200 | 200 Project Management | 2015-05-08: 11; 2015-05-15: 9; 2015-05-22: 8; 2015-05-29: 18; 2015-06-05: 30; 2015-06-12: 30; 2015-06-19: 30; 2015-06-26: 30; 2015-07-03: 26; 2015-07-10: 35; 2015-07-17: 35; 2015-07-24: 35; 2015-07-31: 39; 2015-08-07: 27; 2015-08-14: 30; 2015-08-28: 393
| 210 | 210 Project Engineering | 2015-06-05: 28; 2015-06-12: 24; 2015-06-19: 28; 2015-06-26: 38.5; 2015-07-03: 33; 2015-07-10: 40; 2015-07-17: 40.5; 2015-07-24: 12.5; 2015-08-07: 36; 2015-08-14: 40; 2015-08-21: 40; 2015-08-28: 360.5
| 230 | 230 Project Controls | 2015-05-08: 5; 2015-05-15: 14; 2015-05-22: 11; 2015-05-29: 23.5; 2015-06-05: 33; 2015-06-12: 32; 2015-06-19: 45; 2015-06-26: 57; 2015-07-03: 46; 2015-07-10: 44; 2015-07-17: 49; 2015-07-24: 6; 2015-07-31: 39; 2015-08-07: 32; 2015-08-14: 27; 2015-08-21: 24; 2015-08-28: 487.5
| 240 | 240 Quality Control & HSE | 2015-06-05: 4; 2015-06-12: 12.5; 2015-06-19: 5; 2015-06-26: 7; 2015-07-03: 5; 2015-07-10: 4; 2015-07-17: 7; 2015-07-24: 4; 2015-07-31: 2; 2015-08-07: 3; 2015-08-14: 2; 2015-08-21: 5; 2015-08-28: 60.5
| 250 | 250 Estimating | 2015-06-05: 11; 2015-06-12: 10; 2015-06-19: 10; 2015-07-10: 5; 2015-07-17: 19.5; 2015-07-24: 31.25; 2015-07-31: 51; 2015-08-07: 81; 2015-08-14: 45.5; 2015-08-21: 0.5; 2015-08-28: 264.75
| 280 | 280 Document Control | 2015-05-29: 8; 2015-06-05: 10; 2015-06-12: 8; 2015-06-19: 15; 2015-06-26: 10; 2015-07-03: 14; 2015-07-10: 20; 2015-07-17: 20; 2015-07-24: 20; 2015-07-31: 20; 2015-08-07: 20; 2015-08-14: 15; 2015-08-21: 9; 2015-08-28: 189
| 290 | 290 Project Administration | 2015-05-01: 0.75; 2015-05-08: 0.5; 2015-05-15: 2.5; 2015-05-22: 4.5; 2015-05-29: 6.5; 2015-06-05: 11.5; 2015-06-12: 20; 2015-06-19: 20.5; 2015-06-26: 26.5; 2015-07-03: 22.25; 2015-07-10: 3.5; 2015-07-17: 28; 2015-07-24: 31; 2015-07-31: 32.5; 2015-08-07: 20; 2015-08-14: 17.25; 2015-08-21: 15.5; 2015-08-28: 263.25
| 310 | 310 Process Engineering | 2015-05-01: 21; 2015-05-08: 42.5; 2015-05-15: 51; 2015-05-22: 9; 2015-05-29: 15; 2015-06-05: 38; 2015-06-12: 42; 2015-06-19: 43.5; 2015-06-26: 27; 2015-07-03: 7.25; 2015-07-10: 34.5; 2015-07-17: 26.5; 2015-07-24: 20.25; 2015-07-31: 3; 2015-08-07: 11.5; 2015-08-14: 15; 2015-08-21: 33.5; 2015-08-28: 440.5
| 320 | 320 Mechanical Engineering | 2015-07-17: 0; 2015-07-24: 0; 2015-08-07: 0; 2015-08-14: 0; 2015-08-21: 0; 2015-08-28: 0
| 321 | 321 Stress Engineering | 2015-06-12: 38; 2015-06-19: 35; 2015-07-10: 1; 2015-07-17: 18; 2015-07-24: 10; 2015-07-31: 27; 2015-08-07: 21; 2015-08-14: 15; 2015-08-28: 165
| 360 | 360 Structural Engineering | 2015-05-22: 7; 2015-05-29: 12; 2015-06-05: 33; 2015-06-12: 34; 2015-06-19: 35; 2015-06-26: 63; 2015-07-03: 76; 2015-07-10: 85; 2015-07-17: 60; 2015-07-24: 52; 2015-07-31: 60; 2015-08-07: 54; 2015-08-14: 60; 2015-08-21: 60; 2015-08-28: 691
| 370 | 370 Pipeline Engineering | 2015-05-29: 9; 2015-06-05: 13; 2015-06-12: 16; 2015-06-19: 19; 2015-06-26: 18; 2015-07-03: 19; 2015-07-10: 19; 2015-07-17: 13; 2015-07-24: 19; 2015-07-31: 10; 2015-08-07: 11.5; 2015-08-14: 15; 2015-08-21: 5.5; 2015-08-28: 187
| 380 | 380 Civil - Earthworks Eng | 2015-05-29: 15; 2015-06-05: 15; 2015-06-12: 22.5; 2015-06-19: 19; 2015-06-26: 16; 2015-07-03: 6; 2015-07-10: 18; 2015-07-17: 9; 2015-07-24: 8; 2015-07-31: 8; 2015-08-07: 8; 2015-08-14: 7; 2015-08-21: 7; 2015-08-28: 158.5
| 410 | 410 Process Design | 2015-06-05: 38; 2015-06-12: 47; 2015-06-19: 20; 2015-07-24: 0; 2015-08-28: 105
| 460 | 460 Structural Design | 2015-05-22: 20; 2015-05-29: 24; 2015-06-05: 24; 2015-06-12: 70; 2015-06-19: 44; 2015-06-26: 48; 2015-07-03: 48; 2015-07-10: 45; 2015-07-17: 60; 2015-07-24: 60; 2015-07-31: 60; 2015-08-07: 60; 2015-08-14: 60; 2015-08-21: 60; 2015-08-28: 683
| 470 | 470 Pipeline Design | 2015-05-15: 57.5; 2015-05-22: 39.5; 2015-05-29: 62; 2015-06-05: 80; 2015-06-12: 92; 2015-06-19: 60; 2015-06-26: 108; 2015-07-03: 74.5; 2015-07-10: 90; 2015-07-17: 115.5; 2015-07-24: 128; 2015-07-31: 128.5; 2015-08-07: 94.5; 2015-08-14: 144.5; 2015-08-21: 60.5; 2015-08-28: 1335
| 480 | 480 Civil - Earthworks Design | 2015-05-08: 8; 2015-05-22: 0.5; 2015-05-29: 0.5; 2015-06-05: 13.5; 2015-06-12: 5; 2015-06-19: 24; 2015-06-26: 17.5; 2015-07-03: 13; 2015-07-10: 2; 2015-08-28: 84
| 490 | 490 Eng.Application Services | 2015-06-05: 4; 2015-06-12: 2.5; 2015-06-19: 1; 2015-06-26: 4.5; 2015-07-03: 3; 2015-07-10: 2; 2015-07-17: 10; 2015-07-24: 7; 2015-07-31: 9.5; 2015-08-07: 5.5; 2015-08-14: 30.5; 2015-08-21: 11; 2015-08-28: 90.5
| Gran | Grand Total | 2015-05-01: 21.75; 2015-05-08: 67; 2015-05-15: 134; 2015-05-22: 99.5; 2015-05-29: 193.5; 2015-06-05: 386; 2015-06-12: 505.5; 2015-06-19: 454; 2015-06-26: 471; 2015-07-03: 393; 2015-07-10: 448; 2015-07-17: 511; 2015-07-24: 444; 2015-07-31: 489.5; 2015-08-07: 485; 2015-08-14: 523.75; 2015-08-21: 331.5; 2015-08-28: 5958

## Progress (hidden)
XXX001.8E Client Project Phase 1A Flowlines
EV Progress Cummulative (From P6)
| As of: | 2015-08-21
|  |  | Budgeted | Earned | Remaining | Check | 2015-05-01 | 2015-05-08 | 2015-05-15 | 2015-05-22 | 2015-05-29 | 2015-06-05 | 2015-06-12 | 2015-06-19 | 2015-06-26 | 2015-07-03 | 2015-07-10 | 2015-07-17 | 2015-07-24 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-21 | 2015-08-28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27 | 2015-12-04 | 2015-12-11 | 2015-12-18 | 2015-12-25 | 2016-01-01 | 2016-01-08 | 2016-01-15 | 2016-01-22 | 2016-01-29 | 2016-02-05 | 2016-02-12 | 2016-02-19 | 2016-02-26 | 2016-03-04 | 2016-03-11 | 2016-03-18 | 2016-03-25 | 2016-04-01 | 2016-04-08 | 2016-04-15 | 2016-04-22 | 2016-04-29 | 2016-05-06 | 2016-05-13 | 2016-05-20 | 2016-05-27 | 2016-06-03 | 2016-06-10 | 2016-06-17 | 2016-06-24
| 01. | Project Management | 2601 | 1077.25 | 1523.75 | 0 | 0 | 0 | 0 | 0 | 61 | 149.94 | 238.89 | 327.83 | 416.78 | 486.43 | 574.82 | 663.21 | 751.61 | 838.71 | 906.86 | 992.06 | 1077.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 200 | Project Management | 1306 | 393 | 913 | 0 | 0 | 0 | 0 | 0 | 46 | 75.91 | 105.83 | 135.74 | 165.66 | 189.59 | 219.5 | 249.41 | 279.33 | 309.24 | 333.17 | 363.09 | 393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 210 | Project Engineer | 636 | 360.5 | 275.5 | 0 | 0 | 0 | 0 | 0 | 0 | 31.08 | 62.16 | 93.23 | 124.31 | 149.17 | 180.25 | 211.33 | 242.41 | 273.48 | 298.34 | 329.42 | 360.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 240 | Quality Assurance | 136 | 60.5 | 75.5 | 0 | 0 | 0 | 0 | 0 | 0 | 6.55 | 13.1 | 19.66 | 26.21 | 29.95 | 35.94 | 41.94 | 47.94 | 52.66 | 54.9 | 57.7 | 60.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 290 | Project Administration | 483 | 263.25 | 219.75 | 0 | 0 | 0 | 0 | 0 | 15 | 36.4 | 57.8 | 79.2 | 100.6 | 117.72 | 139.13 | 160.53 | 181.93 | 203.33 | 220.45 | 241.85 | 263.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 390 | Regulatory Affairs | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 02. | Project Controls | 1438.5 | 744.5 | 694 | 0 | 0 | 0 | 0 | 0 | 53.5 | 104.97 | 156.44 | 209.91 | 251.38 | 281.32 | 329.76 | 415.69 | 500.46 | 579.44 | 642.67 | 712.34 | 744.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 230 | Project Controls | 1041.5 | 487.5 | 554 | 0 | 0 | 0 | 0 | 0 | 53.5 | 94.97 | 136.44 | 177.91 | 219.38 | 249.32 | 288.38 | 327.44 | 365.33 | 397.44 | 423.17 | 455.34 | 487.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 250 | Estimating | 397 | 257 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 32 | 32 | 32 | 41.38 | 88.25 | 135.13 | 182 | 219.5 | 257 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 03. | Document Control | 806 | 189 | 617 | 0 | 0 | 0 | 0 | 0 | 8 | 23.6 | 39.21 | 54.81 | 70.41 | 82.9 | 98.5 | 114.1 | 129.71 | 145.31 | 157.79 | 173.4 | 189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 280 | Document Control | 806 | 189 | 617 | 0 | 0 | 0 | 0 | 0 | 8 | 23.6 | 39.21 | 54.81 | 70.41 | 82.9 | 98.5 | 114.1 | 129.71 | 145.31 | 157.79 | 173.4 | 189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 04. | Process Engineering & Design | 981.5 | 550.75 | 430.75 | 0 | 0 | 0 | 0 | 0 | 138.5 | 245.32 | 336.96 | 418.5 | 457.43 | 480.05 | 501.49 | 513.19 | 522.8 | 532.41 | 540.1 | 545.9 | 550.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 310 | Process Engineering | 701.5 | 410.75 | 290.75 | 0 | 0 | 0 | 0 | 0 | 138.5 | 204.69 | 255.71 | 296.62 | 327.43 | 350.05 | 371.01 | 380.33 | 387.56 | 394.79 | 400.58 | 405.9 | 410.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 410 | P&ID Design & Drafting | 280 | 140 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 40.63 | 81.25 | 121.88 | 130 | 130 | 130.48 | 132.86 | 135.24 | 137.62 | 139.52 | 140 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 05. | Mechanical & Stress Engineering | 1045 | 150.5 | 894.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 114.43 | 132.46 | 150.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 320 | Mechanical Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 321 | Stress Engineering | 1045 | 150.5 | 894.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 114.43 | 132.46 | 150.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 06. | Electrical Engineering & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 330 | Electrical Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 430 | Electrical Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 07. | Instrumentation & Controls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 340 | Instrumentation Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 440 | Instrumentation Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 350 | Controls Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 450 | Controls Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 06. | Structural Engineering & Design | 4644 | 1335.65 | 3308.35 | 0 | 0 | 0 | 0 | 0 | 63 | 168.88 | 274.76 | 380.64 | 486.52 | 571.23 | 678.95 | 793.65 | 908.35 | 1021.97 | 1111.6 | 1223.62 | 1335.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 360 | Structural Engineering | 2134 | 593.15 | 1540.85 | 0 | 0 | 0 | 0 | 0 | 19 | 73.45 | 127.9 | 182.35 | 236.81 | 280.37 | 333.27 | 379.55 | 425.83 | 471.04 | 505.93 | 549.54 | 593.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 460 | Structural Design | 2510 | 742.5 | 1767.5 | 0 | 0 | 0 | 0 | 0 | 44 | 95.43 | 146.86 | 198.29 | 249.71 | 290.86 | 345.68 | 414.1 | 482.52 | 550.93 | 605.67 | 674.08 | 742.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 07. | Piping Design & EAS | 204 | 90.5 | 113.5 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8 | 15.6 | 23.41 | 31.21 | 37.45 | 45.25 | 53.05 | 60.85 | 68.66 | 74.9 | 82.7 | 90.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 420 | Piping Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 490 | Eng. Application Services | 204 | 90.5 | 113.5 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8 | 15.6 | 23.41 | 31.21 | 37.45 | 45.25 | 53.05 | 60.85 | 68.66 | 74.9 | 82.7 | 90.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08. | Pipeline Engineering & Design | 7079 | 1378.82 | 5700.18 | 0 | 0 | 0 | 0 | 0 | 168 | 253.86 | 339.71 | 425.56 | 527.91 | 609.1 | 710.28 | 819.83 | 931.56 | 1041.97 | 1128.69 | 1237.09 | 1378.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 370 | Pipeline Engineering | 1613 | 231.28 | 1381.72 | 0 | 0 | 0 | 0 | 0 | 9 | 25.56 | 42.12 | 58.67 | 86.81 | 108.98 | 136.53 | 155.52 | 172.41 | 188.64 | 200.82 | 216.05 | 231.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 470 | Pipeline Design | 5466 | 1147.54 | 4318.46 | 0 | 0 | 0 | 0 | 0 | 159 | 228.3 | 297.59 | 366.89 | 441.1 | 500.12 | 573.75 | 664.31 | 759.15 | 853.33 | 927.87 | 1021.04 | 1147.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 09. | Civil Engineering & Design | 503 | 233 | 270 | 0 | 0 | 0 | 0 | 0 | 24 | 54.89 | 85.78 | 116.67 | 147.56 | 172.28 | 203.16 | 212.72 | 216.95 | 221.17 | 224.55 | 228.78 | 233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 380 | Civil - Earthworks Engineering | 237 | 144 | 93 | 0 | 0 | 0 | 0 | 0 | 15 | 32.56 | 50.11 | 67.67 | 85.23 | 99.28 | 116.83 | 123.72 | 127.95 | 132.17 | 135.55 | 139.78 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 480 | Civil - Earthworks Design | 266 | 89 | 177 | 0 | 0 | 0 | 0 | 0 | 9 | 22.33 | 35.67 | 49 | 62.33 | 73 | 86.33 | 89 | 89 | 89 | 89 | 89 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12. | Procurement & Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 19302 | 5749.97 | 13552.03 | 0 | 0 | 0 | 0 | 0 | 516 | 1009.26 | 1487.35 | 1957.33 | 2389.2 | 2720.76 | 3142.21 | 3585.44 | 4072.29 | 4549.64 | 4901.59 | 5328.35 | 5749.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Project Management Team | 4845.5 | 2010.75 | 2834.75 |  | 0 | 0 | 0 | 0 | 122.5 | 278.51 | 434.54 | 592.55 | 738.57 | 850.65 | 1003.08 | 1193 | 1381.78 | 1563.46 | 1707.32 | 1877.8 | 2010.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Engineering & Design | 14456.5 | 3739.22 | 10717.28 |  | 0 | 0 | 0 | 0 | 393.5 | 730.75 | 1052.81 | 1364.78 | 1650.63 | 1870.11 | 2139.13 | 2392.44 | 2690.51 | 2986.18 | 3194.27 | 3450.55 | 3739.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Error | 0 | 0 | 0
Paste |  | Progress Cummulative | Budgeted | Earned | Remaining | And Here ->
Here -> |  | Total | 19302 | 5749.97 | 13552.03 | Check | 2015-05-01 | 2015-05-08 | 2015-05-15 | 2015-05-22 | 2015-05-29 | 2015-06-05 | 2015-06-12 | 2015-06-19 | 2015-06-26 | 2015-07-03 | 2015-07-10 | 2015-07-17 | 2015-07-24 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-21 | 2015-08-28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | 2015-09-25 | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 | 2015-10-30 | 2015-11-06 | 2015-11-13 | 2015-11-20 | 2015-11-27 | 2015-12-04 | 2015-12-11 | 2015-12-18 | 2015-12-25 | 2016-01-01 | 2016-01-08 | 2016-01-15 | 2016-01-22 | 2016-01-29 | 2016-02-05 | 2016-02-12 | 2016-02-19 | 2016-02-26 | 2016-03-04 | 2016-03-11 | 2016-03-18 | 2016-03-25 | 2016-04-01 | 2016-04-08 | 2016-04-15 | 2016-04-22 | 2016-04-29 | 2016-05-06 | 2016-05-13 | 2016-05-20 | 2016-05-27 | 2016-06-03 | 2016-06-10 | 2016-06-17 | 2016-06-24
| 200 | R200 Project Management | 1306 | 393 | 913 | 0 |  |  |  |  | 46 | 75.91 | 105.83 | 135.74 | 165.66 | 189.59 | 219.5 | 249.41 | 279.33 | 309.24 | 333.17 | 363.09 | 393
| 210 | R210 Project Engineering | 636 | 360.5 | 275.5 | 0 | [5 empty] | 31.08 | 62.16 | 93.23 | 124.31 | 149.17 | 180.25 | 211.33 | 242.41 | 273.48 | 298.34 | 329.42 | 360.5
| 230 | R230 Project Controls | 1041.5 | 487.5 | 554 | 0 |  |  |  |  | 53.5 | 94.97 | 136.44 | 177.91 | 219.38 | 249.32 | 288.38 | 327.44 | 365.33 | 397.44 | 423.17 | 455.34 | 487.5
| 240 | R240 Quality Assurance | 136 | 60.5 | 75.5 | 0 | [5 empty] | 6.55 | 13.1 | 19.66 | 26.21 | 29.95 | 35.94 | 41.94 | 47.94 | 52.66 | 54.9 | 57.7 | 60.5
| 250 | R250 Estimating | 397 | 257 | 140 | 0 | [5 empty] | 10 | 20 | 32 | 32 | 32 | 41.38 | 88.25 | 135.13 | 182 | 219.5 | 257 | 257
| 280 | R280 Document Control | 806 | 189 | 617 | 0 |  |  |  |  | 8 | 23.6 | 39.21 | 54.81 | 70.41 | 82.9 | 98.5 | 114.1 | 129.71 | 145.31 | 157.79 | 173.4 | 189
| 290 | R290 Project Secretarial | 483 | 263.25 | 219.75 | 0 |  |  |  |  | 15 | 36.4 | 57.8 | 79.2 | 100.6 | 117.72 | 139.13 | 160.53 | 181.93 | 203.33 | 220.45 | 241.85 | 263.25
| 310 | R310 Process Engineering | 701.5 | 410.75 | 290.75 | 0 |  |  |  |  | 138.5 | 204.69 | 255.71 | 296.62 | 327.43 | 350.05 | 371.01 | 380.33 | 387.56 | 394.79 | 400.58 | 405.9 | 410.75
| 321 | R321 Stress Engineering | 1045 | 150.5 | 894.5 | 0 | [12 empty] | 50 | 100 | 114.43 | 132.46 | 150.5
| 360 | R360 Structural Engineering | 2134 | 593.15 | 1540.85 | 0 |  |  |  |  | 19 | 73.45 | 127.9 | 182.35 | 236.81 | 280.37 | 333.27 | 379.55 | 425.83 | 471.04 | 505.93 | 549.54 | 593.15
| 370 | R370 Pipeline Engineering | 1613 | 231.28 | 1381.72 | 0 |  |  |  |  | 9 | 25.56 | 42.12 | 58.67 | 86.81 | 108.98 | 136.53 | 155.52 | 172.41 | 188.64 | 200.82 | 216.05 | 231.28
| 380 | R380 Civil - Earthworks Engineering | 237 | 144 | 93 | 0 |  |  |  |  | 15 | 32.56 | 50.11 | 67.67 | 85.23 | 99.28 | 116.83 | 123.72 | 127.95 | 132.17 | 135.55 | 139.78 | 144
| 390 | R390 Environmental Engineering | 40 | 0 | 40 | 0
| 410 | R410 Process Design | 280 | 140 | 140 | 0 | [5 empty] | 40.63 | 81.25 | 121.88 | 130 | 130 | 130.48 | 132.86 | 135.24 | 137.62 | 139.52 | 140 | 140
| 460 | R460 Structural Design | 2510 | 742.5 | 1767.5 | 0 |  |  |  |  | 44 | 95.43 | 146.86 | 198.29 | 249.71 | 290.86 | 345.68 | 414.1 | 482.52 | 550.93 | 605.67 | 674.08 | 742.5
| 470 | R470 Pipeline Design | 5466 | 1147.54 | 4318.46 | 0 |  |  |  |  | 159 | 228.3 | 297.59 | 366.89 | 441.1 | 500.12 | 573.75 | 664.31 | 759.15 | 853.33 | 927.87 | 1021.04 | 1147.54
| 480 | R480 Civil - Earthworks Design | 266 | 89 | 177 | 0 |  |  |  |  | 9 | 22.33 | 35.67 | 49 | 62.33 | 73 | 86.33 | 89 | 89 | 89 | 89 | 89 | 89
| 490 | R490 Engineering Application Services | 204 | 90.5 | 113.5 | 0 | [5 empty] | 7.8 | 15.6 | 23.41 | 31.21 | 37.45 | 45.25 | 53.05 | 60.85 | 68.66 | 74.9 | 82.7 | 90.5
0
0
0
0
0
0
0

## Forecast (hidden)
XXX001.8E Client Project Phase 1A Flowlines
EV Progress Cummulative (From P6)
| As of: | 2015-08-21
|  |  | Budgeted | Earned | Remaining | time axis 2015-05-01 to 2016-06-24
| 01. | Project Management | 2601 | 1077.25 | 1523.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.35 | 58.35 | 46.68 | 58.35 | 58.35 | 58.35 | 58.35 | 46.68 | 58.35 | 58.35 | 58.35 | 58.35 | 58.35 | 78.35 | 78.35 | 58.35 | 58.35 | 0 | 0 | 58.35 | 58.35 | 58.35 | 58.35 | 58.35 | 58.35 | 46.68 | 58.35 | 3 | 3.75 | 3.75 | 3 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3 | 3.75 | 3.75 | 3.75 | 2.25
| 200 | Project Management | 1306 | 393 | 913 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.42 | 37.42 | 29.93 | 37.42 | 37.42 | 37.42 | 37.42 | 29.93 | 37.42 | 37.42 | 37.42 | 37.42 | 37.42 | 37.42 | 37.42 | 37.42 | 37.42 | 0 | 0 | 37.42 | 37.42 | 37.42 | 37.42 | 37.42 | 37.42 | 29.93 | 37.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 210 | Project Engineer | 636 | 360.5 | 275.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.83 | 8.83 | 7.07 | 8.83 | 8.83 | 8.83 | 8.83 | 7.07 | 8.83 | 8.83 | 8.83 | 8.83 | 8.83 | 8.83 | 8.83 | 8.83 | 8.83 | 0 | 0 | 8.83 | 8.83 | 8.83 | 8.83 | 8.83 | 8.83 | 7.07 | 8.83 | 3 | 3.75 | 3.75 | 3 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3 | 3.75 | 3.75 | 3.75 | 2.25
| 240 | Quality Assurance | 136 | 60.5 | 75.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.09 | 3.09 | 2.48 | 3.09 | 3.09 | 3.09 | 3.09 | 2.48 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 0 | 0 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 2.48 | 3.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 290 | Project Administration | 483 | 263.25 | 219.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.01 | 9.01 | 7.2 | 9.01 | 9.01 | 9.01 | 9.01 | 7.2 | 9.01 | 9.01 | 9.01 | 9.01 | 9.01 | 9.01 | 9.01 | 9.01 | 9.01 | 0 | 0 | 9.01 | 9.01 | 9.01 | 9.01 | 9.01 | 9.01 | 7.2 | 9.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 390 | Regulatory Affairs | 40 | 0 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 02. | Project Controls | 1438.5 | 744.5 | 694 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.13 | 60.93 | 16.75 | 20.93 | 20.93 | 20.93 | 20.93 | 16.75 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 0 | 0 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 26.26 | 27.42 | 34.26 | 15.33 | 15.83 | 15.83 | 12.67 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2.5 | 2.5 | 2.5 | 1.5
| 230 | Project Controls | 1041.5 | 487.5 | 554 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.13 | 20.93 | 16.75 | 20.93 | 20.93 | 20.93 | 20.93 | 16.75 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 0 | 0 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 16.75 | 20.93 | 2 | 2.5 | 2.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2.5 | 2.5 | 2.5 | 1.5
| 250 | Estimating | 397 | 257 | 140 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.33 | 10.67 | 13.33 | 13.33 | 13.33 | 13.33 | 10.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 03. | Document Control | 806 | 189 | 617 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.83 | 22.83 | 18.26 | 22.83 | 22.83 | 22.83 | 22.83 | 18.26 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 0 | 0 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 18.26 | 22.83 | 3 | 3.75 | 3.75 | 3 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3 | 3.75 | 3.75 | 3.75 | 2.25
| 280 | Document Control | 806 | 189 | 617 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.83 | 22.83 | 18.26 | 22.83 | 22.83 | 22.83 | 22.83 | 18.26 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 0 | 0 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 18.26 | 22.83 | 3 | 3.75 | 3.75 | 3 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3 | 3.75 | 3.75 | 3.75 | 2.25
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 04. | Process Engineering & Design | 981.5 | 550.75 | 430.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.61 | 15.61 | 4.09 | 5.11 | 5.11 | 24.98 | 42.23 | 30.59 | 38.23 | 42.23 | 38.23 | 39.03 | 19.44 | 19.44 | 42.54 | 38.61 | 5.69 | 0 | 0 | 0 | 0.13 | 0.67 | 0.67 | 0.67 | 0.67 | 0.53 | 0.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 310 | Process Engineering | 701.5 | 410.75 | 290.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.61 | 15.61 | 4.09 | 5.11 | 5.11 | 12.79 | 21.92 | 14.34 | 17.92 | 21.92 | 17.92 | 18.72 | 19.44 | 19.44 | 32.54 | 38.61 | 5.69 | 0 | 0 | 0 | 0.13 | 0.67 | 0.67 | 0.67 | 0.67 | 0.53 | 0.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 410 | P&ID Design & Drafting | 280 | 140 | 140 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.19 | 20.31 | 16.25 | 20.31 | 20.31 | 20.31 | 20.31 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 05. | Mechanical & Stress Engineering | 1045 | 150.5 | 894.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.93 | 64.93 | 51.94 | 64.93 | 64.93 | 64.93 | 64.93 | 32.19 | 32 | 32 | 32 | 32 | 32 | 42.56 | 49.6 | 49.6 | 49.6 | 0 | 0 | 49.6 | 19.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 320 | Mechanical Engineering | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 321 | Stress Engineering | 1045 | 150.5 | 894.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.93 | 64.93 | 51.94 | 64.93 | 64.93 | 64.93 | 64.93 | 32.19 | 32 | 32 | 32 | 32 | 32 | 42.56 | 49.6 | 49.6 | 49.6 | 0 | 0 | 49.6 | 19.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 06. | Electrical Engineering & Design | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 330 | Electrical Engineering | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 430 | Electrical Design | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 07. | Instrumentation & Controls | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 340 | Instrumentation Engineering | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 440 | Instrumentation Design | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 350 | Controls Engineering | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 450 | Controls Design | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 06. | Structural Engineering & Design | 4644 | 1335.65 | 3308.35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126.37 | 126.37 | 101.1 | 138.35 | 141.34 | 141.34 | 149.34 | 119.08 | 151.34 | 158.02 | 149.14 | 149.14 | 149.14 | 133.19 | 151.45 | 148.16 | 148.16 | 0 | 0 | 148.16 | 121.3 | 107.82 | 107.82 | 117.34 | 131.62 | 86.18 | 36.05 | 16 | 0 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 6 | 10 | 8 | 6 | 6 | 9 | 0
| 360 | Structural Engineering | 2134 | 593.15 | 1540.85 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.11 | 47.11 | 37.69 | 52.69 | 54.08 | 54.08 | 58.08 | 49.27 | 64.08 | 63.82 | 56.98 | 56.98 | 56.98 | 53.9 | 71.1 | 73.77 | 73.77 | 0 | 0 | 73.77 | 60.94 | 54.6 | 54.6 | 70.3 | 93.86 | 61.97 | 28.29 | 16 | 0 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 6 | 10 | 8 | 6 | 6 | 9 | 0
| 460 | Structural Design | 2510 | 742.5 | 1767.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.26 | 79.26 | 63.41 | 85.66 | 87.26 | 87.26 | 91.26 | 69.81 | 87.26 | 94.2 | 92.16 | 92.16 | 92.16 | 79.29 | 80.35 | 74.39 | 74.39 | 0 | 0 | 74.39 | 60.36 | 53.22 | 53.22 | 47.04 | 37.76 | 24.21 | 7.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 07. | Piping Design & EAS | 204 | 90.5 | 113.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.56 | 5.56 | 4.45 | 5.56 | 5.56 | 5.56 | 5.56 | 4.45 | 5.56 | 5.56 | 5.56 | 5.56 | 5.56 | 5.56 | 5.56 | 5.56 | 5.56 | 0 | 0 | 5.56 | 5.56 | 5.56 | 4.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 420 | Piping Design | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 490 | Eng. Application Services | 204 | 90.5 | 113.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.56 | 5.56 | 4.45 | 5.56 | 5.56 | 5.56 | 5.56 | 4.45 | 5.56 | 5.56 | 5.56 | 5.56 | 5.56 | 5.56 | 5.56 | 5.56 | 5.56 | 0 | 0 | 5.56 | 5.56 | 5.56 | 4.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08. | Pipeline Engineering & Design | 7079 | 1378.82 | 5700.18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.73 | 196.73 | 157.38 | 282.01 | 303.33 | 304.64 | 310.88 | 215.13 | 266.31 | 289.53 | 272.83 | 292.03 | 274.33 | 259.49 | 286.64 | 268.74 | 202.29 | 0 | 0 | 142.19 | 139.19 | 141.99 | 141.38 | 140.46 | 134.46 | 88.7 | 56.46 | 22.42 | 25.4 | 13.9 | 21.23 | 22.87 | 24.1 | 7.4 | 2.5 | 4.17 | 11.57 | 16.5 | 31.5 | 23.27 | 29.8 | 34.7 | 22.5 | 22.5
| 370 | Pipeline Engineering | 1613 | 231.28 | 1381.72 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.68 | 34.68 | 27.74 | 39.47 | 40.67 | 41.32 | 47.18 | 28.24 | 35.3 | 49.55 | 45.72 | 52.92 | 54.05 | 52.88 | 77.33 | 77.63 | 51.08 | 0 | 0 | 29.58 | 27.78 | 28.98 | 33.97 | 41.47 | 39.77 | 31.64 | 35.9 | 21 | 24 | 13.2 | 20.4 | 21.6 | 22.8 | 7.2 | 2.4 | 4 | 11.2 | 16 | 30.4 | 22.4 | 28.8 | 33.6 | 21.6 | 21.6
| 470 | Pipeline Design | 5466 | 1147.54 | 4318.46 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162.05 | 162.05 | 129.64 | 242.54 | 262.66 | 263.32 | 263.7 | 186.89 | 231.01 | 239.98 | 227.11 | 239.11 | 220.28 | 206.61 | 209.31 | 191.11 | 151.21 | 0 | 0 | 112.61 | 111.41 | 113.01 | 107.41 | 98.99 | 94.69 | 57.06 | 20.56 | 1.42 | 1.4 | 0.7 | 0.83 | 1.27 | 1.3 | 0.2 | 0.1 | 0.17 | 0.37 | 0.5 | 1.1 | 0.87 | 1 | 1.1 | 0.9 | 0.9
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 09. | Civil Engineering & Design | 503 | 233 | 270 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.98 | 25.98 | 22.58 | 30.33 | 31.73 | 37.88 | 33.38 | 15.68 | 18.23 | 17.23 | 5.73 | 5.73 | 4.58 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 380 | Civil - Earthworks Engineering | 237 | 144 | 93 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.79 | 5.79 | 5.03 | 6.89 | 7.29 | 13.29 | 15.29 | 5.43 | 6.29 | 9.29 | 3.79 | 3.79 | 3.03 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 480 | Civil - Earthworks Design | 266 | 89 | 177 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.19 | 20.19 | 17.55 | 23.44 | 24.44 | 24.59 | 18.09 | 10.25 | 11.94 | 7.94 | 1.94 | 1.94 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12. | Procurement & Contracts | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 500 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 510 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 550 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 19302 | 5749.97 | 13552.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551.49 | 577.29 | 423.23 | 628.4 | 654.11 | 681.44 | 708.43 | 498.81 | 613.78 | 646.68 | 605.6 | 625.6 | 587.16 | 582.35 | 661.9 | 612.78 | 513.41 | 0 | 0 | 447.62 | 388.13 | 358.15 | 356.43 | 360.58 | 374.19 | 267.77 | 208.62 | 59.75 | 48.73 | 38.23 | 43.9 | 37.87 | 34.1 | 17.4 | 12.5 | 14.17 | 21.57 | 32.5 | 51.5 | 39.27 | 45.8 | 50.7 | 41.5 | 28.5
|  | Project Management Team | 4845.5 | 2010.75 | 2834.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125.31 | 142.11 | 81.69 | 102.11 | 102.11 | 102.11 | 102.11 | 81.69 | 102.11 | 102.11 | 102.11 | 102.11 | 102.11 | 122.11 | 122.11 | 102.11 | 102.11 | 0 | 0 | 102.11 | 102.11 | 102.11 | 102.11 | 102.11 | 107.44 | 92.36 | 115.44 | 21.33 | 23.33 | 23.33 | 18.67 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 10 | 10 | 10 | 6
|  | Engineering & Design | 14456.5 | 3739.22 | 10717.28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426.18 | 435.18 | 341.54 | 526.29 | 552 | 579.33 | 606.32 | 417.12 | 511.67 | 544.57 | 503.49 | 523.49 | 485.05 | 460.24 | 539.79 | 510.67 | 411.3 | 0 | 0 | 345.51 | 286.02 | 256.04 | 254.32 | 258.47 | 266.75 | 175.41 | 93.18 | 38.42 | 25.4 | 14.9 | 25.23 | 27.87 | 24.1 | 7.4 | 2.5 | 4.17 | 11.57 | 22.5 | 41.5 | 31.27 | 35.8 | 40.7 | 31.5 | 22.5
|  | Error | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | 0.01 | 0 | -0.01 | 0 | 0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | 0 | 0 | 0 | 0 | -0.01 | 0 | -0.01 | -0.01 | -0.01 | 0 | -0.01 | -0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Paste
Here -> |  | Activity Name | Budgeted Units | Actual Units | Remaining Units | Spreadsheet Field | time axis 2015-04-25 to 2016-06-18
|  | Total | 19302 | 5749.97 | 13552.03 | Remaining Units | [17 empty] | 551.48 | 577.28 | 423.23 | 628.39 | 654.11 | 681.45 | 708.43 | 498.8 | 613.79 | 646.69 | 605.61 | 625.61 | 587.17 | 582.36 | 661.91 | 612.78 | 513.41 |  |  | 447.63 | 388.13 | 358.16 | 356.44 | 360.59 | 374.19 | 267.78 | 208.63 | 59.75 | 48.73 | 38.23 | 43.9 | 37.87 | 34.1 | 17.4 | 12.5 | 14.17 | 21.57 | 32.5 | 51.5 | 39.27 | 45.8 | 50.7 | 41.5 | 28.5
| 200 | R200 Project Management | 1306 | 393 | 913 | Remaining Units | 2015-08-22: 37.42; 2015-08-29: 37.42; 2015-09-05: 29.93; 2015-09-12: 37.42; 2015-09-19: 37.42; 2015-09-26: 37.42; 2015-10-03: 37.42; 2015-10-10: 29.93; 2015-10-17: 37.42; 2015-10-24: 37.42; 2015-10-31: 37.42; 2015-11-07: 37.42; 2015-11-14: 37.42; 2015-11-21: 37.42; 2015-11-28: 37.42; 2015-12-05: 37.42; 2015-12-12: 37.42; 2016-01-02: 37.42; 2016-01-09: 37.42; 2016-01-16: 37.42; 2016-01-23: 37.42; 2016-01-30: 37.42; 2016-02-06: 37.42; 2016-02-13: 29.93; 2016-02-20: 37.42
| 210 | R210 Project Engineering | 636 | 360.5 | 275.5 | Remaining Units | [17 empty] | 8.83 | 8.83 | 7.07 | 8.83 | 8.83 | 8.83 | 8.83 | 7.07 | 8.83 | 8.83 | 8.83 | 8.83 | 8.83 | 8.83 | 8.83 | 8.83 | 8.83 |  |  | 8.83 | 8.83 | 8.83 | 8.83 | 8.83 | 8.83 | 7.07 | 8.83 | 3 | 3.75 | 3.75 | 3 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3 | 3.75 | 3.75 | 3.75 | 2.25
| 230 | R230 Project Controls | 1041.5 | 487.5 | 554 | Remaining Units | [17 empty] | 24.13 | 20.93 | 16.75 | 20.93 | 20.93 | 20.93 | 20.93 | 16.75 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 |  |  | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 16.75 | 20.93 | 2 | 2.5 | 2.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2.5 | 2.5 | 2.5 | 1.5
| 240 | R240 Quality Assurance | 136 | 60.5 | 75.5 | Remaining Units | 2015-08-22: 3.09; 2015-08-29: 3.09; 2015-09-05: 2.48; 2015-09-12: 3.09; 2015-09-19: 3.09; 2015-09-26: 3.09; 2015-10-03: 3.09; 2015-10-10: 2.48; 2015-10-17: 3.09; 2015-10-24: 3.09; 2015-10-31: 3.09; 2015-11-07: 3.09; 2015-11-14: 3.09; 2015-11-21: 3.09; 2015-11-28: 3.09; 2015-12-05: 3.09; 2015-12-12: 3.09; 2016-01-02: 3.09; 2016-01-09: 3.09; 2016-01-16: 3.09; 2016-01-23: 3.09; 2016-01-30: 3.09; 2016-02-06: 3.09; 2016-02-13: 2.48; 2016-02-20: 3.09
| 250 | R250 Estimating | 397 | 257 | 140 | Remaining Units | 2015-08-22: 20; 2015-08-29: 40; 2016-02-06: 5.33; 2016-02-13: 10.67; 2016-02-20: 13.33; 2016-02-27: 13.33; 2016-03-05: 13.33; 2016-03-12: 13.33; 2016-03-19: 10.67
| 280 | R280 Document Control | 806 | 189 | 617 | Remaining Units | [17 empty] | 22.83 | 22.83 | 18.26 | 22.83 | 22.83 | 22.83 | 22.83 | 18.26 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 |  |  | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 22.83 | 18.26 | 22.83 | 3 | 3.75 | 3.75 | 3 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3.75 | 3 | 3.75 | 3.75 | 3.75 | 2.25
| 290 | R290 Project Secretarial | 483 | 263.25 | 219.75 | Remaining Units | 2015-08-22: 9.01; 2015-08-29: 9.01; 2015-09-05: 7.2; 2015-09-12: 9.01; 2015-09-19: 9.01; 2015-09-26: 9.01; 2015-10-03: 9.01; 2015-10-10: 7.2; 2015-10-17: 9.01; 2015-10-24: 9.01; 2015-10-31: 9.01; 2015-11-07: 9.01; 2015-11-14: 9.01; 2015-11-21: 9.01; 2015-11-28: 9.01; 2015-12-05: 9.01; 2015-12-12: 9.01; 2016-01-02: 9.01; 2016-01-09: 9.01; 2016-01-16: 9.01; 2016-01-23: 9.01; 2016-01-30: 9.01; 2016-02-06: 9.01; 2016-02-13: 7.2; 2016-02-20: 9.01
| 310 | R310 Process Engineering | 701.5 | 410.75 | 290.75 | Remaining Units | 2015-08-22: 15.61; 2015-08-29: 15.61; 2015-09-05: 4.09; 2015-09-12: 5.11; 2015-09-19: 5.11; 2015-09-26: 12.79; 2015-10-03: 21.92; 2015-10-10: 14.34; 2015-10-17: 17.92; 2015-10-24: 21.92; 2015-10-31: 17.92; 2015-11-07: 18.72; 2015-11-14: 19.44; 2015-11-21: 19.44; 2015-11-28: 32.54; 2015-12-05: 38.61; 2015-12-12: 5.69; 2016-01-09: 0.13; 2016-01-16: 0.67; 2016-01-23: 0.67; 2016-01-30: 0.67; 2016-02-06: 0.67; 2016-02-13: 0.53; 2016-02-20: 0.67
| 321 | R321 Stress Engineering | 1045 | 150.5 | 894.5 | Remaining Units | 2015-08-22: 64.93; 2015-08-29: 64.93; 2015-09-05: 51.94; 2015-09-12: 64.93; 2015-09-19: 64.93; 2015-09-26: 64.93; 2015-10-03: 64.93; 2015-10-10: 32.19; 2015-10-17: 32; 2015-10-24: 32; 2015-10-31: 32; 2015-11-07: 32; 2015-11-14: 32; 2015-11-21: 42.56; 2015-11-28: 49.6; 2015-12-05: 49.6; 2015-12-12: 49.6; 2016-01-02: 49.6; 2016-01-09: 19.84
| 360 | R360 Structural Engineering | 2134 | 593.15 | 1540.85 | Remaining Units | 2015-08-22: 47.11; 2015-08-29: 47.11; 2015-09-05: 37.69; 2015-09-12: 52.69; 2015-09-19: 54.08; 2015-09-26: 54.08; 2015-10-03: 58.08; 2015-10-10: 49.27; 2015-10-17: 64.08; 2015-10-24: 63.82; 2015-10-31: 56.98; 2015-11-07: 56.98; 2015-11-14: 56.98; 2015-11-21: 53.9; 2015-11-28: 71.1; 2015-12-05: 73.77; 2015-12-12: 73.77; 2016-01-02: 73.77; 2016-01-09: 60.94; 2016-01-16: 54.6; 2016-01-23: 54.6; 2016-01-30: 70.3; 2016-02-06: 93.86; 2016-02-13: 61.97; 2016-02-20: 28.29; 2016-02-27: 16; 2016-03-12: 1; 2016-03-19: 4; 2016-03-26: 5; 2016-05-07: 6; 2016-05-14: 10; 2016-05-21: 8; 2016-05-28: 6; 2016-06-04: 6; 2016-06-11: 9
| 370 | R370 Pipeline Engineering | 1613 | 231.28 | 1381.72 | Remaining Units | [17 empty] | 34.68 | 34.68 | 27.74 | 39.47 | 40.67 | 41.32 | 47.18 | 28.24 | 35.3 | 49.55 | 45.72 | 52.92 | 54.05 | 52.88 | 77.33 | 77.63 | 51.08 |  |  | 29.58 | 27.78 | 28.98 | 33.97 | 41.47 | 39.77 | 31.64 | 35.9 | 21 | 24 | 13.2 | 20.4 | 21.6 | 22.8 | 7.2 | 2.4 | 4 | 11.2 | 16 | 30.4 | 22.4 | 28.8 | 33.6 | 21.6 | 21.6
| 380 | R380 Civil - Earthworks Engineering | 237 | 144 | 93 | Remaining Units | 2015-08-22: 3.79; 2015-08-29: 5.79; 2015-09-05: 5.03; 2015-09-12: 6.89; 2015-09-19: 7.29; 2015-09-26: 13.29; 2015-10-03: 15.29; 2015-10-10: 5.43; 2015-10-17: 6.29; 2015-10-24: 9.29; 2015-10-31: 3.79; 2015-11-07: 3.79; 2015-11-14: 3.03; 2015-11-28: 4
| 390 | R390 Environmental Engineering | 40 | 0 | 40 | Remaining Units | 2015-11-21: 20; 2015-11-28: 20
| 410 | R410 Process Design | 280 | 140 | 140 | Remaining Units | 2015-09-26: 12.19; 2015-10-03: 20.31; 2015-10-10: 16.25; 2015-10-17: 20.31; 2015-10-24: 20.31; 2015-10-31: 20.31; 2015-11-07: 20.31; 2015-11-28: 10
| 460 | R460 Structural Design | 2510 | 742.5 | 1767.5 | Remaining Units | 2015-08-22: 79.26; 2015-08-29: 79.26; 2015-09-05: 63.41; 2015-09-12: 85.66; 2015-09-19: 87.26; 2015-09-26: 87.26; 2015-10-03: 91.26; 2015-10-10: 69.81; 2015-10-17: 87.26; 2015-10-24: 94.2; 2015-10-31: 92.16; 2015-11-07: 92.16; 2015-11-14: 92.16; 2015-11-21: 79.29; 2015-11-28: 80.35; 2015-12-05: 74.39; 2015-12-12: 74.39; 2016-01-02: 74.39; 2016-01-09: 60.36; 2016-01-16: 53.22; 2016-01-23: 53.22; 2016-01-30: 47.04; 2016-02-06: 37.76; 2016-02-13: 24.21; 2016-02-20: 7.76
| 470 | R470 Pipeline Design | 5466 | 1147.54 | 4318.46 | Remaining Units | [17 empty] | 162.05 | 162.05 | 129.64 | 242.54 | 262.66 | 263.32 | 263.7 | 186.89 | 231.01 | 239.98 | 227.11 | 239.11 | 220.28 | 206.61 | 209.31 | 191.11 | 151.21 |  |  | 112.61 | 111.41 | 113.01 | 107.41 | 98.99 | 94.69 | 57.06 | 20.56 | 1.42 | 1.4 | 0.7 | 0.83 | 1.27 | 1.3 | 0.2 | 0.1 | 0.17 | 0.37 | 0.5 | 1.1 | 0.87 | 1 | 1.1 | 0.9 | 0.9
| 480 | R480 Civil - Earthworks Design | 266 | 89 | 177 | Remaining Units | 2015-08-22: 13.19; 2015-08-29: 20.19; 2015-09-05: 17.55; 2015-09-12: 23.44; 2015-09-19: 24.44; 2015-09-26: 24.59; 2015-10-03: 18.09; 2015-10-10: 10.25; 2015-10-17: 11.94; 2015-10-24: 7.94; 2015-10-31: 1.94; 2015-11-07: 1.94; 2015-11-14: 1.55
| 490 | R490 Engineering Application Services | 204 | 90.5 | 113.5 | Remaining Units | 2015-08-22: 5.56; 2015-08-29: 5.56; 2015-09-05: 4.45; 2015-09-12: 5.56; 2015-09-19: 5.56; 2015-09-26: 5.56; 2015-10-03: 5.56; 2015-10-10: 4.45; 2015-10-17: 5.56; 2015-10-24: 5.56; 2015-10-31: 5.56; 2015-11-07: 5.56; 2015-11-14: 5.56; 2015-11-21: 5.56; 2015-11-28: 5.56; 2015-12-05: 5.56; 2015-12-12: 5.56; 2016-01-02: 5.56; 2016-01-09: 5.56; 2016-01-16: 5.56; 2016-01-23: 4.45
0
0
0

## MOC (hidden)
XXX001.8E Client Project Phase 1A Flowlines
Changes Cummulative Hours (From P6)
| As of: | 2015-08-21
|  |  | Budgeted | Earned | Remaining | time axis 2015-05-01 to 2016-06-24
| 01. | Project Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 200 | Project Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 210 | Project Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 240 | Quality Assurance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 290 | Project Administration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 390 | Regulatory Affairs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 02. | Project Controls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 230 | Project Controls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 250 | Estimating | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 03. | Document Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 280 | Document Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 04. | Process Engineering & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 310 | Process Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 410 | P&ID Design & Drafting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 05. | Mechanical & Stress Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 320 | Mechanical Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 321 | Stress Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 06. | Electrical Engineering & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 330 | Electrical Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 430 | Electrical Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 07. | Instrumentation & Controls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 340 | Instrumentation Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 440 | Instrumentation Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 350 | Controls Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 450 | Controls Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 06. | Structural Engineering & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 360 | Structural Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 460 | Structural Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 07. | Piping Design & EAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 420 | Piping Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 490 | Eng. Application Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08. | Pipeline Engineering & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 370 | Pipeline Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 470 | Pipeline Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 09. | Civil Engineering & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 380 | Civil - Earthworks Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 480 | Civil - Earthworks Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12. | Procurement & Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Project Management Team | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Engineering & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Error | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And Here ->
Paste |  |  | Budgeted | Earned | Remaining | Week # 1 | Week # 2 | Week # 3 | Week # 4 | Week # 5 | Week # 6 | Week # 7 | Week # 8 | Week # 9 | Week # 10 | Week # 11 | Week # 12 | Week # 13 | Week # 14 | Week # 15 | Week # 16 | Week # 17 | Week # 18 | Week # 19 | Week # 20 | Week # 21 | Week # 22 | Week # 23 | Week # 24 | Week # 25 | Week # 26 | Week # 27 | Week # 28 | Week # 29 | Week # 30 | Week # 31 | Week # 32 | Week # 33 | Week # 34 | Week # 35 | Week # 36 | Week # 37 | Week # 38 | Week # 39 | Week # 40 | Week # 41 | Week # 42 | Week # 43 | Week # 44 | Week # 45 | Week # 46 | Week # 47 | Week # 48 | Week # 49 | Week # 50 | Week # 51 | Week # 52 | Week # 53 | Week # 54 | Week # 55 | Week # 56 | Week # 57 | Week # 58 | Week # 59 | Week # 60 | Week # 61
Here |  | TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
->

## Baseline (hidden)
XXX001.8E Client Project Phase 1A Flowlines
Baseline Cummulative Hours (From P6)
| As of: | 2015-08-21
|  |  | Budgeted | Earned | Remaining | time axis 2015-05-01 to 2016-06-24
| 01. | Project Management | 2601 | 0 | 2601 |  | 12.71 | 25.42 | 38.13 | 48.3 | 61 | 131.75 | 202.5 | 273.25 | 344 | 399.1 | 471.85 | 544.6 | 611.6 | 678.6 | 732.2 | 799.2 | 866.2 | 933.2 | 1000.2 | 1053.8 | 1120.8 | 1187.8 | 1254.8 | 1321.8 | 1375.4 | 1442.4 | 1509.4 | 1576.4 | 1643.4 | 1710.4 | 1797.4 | 1884.4 | 1951.4 | 2018.4 | 2018.4 | 2018.4 | 2085.4 | 2152.4 | 2219.4 | 2286.4 | 2353.4 | 2420.4 | 2474 | 2541 | 2544 | 2547.75 | 2551.5 | 2554.5 | 2558.25 | 2562 | 2565.75 | 2569.5 | 2573.25 | 2577 | 2580.75 | 2584.5 | 2587.5 | 2591.25 | 2595 | 2598.75 | 2601
| 200 | Project Management | 1306 | 0 | 1306 |  | 9.58 | 19.17 | 28.75 | 36.42 | 46 | 81 | 116 | 151 | 186 | 214 | 249 | 284 | 319 | 354 | 382 | 417 | 452 | 487 | 522 | 550 | 585 | 620 | 655 | 690 | 718 | 753 | 788 | 823 | 858 | 893 | 928 | 963 | 998 | 1033 | 1033 | 1033 | 1068 | 1103 | 1138 | 1173 | 1208 | 1243 | 1271 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306
| 210 | Project Engineer | 636 | 0 | 636 |  | 0 | 0 | 0 | 0 | 0 | 16 | 32 | 48 | 64 | 76.8 | 92.8 | 108.8 | 124.8 | 140.8 | 153.6 | 169.6 | 185.6 | 201.6 | 217.6 | 230.4 | 246.4 | 262.4 | 278.4 | 294.4 | 307.2 | 323.2 | 339.2 | 355.2 | 371.2 | 387.2 | 403.2 | 419.2 | 435.2 | 451.2 | 451.2 | 451.2 | 467.2 | 483.2 | 499.2 | 515.2 | 531.2 | 547.2 | 560 | 576 | 579 | 582.75 | 586.5 | 589.5 | 593.25 | 597 | 600.75 | 604.5 | 608.25 | 612 | 615.75 | 619.5 | 622.5 | 626.25 | 630 | 633.75 | 636
| 240 | Quality Assurance | 136 | 0 | 136 |  | 0 | 0 | 0 | 0 | 0 | 6.75 | 13.5 | 20.25 | 27 | 30.9 | 39.65 | 48.4 | 51.4 | 54.4 | 56.8 | 59.8 | 62.8 | 65.8 | 68.8 | 71.2 | 74.2 | 77.2 | 80.2 | 83.2 | 85.6 | 88.6 | 91.6 | 94.6 | 97.6 | 100.6 | 103.6 | 106.6 | 109.6 | 112.6 | 112.6 | 112.6 | 115.6 | 118.6 | 121.6 | 124.6 | 127.6 | 130.6 | 133 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136
| 290 | Project Administration | 483 | 0 | 483 |  | 3.13 | 6.25 | 9.38 | 11.88 | 15 | 28 | 41 | 54 | 67 | 77.4 | 90.4 | 103.4 | 116.4 | 129.4 | 139.8 | 152.8 | 165.8 | 178.8 | 191.8 | 202.2 | 215.2 | 228.2 | 241.2 | 254.2 | 264.6 | 277.6 | 290.6 | 303.6 | 316.6 | 329.6 | 342.6 | 355.6 | 368.6 | 381.6 | 381.6 | 381.6 | 394.6 | 407.6 | 420.6 | 433.6 | 446.6 | 459.6 | 470 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483
| 390 | Regulatory Affairs | 40 | 0 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 02. | Project Controls | 1438.5 | 0 | 1438.5 |  | 11.15 | 22.29 | 33.44 | 42.35 | 53.5 | 98.52 | 143.55 | 190.57 | 225.59 | 251.7 | 297.2 | 378.7 | 447.7 | 516.7 | 575.46 | 648.9 | 682.9 | 716.9 | 780.9 | 800.1 | 824.1 | 848.1 | 872.1 | 896.1 | 915.3 | 939.3 | 963.3 | 987.3 | 1011.3 | 1035.3 | 1059.3 | 1083.3 | 1107.3 | 1131.3 | 1131.3 | 1131.3 | 1155.3 | 1179.3 | 1203.3 | 1227.3 | 1251.3 | 1280.63 | 1310.5 | 1347.83 | 1363.17 | 1379 | 1394.83 | 1407.5 | 1410 | 1412.5 | 1415 | 1417.5 | 1420 | 1422.5 | 1425 | 1427.5 | 1429.5 | 1432 | 1434.5 | 1437 | 1438.5
| 230 | Project Controls | 1041.5 | 0 | 1041.5 |  | 11.15 | 22.29 | 33.44 | 42.35 | 53.5 | 88.52 | 123.55 | 158.57 | 193.59 | 219.7 | 256.2 | 292.7 | 316.7 | 340.7 | 363.46 | 391.9 | 415.9 | 439.9 | 463.9 | 483.1 | 507.1 | 531.1 | 555.1 | 579.1 | 598.3 | 622.3 | 646.3 | 670.3 | 694.3 | 718.3 | 742.3 | 766.3 | 790.3 | 814.3 | 814.3 | 814.3 | 838.3 | 862.3 | 886.3 | 910.3 | 934.3 | 958.3 | 977.5 | 1001.5 | 1003.5 | 1006 | 1008.5 | 1010.5 | 1013 | 1015.5 | 1018 | 1020.5 | 1023 | 1025.5 | 1028 | 1030.5 | 1032.5 | 1035 | 1037.5 | 1040 | 1041.5
| 250 | Estimating | 397 | 0 | 397 |  | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 32 | 32 | 32 | 41 | 86 | 131 | 176 | 212 | 257 | 267 | 277 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 322.33 | 333 | 346.33 | 359.67 | 373 | 386.33 | 397 | 397 | 397 | 397 | 397 | 397 | 397 | 397 | 397 | 397 | 397 | 397 | 397 | 397
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 03. | Document Control | 806 | 0 | 806 |  | 1.67 | 3.33 | 5 | 6.33 | 8 | 28.5 | 49 | 69.5 | 90 | 106.4 | 126.9 | 147.4 | 167.9 | 188.4 | 204.8 | 225.3 | 245.8 | 266.3 | 286.8 | 303.2 | 323.7 | 344.2 | 364.7 | 385.2 | 401.6 | 422.1 | 442.6 | 463.1 | 483.6 | 504.1 | 524.6 | 545.1 | 565.6 | 586.1 | 586.1 | 586.1 | 606.6 | 627.1 | 647.6 | 668.1 | 688.6 | 709.1 | 725.5 | 746 | 749 | 752.75 | 756.5 | 759.5 | 763.25 | 767 | 770.75 | 774.5 | 778.25 | 782 | 785.75 | 789.5 | 792.5 | 796.25 | 800 | 803.75 | 806
| 280 | Document Control | 806 | 0 | 806 |  | 1.67 | 3.33 | 5 | 6.33 | 8 | 28.5 | 49 | 69.5 | 90 | 106.4 | 126.9 | 147.4 | 167.9 | 188.4 | 204.8 | 225.3 | 245.8 | 266.3 | 286.8 | 303.2 | 323.7 | 344.2 | 364.7 | 385.2 | 401.6 | 422.1 | 442.6 | 463.1 | 483.6 | 504.1 | 524.6 | 545.1 | 565.6 | 586.1 | 586.1 | 586.1 | 606.6 | 627.1 | 647.6 | 668.1 | 688.6 | 709.1 | 725.5 | 746 | 749 | 752.75 | 756.5 | 759.5 | 763.25 | 767 | 770.75 | 774.5 | 778.25 | 782 | 785.75 | 789.5 | 792.5 | 796.25 | 800 | 803.75 | 806
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 04. | Process Engineering & Design | 981.5 | 0 | 981.5 |  | 27.7 | 73.87 | 120.03 | 138.5 | 138.5 | 249.88 | 357.84 | 463.5 | 481.5 | 495.9 | 504.5 | 514.5 | 524.5 | 534.5 | 542.5 | 558 | 573.5 | 578.5 | 583.5 | 587.5 | 596.5 | 601.5 | 626.38 | 664.5 | 695 | 733.12 | 776.46 | 816.58 | 857.9 | 879.9 | 899.5 | 939 | 973.5 | 977.5 | 977.5 | 977.5 | 977.5 | 977.63 | 978.3 | 978.97 | 979.63 | 980.3 | 980.83 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5
| 310 | Process Engineering | 701.5 | 0 | 701.5 |  | 27.7 | 73.87 | 120.03 | 138.5 | 138.5 | 206.55 | 271.17 | 333.5 | 351.5 | 365.9 | 374 | 381.5 | 389 | 396.5 | 402.5 | 418 | 433.5 | 438.5 | 443.5 | 447.5 | 456.5 | 461.5 | 474.19 | 492 | 506.25 | 524.06 | 547.08 | 566.89 | 587.9 | 609.9 | 629.5 | 659 | 693.5 | 697.5 | 697.5 | 697.5 | 697.5 | 697.63 | 698.3 | 698.97 | 699.63 | 700.3 | 700.83 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5
| 410 | P&ID Design & Drafting | 280 | 0 | 280 |  | 0 | 0 | 0 | 0 | 0 | 43.33 | 86.67 | 130 | 130 | 130 | 130.5 | 133 | 135.5 | 138 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 152.19 | 172.5 | 188.75 | 209.06 | 229.38 | 249.69 | 270 | 270 | 270 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 05. | Mechanical & Stress Engineering | 1045 | 0 | 1045 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 150.5 | 213.63 | 276.75 | 339.88 | 403 | 453.5 | 516.63 | 579.75 | 624.2 | 656.2 | 681.8 | 713.8 | 745.8 | 777.8 | 816.84 | 866.44 | 916.04 | 965.64 | 1015.24 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045
| 320 | Mechanical Engineering | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 321 | Stress Engineering | 1045 | 0 | 1045 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 150.5 | 213.63 | 276.75 | 339.88 | 403 | 453.5 | 516.63 | 579.75 | 624.2 | 656.2 | 681.8 | 713.8 | 745.8 | 777.8 | 816.84 | 866.44 | 916.04 | 965.64 | 1015.24 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 06. | Electrical Engineering & Design | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 330 | Electrical Engineering | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 430 | Electrical Design | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 07. | Instrumentation & Controls | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 340 | Instrumentation Engineering | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 440 | Instrumentation Design | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 350 | Controls Engineering | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 450 | Controls Design | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 06. | Structural Engineering & Design | 4644 | 0 | 4644 |  | 0 | 0 | 22.5 | 40.5 | 63 | 171.8 | 280.59 | 389.39 | 498.17 | 585.21 | 696.93 | 819.92 | 942.9 | 1064.82 | 1161.07 | 1281.4 | 1401.72 | 1522.03 | 1642.35 | 1738.6 | 1881.11 | 2019.17 | 2157.23 | 2295.28 | 2411.72 | 2559.78 | 2714.52 | 2860.37 | 3009.43 | 3163.28 | 3298.29 | 3448.36 | 3595.14 | 3738.71 | 3738.71 | 3738.71 | 3877.49 | 3994.19 | 4100.63 | 4207.07 | 4323.03 | 4453.26 | 4538.34 | 4573 | 4589 | 4589 | 4590 | 4594 | 4599 | 4599 | 4599 | 4599 | 4599 | 4599 | 4605 | 4615 | 4623 | 4629 | 4635 | 4644 | 4644
| 360 | Structural Engineering | 2134 | 0 | 2134 |  | 0 | 0 | 6.79 | 12.21 | 19 | 73.37 | 127.73 | 182.1 | 236.46 | 279.95 | 333.16 | 381.3 | 429.44 | 476.51 | 512.89 | 558.37 | 603.84 | 649.31 | 694.78 | 731.16 | 787 | 840.43 | 893.87 | 947.3 | 996.04 | 1059.47 | 1122.65 | 1178.98 | 1238.51 | 1302.84 | 1359.98 | 1431.13 | 1504.94 | 1575.55 | 1575.55 | 1575.55 | 1641.36 | 1699.13 | 1753.77 | 1808.42 | 1878.76 | 1972.66 | 2034.67 | 2063 | 2079 | 2079 | 2080 | 2084 | 2089 | 2089 | 2089 | 2089 | 2089 | 2089 | 2095 | 2105 | 2113 | 2119 | 2125 | 2134 | 2134
| 460 | Structural Design | 2510 | 0 | 2510 |  | 0 | 0 | 15.71 | 28.29 | 44 | 98.43 | 152.86 | 207.29 | 261.71 | 305.26 | 363.77 | 438.62 | 513.46 | 588.31 | 648.18 | 723.03 | 797.88 | 872.72 | 947.57 | 1007.44 | 1094.11 | 1178.74 | 1263.36 | 1347.98 | 1415.68 | 1500.31 | 1591.87 | 1681.39 | 1770.92 | 1860.44 | 1938.31 | 2017.23 | 2090.2 | 2163.16 | 2163.16 | 2163.16 | 2236.13 | 2295.06 | 2346.86 | 2398.65 | 2444.27 | 2480.6 | 2503.67 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 07. | Piping Design & EAS | 204 | 0 | 204 |  | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 20 | 24 | 29 | 34 | 39 | 44 | 48 | 53 | 58 | 63 | 68 | 72 | 77 | 82 | 87 | 92 | 96 | 101 | 106 | 111 | 116 | 121 | 126 | 131 | 136 | 141 | 141 | 141 | 146 | 151 | 156 | 161 | 166 | 171 | 175 | 180 | 181.2 | 182.7 | 184.2 | 185.4 | 186.9 | 188.4 | 189.9 | 191.4 | 192.9 | 194.4 | 195.9 | 197.4 | 198.6 | 200.1 | 201.6 | 203.1 | 204
| 420 | Piping Design | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 490 | Eng. Application Services | 204 | 0 | 204 |  | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 15 | 20 | 24 | 29 | 34 | 39 | 44 | 48 | 53 | 58 | 63 | 68 | 72 | 77 | 82 | 87 | 92 | 96 | 101 | 106 | 111 | 116 | 121 | 126 | 131 | 136 | 141 | 141 | 141 | 146 | 151 | 156 | 161 | 166 | 171 | 175 | 180 | 181.2 | 182.7 | 184.2 | 185.4 | 186.9 | 188.4 | 189.9 | 191.4 | 192.9 | 194.4 | 195.9 | 197.4 | 198.6 | 200.1 | 201.6 | 203.1 | 204
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 08. | Pipeline Engineering & Design | 7079 | 0 | 7079 |  | 34.94 | 70.93 | 106.94 | 134.67 | 168 | 264.3 | 360.59 | 456.89 | 568.52 | 657.82 | 769.16 | 976.41 | 1207.74 | 1437.75 | 1620.15 | 1848.15 | 2076.15 | 2304.16 | 2510.22 | 2663.37 | 2903.31 | 3126.6 | 3351.21 | 3561.95 | 3712.87 | 3901.52 | 4143.91 | 4388.8 | 4606.7 | 4847.21 | 5071.07 | 5338.29 | 5599.2 | 5795.47 | 5795.47 | 5795.47 | 5932.84 | 6061.5 | 6189.17 | 6321.93 | 6457.56 | 6592.9 | 6685.34 | 6742.68 | 6765.1 | 6790.5 | 6804.4 | 6825.63 | 6848.5 | 6872.6 | 6880 | 6882.5 | 6886.67 | 6898.23 | 6914.73 | 6946.23 | 6969.5 | 6999.3 | 7034 | 7056.5 | 7079
| 370 | Pipeline Engineering | 1613 | 0 | 1613 |  | 1.88 | 3.75 | 5.63 | 7.13 | 9 | 32.01 | 55.02 | 78.03 | 112.04 | 139.24 | 173.11 | 207.05 | 241.07 | 274.42 | 300.3 | 332.65 | 365 | 397.36 | 426.11 | 447.19 | 485.69 | 517.22 | 549.41 | 579.43 | 600.33 | 626.46 | 677.63 | 732.17 | 777.72 | 819.77 | 858.85 | 926.58 | 998.21 | 1045.09 | 1045.09 | 1045.09 | 1071.67 | 1090.75 | 1107.23 | 1134.41 | 1172.88 | 1215.35 | 1252.19 | 1290.8 | 1311.8 | 1335.8 | 1349 | 1369.4 | 1391 | 1413.8 | 1421 | 1423.4 | 1427.4 | 1438.6 | 1454.6 | 1485 | 1507.4 | 1536.2 | 1569.8 | 1591.4 | 1613
| 470 | Pipeline Design | 5466 | 0 | 5466 |  | 33.06 | 67.18 | 101.31 | 127.54 | 159 | 232.29 | 305.57 | 378.86 | 456.48 | 518.58 | 596.05 | 769.36 | 966.67 | 1163.33 | 1319.85 | 1515.5 | 1711.15 | 1906.8 | 2084.11 | 2216.18 | 2417.62 | 2609.38 | 2801.8 | 2982.52 | 3112.54 | 3275.06 | 3466.28 | 3656.63 | 3828.98 | 4027.44 | 4212.22 | 4411.71 | 4600.99 | 4750.38 | 4750.38 | 4750.38 | 4861.17 | 4970.75 | 5081.94 | 5187.52 | 5284.68 | 5377.55 | 5433.15 | 5451.88 | 5453.3 | 5454.7 | 5455.4 | 5456.23 | 5457.5 | 5458.8 | 5459 | 5459.1 | 5459.27 | 5459.63 | 5460.13 | 5461.23 | 5462.1 | 5463.1 | 5464.2 | 5465.1 | 5466
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 09. | Civil Engineering & Design | 503 | 0 | 503 |  | 8.57 | 17.14 | 24 | 24 | 24 | 55.66 | 87.34 | 119 | 150.66 | 176 | 207.66 | 228.09 | 245.71 | 263.32 | 277.41 | 295.03 | 316.03 | 337.9 | 359.77 | 377.26 | 407.4 | 428 | 443 | 458 | 467 | 474.5 | 485 | 490 | 495 | 499 | 499 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503
| 380 | Civil - Earthworks Engineering | 237 | 0 | 237 |  | 5.36 | 10.71 | 15 | 15 | 15 | 32.33 | 49.67 | 67 | 84.33 | 98.2 | 115.53 | 123.11 | 128.25 | 133.38 | 137.49 | 142.63 | 148.56 | 154.7 | 160.84 | 165.75 | 182.1 | 192.6 | 199.1 | 205.6 | 209.8 | 213.8 | 221.8 | 225.8 | 229.8 | 233 | 233 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237
| 480 | Civil - Earthworks Design | 266 | 0 | 266 |  | 3.21 | 6.43 | 9 | 9 | 9 | 23.33 | 37.67 | 52 | 66.33 | 77.8 | 92.13 | 104.98 | 117.46 | 129.94 | 139.92 | 152.4 | 167.47 | 183.2 | 198.93 | 211.51 | 225.3 | 235.4 | 243.9 | 252.4 | 257.2 | 260.7 | 263.2 | 264.2 | 265.2 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266
| 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12. | Procurement & Contracts | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 500 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 510 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 550 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grand Total | 19302 | 0 | 19302 |  | 96.74 | 212.98 | 350.04 | 434.65 | 516 | 1005.41 | 1491.41 | 1977.1 | 2378.44 | 2696.13 | 3103.2 | 3643.62 | 4237.05 | 4828.09 | 5312.09 | 5922.61 | 6497.05 | 7061.87 | 7634.74 | 8049.33 | 8650.55 | 9217.12 | 9780.62 | 10331.03 | 10756.69 | 11287.52 | 11886.99 | 12471.35 | 13040.17 | 13626.63 | 14191.2 | 14838.09 | 15446.38 | 15936.48 | 15936.48 | 15936.48 | 16329.13 | 16691.12 | 17042.4 | 17398.77 | 17767.52 | 18155.59 | 18437.51 | 18660.01 | 18720.97 | 18771.2 | 18810.93 | 18856.03 | 18895.4 | 18931 | 18949.9 | 18963.9 | 18979.57 | 19002.63 | 19036.63 | 19089.63 | 19130.1 | 19177.4 | 19229.6 | 19272.6 | 19302
|  | Project Management Team | 4845.5 | 0 | 4845.5 |  | 25.53 | 51.04 | 76.57 | 96.98 | 122.5 | 258.77 | 395.05 | 533.32 | 659.59 | 757.2 | 895.95 | 1070.7 | 1227.2 | 1383.7 | 1512.46 | 1673.4 | 1794.9 | 1916.4 | 2067.9 | 2157.1 | 2268.6 | 2380.1 | 2491.6 | 2603.1 | 2692.3 | 2803.8 | 2915.3 | 3026.8 | 3138.3 | 3249.8 | 3381.3 | 3512.8 | 3624.3 | 3735.8 | 3735.8 | 3735.8 | 3847.3 | 3958.8 | 4070.3 | 4181.8 | 4293.3 | 4410.13 | 4510 | 4634.83 | 4656.17 | 4679.5 | 4702.83 | 4721.5 | 4731.5 | 4741.5 | 4751.5 | 4761.5 | 4771.5 | 4781.5 | 4791.5 | 4801.5 | 4809.5 | 4819.5 | 4829.5 | 4839.5 | 4845.5
|  | Engineering & Design | 14456.5 | 0 | 14456.5 |  | 71.21 | 161.94 | 273.47 | 337.67 | 393.5 | 746.64 | 1096.36 | 1443.78 | 1718.85 | 1938.93 | 2207.25 | 2572.92 | 3009.85 | 3444.39 | 3799.63 | 4249.21 | 4702.15 | 5145.47 | 5566.84 | 5892.23 | 6381.95 | 6837.02 | 7289.02 | 7727.93 | 8064.39 | 8483.72 | 8971.69 | 9444.55 | 9901.87 | 10376.83 | 10809.9 | 11325.29 | 11822.08 | 12200.68 | 12200.68 | 12200.68 | 12481.83 | 12732.32 | 12972.1 | 13216.97 | 13474.22 | 13745.46 | 13927.51 | 14025.18 | 14064.8 | 14091.7 | 14108.1 | 14134.53 | 14163.9 | 14189.5 | 14198.4 | 14202.4 | 14208.07 | 14221.13 | 14245.13 | 14288.13 | 14320.6 | 14357.9 | 14400.1 | 14433.1 | 14456.5
|  | Error | 0 | 0 | 0 |  | 0.01 | 0 | 0.01 | 0 | 0 | 0 | 0.02 | 0.01 | -0.01 | 0 | 0 | 0.01 | 0 | 0.01 | 0 | 0.01 | -0.01 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0.02 | 0 | 0.01 | 0.01 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | 0 | -0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Paste
Here -> |  | Activity Name | Budgeted Units | Actual Units | Remaining Units | Spreadsheet Field | time axis 2015-04-25 to 2016-06-18
|  | Total | 19302 | 0 | 19302 | Cum Budgeted Units | 96.73 | 212.98 | 350.03 | 434.65 | 516 | 1005.41 | 1491.39 | 1977.09 | 2378.45 | 2696.13 | 3103.2 | 3643.61 | 4237.05 | 4828.08 | 5312.09 | 5922.6 | 6497.06 | 7061.87 | 7634.74 | 8049.33 | 8650.55 | 9217.12 | 9780.61 | 10331.03 | 10756.69 | 11287.52 | 11886.97 | 12471.35 | 13040.16 | 13626.62 | 14191.2 | 14838.08 | 15446.38 | 15936.48 | 15936.48 | 15936.48 | 16329.12 | 16691.12 | 17042.4 | 17398.76 | 17767.52 | 18155.59 | 18437.51 | 18660.02 | 18720.97 | 18771.2 | 18810.93 | 18856.03 | 18895.4 | 18931 | 18949.9 | 18963.9 | 18979.57 | 19002.63 | 19036.63 | 19089.63 | 19130.1 | 19177.4 | 19229.6 | 19272.6 | 19302
| 200 | R200 Project Management | 1306 | 0 | 1306 | Cum Budgeted Units | 9.58 | 19.17 | 28.75 | 36.42 | 46 | 81 | 116 | 151 | 186 | 214 | 249 | 284 | 319 | 354 | 382 | 417 | 452 | 487 | 522 | 550 | 585 | 620 | 655 | 690 | 718 | 753 | 788 | 823 | 858 | 893 | 928 | 963 | 998 | 1033 | 1033 | 1033 | 1068 | 1103 | 1138 | 1173 | 1208 | 1243 | 1271 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306 | 1306
| 210 | R210 Project Engineering | 636 | 0 | 636 | Cum Budgeted Units | [5 empty] | 16 | 32 | 48 | 64 | 76.8 | 92.8 | 108.8 | 124.8 | 140.8 | 153.6 | 169.6 | 185.6 | 201.6 | 217.6 | 230.4 | 246.4 | 262.4 | 278.4 | 294.4 | 307.2 | 323.2 | 339.2 | 355.2 | 371.2 | 387.2 | 403.2 | 419.2 | 435.2 | 451.2 | 451.2 | 451.2 | 467.2 | 483.2 | 499.2 | 515.2 | 531.2 | 547.2 | 560 | 576 | 579 | 582.75 | 586.5 | 589.5 | 593.25 | 597 | 600.75 | 604.5 | 608.25 | 612 | 615.75 | 619.5 | 622.5 | 626.25 | 630 | 633.75 | 636
| 230 | R230 Project Controls | 1041.5 | 0 | 1041.5 | Cum Budgeted Units | 11.15 | 22.29 | 33.44 | 42.35 | 53.5 | 88.52 | 123.55 | 158.57 | 193.59 | 219.7 | 256.2 | 292.7 | 316.7 | 340.7 | 363.46 | 391.9 | 415.9 | 439.9 | 463.9 | 483.1 | 507.1 | 531.1 | 555.1 | 579.1 | 598.3 | 622.3 | 646.3 | 670.3 | 694.3 | 718.3 | 742.3 | 766.3 | 790.3 | 814.3 | 814.3 | 814.3 | 838.3 | 862.3 | 886.3 | 910.3 | 934.3 | 958.3 | 977.5 | 1001.5 | 1003.5 | 1006 | 1008.5 | 1010.5 | 1013 | 1015.5 | 1018 | 1020.5 | 1023 | 1025.5 | 1028 | 1030.5 | 1032.5 | 1035 | 1037.5 | 1040 | 1041.5
| 240 | R240 Quality Assurance | 136 | 0 | 136 | Cum Budgeted Units | [5 empty] | 6.75 | 13.5 | 20.25 | 27 | 30.9 | 39.65 | 48.4 | 51.4 | 54.4 | 56.8 | 59.8 | 62.8 | 65.8 | 68.8 | 71.2 | 74.2 | 77.2 | 80.2 | 83.2 | 85.6 | 88.6 | 91.6 | 94.6 | 97.6 | 100.6 | 103.6 | 106.6 | 109.6 | 112.6 | 112.6 | 112.6 | 115.6 | 118.6 | 121.6 | 124.6 | 127.6 | 130.6 | 133 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136
| 250 | R250 Estimating | 397 | 0 | 397 | Cum Budgeted Units | [5 empty] | 10 | 20 | 32 | 32 | 32 | 41 | 86 | 131 | 176 | 212 | 257 | 267 | 277 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 317 | 322.33 | 333 | 346.33 | 359.67 | 373 | 386.33 | 397 | 397 | 397 | 397 | 397 | 397 | 397 | 397 | 397 | 397 | 397 | 397 | 397 | 397
| 280 | R280 Document Control | 806 | 0 | 806 | Cum Budgeted Units | 1.67 | 3.33 | 5 | 6.33 | 8 | 28.5 | 49 | 69.5 | 90 | 106.4 | 126.9 | 147.4 | 167.9 | 188.4 | 204.8 | 225.3 | 245.8 | 266.3 | 286.8 | 303.2 | 323.7 | 344.2 | 364.7 | 385.2 | 401.6 | 422.1 | 442.6 | 463.1 | 483.6 | 504.1 | 524.6 | 545.1 | 565.6 | 586.1 | 586.1 | 586.1 | 606.6 | 627.1 | 647.6 | 668.1 | 688.6 | 709.1 | 725.5 | 746 | 749 | 752.75 | 756.5 | 759.5 | 763.25 | 767 | 770.75 | 774.5 | 778.25 | 782 | 785.75 | 789.5 | 792.5 | 796.25 | 800 | 803.75 | 806
| 290 | R290 Project Secretarial | 483 | 0 | 483 | Cum Budgeted Units | 3.13 | 6.25 | 9.38 | 11.88 | 15 | 28 | 41 | 54 | 67 | 77.4 | 90.4 | 103.4 | 116.4 | 129.4 | 139.8 | 152.8 | 165.8 | 178.8 | 191.8 | 202.2 | 215.2 | 228.2 | 241.2 | 254.2 | 264.6 | 277.6 | 290.6 | 303.6 | 316.6 | 329.6 | 342.6 | 355.6 | 368.6 | 381.6 | 381.6 | 381.6 | 394.6 | 407.6 | 420.6 | 433.6 | 446.6 | 459.6 | 470 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483 | 483
| 310 | R310 Process Engineering | 701.5 | 0 | 701.5 | Cum Budgeted Units | 27.7 | 73.87 | 120.03 | 138.5 | 138.5 | 206.55 | 271.17 | 333.5 | 351.5 | 365.9 | 374 | 381.5 | 389 | 396.5 | 402.5 | 418 | 433.5 | 438.5 | 443.5 | 447.5 | 456.5 | 461.5 | 474.19 | 492 | 506.25 | 524.06 | 547.08 | 566.89 | 587.9 | 609.9 | 629.5 | 659 | 693.5 | 697.5 | 697.5 | 697.5 | 697.5 | 697.63 | 698.3 | 698.97 | 699.63 | 700.3 | 700.83 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5 | 701.5
| 321 | R321 Stress Engineering | 1045 | 0 | 1045 | Cum Budgeted Units | [12 empty] | 50 | 100 | 150.5 | 213.63 | 276.75 | 339.88 | 403 | 453.5 | 516.63 | 579.75 | 624.2 | 656.2 | 681.8 | 713.8 | 745.8 | 777.8 | 816.84 | 866.44 | 916.04 | 965.64 | 1015.24 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045
| 360 | R360 Structural Engineering | 2134 | 0 | 2134 | Cum Budgeted Units |  |  | 6.79 | 12.21 | 19 | 73.37 | 127.73 | 182.1 | 236.46 | 279.95 | 333.16 | 381.3 | 429.44 | 476.51 | 512.89 | 558.37 | 603.84 | 649.31 | 694.78 | 731.16 | 787 | 840.43 | 893.87 | 947.3 | 996.04 | 1059.47 | 1122.65 | 1178.98 | 1238.51 | 1302.84 | 1359.98 | 1431.13 | 1504.94 | 1575.55 | 1575.55 | 1575.55 | 1641.36 | 1699.13 | 1753.77 | 1808.42 | 1878.76 | 1972.66 | 2034.67 | 2063 | 2079 | 2079 | 2080 | 2084 | 2089 | 2089 | 2089 | 2089 | 2089 | 2089 | 2095 | 2105 | 2113 | 2119 | 2125 | 2134 | 2134
| 370 | R370 Pipeline Engineering | 1613 | 0 | 1613 | Cum Budgeted Units | 1.88 | 3.75 | 5.63 | 7.13 | 9 | 32.01 | 55.02 | 78.03 | 112.04 | 139.24 | 173.11 | 207.05 | 241.07 | 274.42 | 300.3 | 332.65 | 365 | 397.36 | 426.11 | 447.19 | 485.69 | 517.22 | 549.41 | 579.43 | 600.33 | 626.46 | 677.63 | 732.17 | 777.72 | 819.77 | 858.85 | 926.58 | 998.21 | 1045.09 | 1045.09 | 1045.09 | 1071.67 | 1090.75 | 1107.23 | 1134.41 | 1172.88 | 1215.35 | 1252.19 | 1290.8 | 1311.8 | 1335.8 | 1349 | 1369.4 | 1391 | 1413.8 | 1421 | 1423.4 | 1427.4 | 1438.6 | 1454.6 | 1485 | 1507.4 | 1536.2 | 1569.8 | 1591.4 | 1613
| 380 | R380 Civil - Earthworks Engineering | 237 | 0 | 237 | Cum Budgeted Units | 5.36 | 10.71 | 15 | 15 | 15 | 32.33 | 49.67 | 67 | 84.33 | 98.2 | 115.53 | 123.11 | 128.25 | 133.38 | 137.49 | 142.63 | 148.56 | 154.7 | 160.84 | 165.75 | 182.1 | 192.6 | 199.1 | 205.6 | 209.8 | 213.8 | 221.8 | 225.8 | 229.8 | 233 | 233 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237 | 237
| 390 | R390 Environmental Engineering | 40 | 0 | 40 | Cum Budgeted Units | 2015-11-21: 20; 2015-11-28: 40; 2015-12-05: 40; 2015-12-12: 40; 2015-12-19: 40; 2015-12-26: 40; 2016-01-02: 40; 2016-01-09: 40; 2016-01-16: 40; 2016-01-23: 40; 2016-01-30: 40; 2016-02-06: 40; 2016-02-13: 40; 2016-02-20: 40; 2016-02-27: 40; 2016-03-05: 40; 2016-03-12: 40; 2016-03-19: 40; 2016-03-26: 40; 2016-04-02: 40; 2016-04-09: 40; 2016-04-16: 40; 2016-04-23: 40; 2016-04-30: 40; 2016-05-07: 40; 2016-05-14: 40; 2016-05-21: 40; 2016-05-28: 40; 2016-06-04: 40; 2016-06-11: 40; 2016-06-18: 40
| 410 | R410 Process Design | 280 | 0 | 280 | Cum Budgeted Units | [5 empty] | 43.33 | 86.67 | 130 | 130 | 130 | 130.5 | 133 | 135.5 | 138 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 152.19 | 172.5 | 188.75 | 209.06 | 229.38 | 249.69 | 270 | 270 | 270 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280
| 460 | R460 Structural Design | 2510 | 0 | 2510 | Cum Budgeted Units |  |  | 15.71 | 28.29 | 44 | 98.43 | 152.86 | 207.29 | 261.71 | 305.26 | 363.77 | 438.62 | 513.46 | 588.31 | 648.18 | 723.03 | 797.88 | 872.72 | 947.57 | 1007.44 | 1094.11 | 1178.74 | 1263.36 | 1347.98 | 1415.68 | 1500.31 | 1591.87 | 1681.39 | 1770.92 | 1860.44 | 1938.31 | 2017.23 | 2090.2 | 2163.16 | 2163.16 | 2163.16 | 2236.13 | 2295.06 | 2346.86 | 2398.65 | 2444.27 | 2480.6 | 2503.67 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510 | 2510
| 470 | R470 Pipeline Design | 5466 | 0 | 5466 | Cum Budgeted Units | 33.06 | 67.18 | 101.31 | 127.54 | 159 | 232.29 | 305.57 | 378.86 | 456.48 | 518.58 | 596.05 | 769.36 | 966.67 | 1163.33 | 1319.85 | 1515.5 | 1711.15 | 1906.8 | 2084.11 | 2216.18 | 2417.62 | 2609.38 | 2801.8 | 2982.52 | 3112.54 | 3275.06 | 3466.28 | 3656.63 | 3828.98 | 4027.44 | 4212.22 | 4411.71 | 4600.99 | 4750.38 | 4750.38 | 4750.38 | 4861.17 | 4970.75 | 5081.94 | 5187.52 | 5284.68 | 5377.55 | 5433.15 | 5451.88 | 5453.3 | 5454.7 | 5455.4 | 5456.23 | 5457.5 | 5458.8 | 5459 | 5459.1 | 5459.27 | 5459.63 | 5460.13 | 5461.23 | 5462.1 | 5463.1 | 5464.2 | 5465.1 | 5466
| 480 | R480 Civil - Earthworks Design | 266 | 0 | 266 | Cum Budgeted Units | 3.21 | 6.43 | 9 | 9 | 9 | 23.33 | 37.67 | 52 | 66.33 | 77.8 | 92.13 | 104.98 | 117.46 | 129.94 | 139.92 | 152.4 | 167.47 | 183.2 | 198.93 | 211.51 | 225.3 | 235.4 | 243.9 | 252.4 | 257.2 | 260.7 | 263.2 | 264.2 | 265.2 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266 | 266
| 490 | R490 Engineering Application Services | 204 | 0 | 204 | Cum Budgeted Units | [5 empty] | 5 | 10 | 15 | 20 | 24 | 29 | 34 | 39 | 44 | 48 | 53 | 58 | 63 | 68 | 72 | 77 | 82 | 87 | 92 | 96 | 101 | 106 | 111 | 116 | 121 | 126 | 131 | 136 | 141 | 141 | 141 | 146 | 151 | 156 | 161 | 166 | 171 | 175 | 180 | 181.2 | 182.7 | 184.2 | 185.4 | 186.9 | 188.4 | 189.9 | 191.4 | 192.9 | 194.4 | 195.9 | 197.4 | 198.6 | 200.1 | 201.6 | 203.1 | 204

## Report
| XXX001.8E Client Project Phase 1A Flowlines | [14 empty] | Earned Value Report as of: | 2015-08-21
| Group | Original | Approved | Control | Approved | Potential | Pending | Forecast | Original | Original | Current | Current | Earned | Earned | Actual | Actual | CPI | SPI
| Discipline | Budget | Changes | Budget | Non Scope | Changes | Changes | at completion | Plan Hours | Plan Percent | Plan Hours | Plan Percent | Hours | Percent | Hours | Percent
01. | Project Management | 2601 | 0 | 2601 | 0 | 0 | 0 | 2601 | 866.2 | 33.3% | 866.2 | 33.3% | 1077.25 | 41.42% | 1077.25 | 41.42% | 1 | 1.2437
200 | Project Management | 1306 | 0 | 1306 | 0 | 0 | 0 | 1306 | 452 | 34.61% | 452 | 34.61% | 393 | 30.09% | 393 | 30.09% | 1 | 0.86947
210 | Project Engineer | 636 | 0 | 636 | 0 | 0 | 0 | 636 | 185.6 | 29.18% | 185.6 | 29.18% | 360.5 | 56.68% | 360.5 | 56.68% | 1 | 1.9423
240 | Quality Assurance | 136 | 0 | 136 | 0 | 0 | 0 | 136 | 62.8 | 46.18% | 62.8 | 46.18% | 60.5 | 44.49% | 60.5 | 44.49% | 1 | 0.96338
290 | Project Administration | 483 | 0 | 483 | 0 | 0 | 0 | 483 | 165.8 | 34.33% | 165.8 | 34.33% | 263.25 | 54.5% | 263.25 | 54.5% | 1 | 1.5878
390 | Regulatory Affairs | 40 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
02. | Project Controls | 1438.5 | 0 | 1438.5 | 0 | 7.75 | 0 | 1446.25 | 682.9 | 47.47% | 682.9 | 47.47% | 744.5 | 51.76% | 752.25 | 52.29% | 0.9897 | 1.0902
230 | Project Controls | 1041.5 | 0 | 1041.5 | 0 | 0 | 0 | 1041.5 | 415.9 | 39.93% | 415.9 | 39.93% | 487.5 | 46.81% | 487.5 | 46.81% | 1 | 1.1722
250 | Estimating | 397 | 0 | 397 | 0 | 7.75 | 0 | 404.75 | 267 | 67.25% | 267 | 67.25% | 257 | 64.74% | 264.75 | 66.69% | 0.97073 | 0.96255
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
03. | Document Control | 806 | 0 | 806 | 0 | 0 | 0 | 806 | 245.8 | 30.5% | 245.8 | 30.5% | 189 | 23.45% | 189 | 23.45% | 1 | 0.76892
280 | Document Control | 806 | 0 | 806 | 0 | 0 | 0 | 806 | 245.8 | 30.5% | 245.8 | 30.5% | 189 | 23.45% | 189 | 23.45% | 1 | 0.76892
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
04. | Process Engineering & Design | 981.5 | 0 | 981.5 | 0 | -5.25 | 0 | 976.25 | 573.5 | 58.43% | 573.5 | 58.43% | 550.75 | 56.11% | 545.5 | 55.58% | 1.0096 | 0.96033
310 | Process Engineering | 701.5 | 0 | 701.5 | 0 | 29.75 | 0 | 731.25 | 433.5 | 61.8% | 433.5 | 61.8% | 410.75 | 58.55% | 440.5 | 62.79% | 0.93246 | 0.94752
410 | P&ID Design & Drafting | 280 | 0 | 280 | 0 | -35 | 0 | 245 | 140 | 50% | 140 | 50% | 140 | 50% | 105 | 37.5% | 1.3333 | 1
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
05. | Mechanical & Stress Engineering | 1045 | 0 | 1045 | 0 | 14.5 | 0 | 1059.5 | 276.75 | 26.48% | 276.75 | 26.48% | 150.5 | 14.4% | 165 | 15.79% | 0.91212 | 0.54381
320 | Mechanical Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
321 | Stress Engineering | 1045 | 0 | 1045 | 0 | 14.5 | 0 | 1059.5 | 276.75 | 26.48% | 276.75 | 26.48% | 150.5 | 14.4% | 165 | 15.79% | 0.91212 | 0.54381
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
06. | Electrical Engineering & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
330 | Electrical Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
430 | Electrical Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
07. | Instrumentation & Controls | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
340 | Instrumentation Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
440 | Instrumentation Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
350 | Controls Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
450 | Controls Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
06. | Structural Engineering & Design | 4644 | 0 | 4644 | 0 | 38.35 | 0 | 4682.35 | 1401.72 | 30.18% | 1401.72 | 30.18% | 1335.65 | 28.76% | 1374 | 29.59% | 0.97209 | 0.95287
360 | Structural Engineering | 2134 | 0 | 2134 | 0 | 97.85 | 0 | 2231.85 | 603.84 | 28.3% | 603.84 | 28.3% | 593.15 | 27.8% | 691 | 32.38% | 0.85839 | 0.9823
460 | Structural Design | 2510 | 0 | 2510 | 0 | -59.5 | 0 | 2450.5 | 797.88 | 31.79% | 797.88 | 31.79% | 742.5 | 29.58% | 683 | 27.21% | 1.0871 | 0.93059
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
07. | Piping Design & EAS | 204 | 0 | 204 | 0 | 0 | 0 | 204 | 58 | 28.43% | 58 | 28.43% | 90.5 | 44.36% | 90.5 | 44.36% | 1 | 1.5603
420 | Piping Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
490 | Eng. Application Services | 204 | 0 | 204 | 0 | 0 | 0 | 204 | 58 | 28.43% | 58 | 28.43% | 90.5 | 44.36% | 90.5 | 44.36% | 1 | 1.5603
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
08. | Pipeline Engineering & Design | 7079 | 0 | 7079 | 0 | 143.18 | 0 | 7222.18 | 2076.15 | 29.33% | 2076.15 | 29.33% | 1378.82 | 19.48% | 1522 | 21.5% | 0.90593 | 0.66412
370 | Pipeline Engineering | 1613 | 0 | 1613 | 0 | -44.28 | 0 | 1568.72 | 365 | 22.63% | 365 | 22.63% | 231.28 | 14.34% | 187 | 11.59% | 1.2368 | 0.63364
470 | Pipeline Design | 5466 | 0 | 5466 | 0 | 187.46 | 0 | 5653.46 | 1711.15 | 31.31% | 1711.15 | 31.31% | 1147.54 | 20.99% | 1335 | 24.42% | 0.85958 | 0.67063
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
09. | Civil Engineering & Design | 503 | 0 | 503 | 0 | 9.5 | 0 | 512.5 | 316.03 | 62.83% | 316.03 | 62.83% | 233 | 46.32% | 242.5 | 48.21% | 0.96082 | 0.73727
380 | Civil - Earthworks Engineering | 237 | 0 | 237 | 0 | 14.5 | 0 | 251.5 | 148.56 | 62.68% | 148.56 | 62.68% | 144 | 60.76% | 158.5 | 66.88% | 0.90852 | 0.96931
480 | Civil - Earthworks Design | 266 | 0 | 266 | 0 | -5 | 0 | 261 | 167.47 | 62.96% | 167.47 | 62.96% | 89 | 33.46% | 84 | 31.58% | 1.0595 | 0.53144
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
12. | Procurement & Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| TOTAL: | 19302 | 0 | 19302 | 0 | 208.03 | 0 | 19510.03 | 6497.05 | 33.66% | 6497.05 | 33.66% | 5749.97 | 29.79% | 5958 | 30.87% | 0.96508 | 0.88501
| Legend: | [5 empty] | Note:
| Control Plan Hours | (Budgeted Cost of Work Scheduled) |  |  |  |  | Current Plan Hours are based on the previous month end ASAP scenario.
| Control Plan Percent | Control Plan Hours / Control Budget
| Baseline Plan Hours | (Budgeted Cost of Work Scheduled) |  |  |  |  | Control Budget includes hours required to perform an additional work as per approved Change Notices.
| Baseline Plan Percent | Baseline Plan Hours / Control Budget
| Earned Hours | (Budgeted Cost of Work Performed) |  |  |  |  | Potential Changes include hours from Initiated Change Notices and the Cummulative Productivity Gap (Actual Hours - Earned Hours)
| Earned Percent | Earned Value / Control Budget
| Actual Hours | (Actual Cost Work Performed) |  |  |  |  | Approved Non Scope include hours considered in the Forecast at completion but not part of the control budget per approved Trends/Non ScopeChanges.
| Actual Percent | Actual Cost / Control Budget
Pending Changes include hours required to perform an additional work pending approval.

## Overall
XXX001.8E Client Project Phase 1A Flowlines | [61 empty] | Overall
[5 empty] | 3 Part Curves as of : | 2015-08-21
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Control Hours | 96.74 | 212.98 | 350.04 | 434.65 | 516 | 1005.41 | 1491.41 | 1977.1 | 2378.44 | 2696.13 | 3103.2 | 3643.62 | 4237.05 | 4828.09 | 5312.09 | 5922.61 | 6497.05 | 7061.87 | 7634.74 | 8049.33 | 8650.55 | 9217.12 | 9780.62 | 10331.03 | 10756.69 | 11287.52 | 11886.99 | 12471.35 | 13040.17 | 13626.63 | 14191.2 | 14838.09 | 15446.38 | 15936.48 | 15936.48 | 15936.48 | 16329.13 | 16691.12 | 17042.4 | 17398.77 | 17767.52 | 18155.59 | 18437.51 | 18660.01 | 18720.97 | 18771.2 | 18810.93 | 18856.03 | 18895.4 | 18931 | 18949.9 | 18963.9 | 18979.57 | 19002.63 | 19036.63 | 19089.63 | 19130.1 | 19177.4 | 19229.6 | 19272.6 | 19302
Earned Hours | #N/A | #N/A | #N/A | #N/A | 516 | 1009.26 | 1487.35 | 1957.33 | 2389.2 | 2720.76 | 3142.21 | 3585.44 | 4072.29 | 4549.64 | 4901.59 | 5328.35 | 5749.97 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Actual Hours | 21.75 | 88.75 | 222.75 | 322.25 | 515.75 | 901.75 | 1407.25 | 1861.25 | 2332.25 | 2725.25 | 3173.25 | 3684.25 | 4128.25 | 4617.75 | 5102.75 | 5626.5 | 5958 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Forecast Hours | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5958 | 6509.49 | 7086.78 | 7510.01 | 8138.41 | 8792.52 | 9473.96 | 10182.39 | 10681.2 | 11294.98 | 11941.66 | 12547.26 | 13172.86 | 13760.02 | 14342.37 | 15004.27 | 15617.05 | 16130.46 | 16130.46 | 16130.46 | 16578.08 | 16966.21 | 17324.36 | 17680.79 | 18041.37 | 18415.56 | 18683.33 | 18891.95 | 18951.7 | 19000.43 | 19038.66 | 19082.56 | 19120.43 | 19154.53 | 19171.93 | 19184.43 | 19198.6 | 19220.17 | 19252.67 | 19304.17 | 19343.44 | 19389.24 | 19439.94 | 19481.44 | 19509.94
Cumulative %
Control Hours % | 0.5012% | 1.103% | 1.813% | 2.252% | 2.673% | 5.209% | 7.727% | 10.24% | 12.32% | 13.97% | 16.08% | 18.88% | 21.95% | 25.01% | 27.52% | 30.68% | 33.66% | 36.59% | 39.55% | 41.7% | 44.82% | 47.75% | 50.67% | 53.52% | 55.73% | 58.48% | 61.58% | 64.61% | 67.56% | 70.6% | 73.52% | 76.87% | 80.02% | 82.56% | 82.56% | 82.56% | 84.6% | 86.47% | 88.29% | 90.14% | 92.05% | 94.06% | 95.52% | 96.67% | 96.99% | 97.25% | 97.46% | 97.69% | 97.89% | 98.08% | 98.18% | 98.25% | 98.33% | 98.45% | 98.63% | 98.9% | 99.11% | 99.35% | 99.62% | 99.85% | 100%
Earned Hours % | 2015-05-29: 2.673%; 2015-06-05: 5.229%; 2015-06-12: 7.706%; 2015-06-19: 10.14%; 2015-06-26: 12.38%; 2015-07-03: 14.1%; 2015-07-10: 16.28%; 2015-07-17: 18.58%; 2015-07-24: 21.1%; 2015-07-31: 23.57%; 2015-08-07: 25.39%; 2015-08-14: 27.61%; 2015-08-21: 29.79%
Actual Hours % | 2015-05-01: 0.1127%; 2015-05-08: 0.4598%; 2015-05-15: 1.154%; 2015-05-22: 1.67%; 2015-05-29: 2.672%; 2015-06-05: 4.672%; 2015-06-12: 7.291%; 2015-06-19: 9.643%; 2015-06-26: 12.08%; 2015-07-03: 14.12%; 2015-07-10: 16.44%; 2015-07-17: 19.09%; 2015-07-24: 21.39%; 2015-07-31: 23.92%; 2015-08-07: 26.44%; 2015-08-14: 29.15%; 2015-08-21: 30.87%
Forecast Hours % | [16 empty] | 30.87% | 33.72% | 36.72% | 38.91% | 42.16% | 45.55% | 49.08% | 52.75% | 55.34% | 58.52% | 61.87% | 65% | 68.25% | 71.29% | 74.31% | 77.73% | 80.91% | 83.57% | 83.57% | 83.57% | 85.89% | 87.9% | 89.75% | 91.6% | 93.47% | 95.41% | 96.79% | 97.88% | 98.19% | 98.44% | 98.64% | 98.86% | 99.06% | 99.24% | 99.33% | 99.39% | 99.46% | 99.58% | 99.74% | 100% | 100.2% | 100.5% | 100.7% | 100.9% | 101.1%
Source Hours
Working Hours | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40
Baseline Hours (Cum) | 96.74 | 212.98 | 350.04 | 434.65 | 516 | 1005.41 | 1491.41 | 1977.1 | 2378.44 | 2696.13 | 3103.2 | 3643.62 | 4237.05 | 4828.09 | 5312.09 | 5922.61 | 6497.05 | 7061.87 | 7634.74 | 8049.33 | 8650.55 | 9217.12 | 9780.62 | 10331.03 | 10756.69 | 11287.52 | 11886.99 | 12471.35 | 13040.17 | 13626.63 | 14191.2 | 14838.09 | 15446.38 | 15936.48 | 15936.48 | 15936.48 | 16329.13 | 16691.12 | 17042.4 | 17398.77 | 17767.52 | 18155.59 | 18437.51 | 18660.01 | 18720.97 | 18771.2 | 18810.93 | 18856.03 | 18895.4 | 18931 | 18949.9 | 18963.9 | 18979.57 | 19002.63 | 19036.63 | 19089.63 | 19130.1 | 19177.4 | 19229.6 | 19272.6 | 19302
MOC Hours (Cum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Hours | 21.75 | 67 | 134 | 99.5 | 193.5 | 386 | 505.5 | 454 | 471 | 393 | 448 | 511 | 444 | 489.5 | 485 | 523.75 | 331.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earned Hours (Cum) | 0 | 0 | 0 | 0 | 516 | 1009.26 | 1487.35 | 1957.33 | 2389.2 | 2720.76 | 3142.21 | 3585.44 | 4072.29 | 4549.64 | 4901.59 | 5328.35 | 5749.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551.49 | 577.29 | 423.23 | 628.4 | 654.11 | 681.44 | 708.43 | 498.81 | 613.78 | 646.68 | 605.6 | 625.6 | 587.16 | 582.35 | 661.9 | 612.78 | 513.41 | 0 | 0 | 447.62 | 388.13 | 358.15 | 356.43 | 360.58 | 374.19 | 267.77 | 208.62 | 59.75 | 48.73 | 38.23 | 43.9 | 37.87 | 34.1 | 17.4 | 12.5 | 14.17 | 21.57 | 32.5 | 51.5 | 39.27 | 45.8 | 50.7 | 41.5 | 28.5
Control Budget: | 2015-05-01: 19302
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Control FTEs | 2.4185 | 2.906 | 3.4265 | 2.6441 | 2.0337 | 12.2353 | 12.15 | 12.1422 | 10.0335 | 9.9278 | 10.1768 | 13.5105 | 14.8357 | 14.776 | 15.125 | 15.263 | 14.361 | 14.1205 | 14.3218 | 12.9559 | 15.0305 | 14.1642 | 14.0875 | 13.7602 | 13.3019 | 13.2707 | 14.9867 | 14.609 | 14.2205 | 14.6615 | 14.1142 | 16.1722 | 15.2073 | 12.2525 | 0 | 0 | 9.8162 | 9.0498 | 8.782 | 8.9092 | 9.2188 | 9.7017 | 8.81 | 5.5625 | 1.524 | 1.2557 | 0.99325 | 1.4094 | 0.98425 | 0.89 | 0.4725 | 0.35 | 0.39175 | 0.5765 | 0.85 | 1.325 | 1.2647 | 1.1825 | 1.305 | 1.075 | 0.735
Actual FTEs | 0.54375 | 1.675 | 3.35 | 3.1094 | 4.8375 | 9.65 | 12.6375 | 11.35 | 11.775 | 12.2812 | 11.2 | 12.775 | 11.1 | 12.2375 | 15.1562 | 13.0938 | 8.2875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast FTEs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.7873 | 14.4322 | 13.2259 | 15.71 | 16.3528 | 17.036 | 17.7107 | 15.5878 | 15.3445 | 16.167 | 15.14 | 15.64 | 14.679 | 14.5587 | 16.5475 | 15.3195 | 12.8352 | 0 | 0 | 11.1905 | 9.7033 | 8.9538 | 8.9108 | 9.0145 | 9.3547 | 8.3678 | 5.2155 | 1.4937 | 1.2183 | 0.95575 | 1.3719 | 0.94675 | 0.8525 | 0.435 | 0.3125 | 0.35425 | 0.53925 | 0.8125 | 1.2875 | 1.2272 | 1.145 | 1.2675 | 1.0375 | 0.7125
FTEs = Full Time Equivalents
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Planned PF | bar: 2015-05-01 to 2016-06-24
Cumulative PF | #N/A | #N/A | #N/A | #N/A | 1.0005 | 1.1192 | 1.0569 | 1.0516 | 1.0244 | 0.99835 | 0.99022 | 0.97318 | 0.98644 | 0.98525 | 0.96058 | 0.94701 | 0.96508 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Eng
XXX001.8E Client Project Phase 1A Flowlines | [61 empty] | Engineering & Design
[5 empty] | 3 Part Curves as of : | 2015-08-21
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Control Hours | 71.21 | 161.94 | 273.47 | 337.67 | 393.5 | 746.64 | 1096.36 | 1443.78 | 1718.85 | 1938.93 | 2207.25 | 2572.92 | 3009.85 | 3444.39 | 3799.63 | 4249.21 | 4702.15 | 5145.47 | 5566.84 | 5892.23 | 6381.95 | 6837.02 | 7289.02 | 7727.93 | 8064.39 | 8483.72 | 8971.69 | 9444.55 | 9901.87 | 10376.83 | 10809.9 | 11325.29 | 11822.08 | 12200.68 | 12200.68 | 12200.68 | 12481.83 | 12732.32 | 12972.1 | 13216.97 | 13474.22 | 13745.46 | 13927.51 | 14025.18 | 14064.8 | 14091.7 | 14108.1 | 14134.53 | 14163.9 | 14189.5 | 14198.4 | 14202.4 | 14208.07 | 14221.13 | 14245.13 | 14288.13 | 14320.6 | 14357.9 | 14400.1 | 14433.1 | 14456.5
Earned Hours | #N/A | #N/A | #N/A | #N/A | 393.5 | 730.75 | 1052.81 | 1364.78 | 1650.63 | 1870.11 | 2139.13 | 2392.44 | 2690.51 | 2986.18 | 3194.27 | 3450.55 | 3739.22 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Actual Hours | 21 | 71.5 | 180 | 256 | 393.5 | 652 | 1021 | 1321.5 | 1623.5 | 1870.25 | 2166.75 | 2478.75 | 2783 | 3089 | 3355 | 3702 | 3939.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Forecast Hours | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3939.5 | 4365.68 | 4800.86 | 5142.4 | 5668.69 | 6220.69 | 6800.02 | 7406.34 | 7823.46 | 8335.13 | 8879.7 | 9383.19 | 9906.68 | 10391.73 | 10851.97 | 11391.76 | 11902.43 | 12313.73 | 12313.73 | 12313.73 | 12659.24 | 12945.26 | 13201.3 | 13455.62 | 13714.09 | 13980.84 | 14156.25 | 14249.43 | 14287.85 | 14313.25 | 14328.15 | 14353.38 | 14381.25 | 14405.35 | 14412.75 | 14415.25 | 14419.42 | 14430.99 | 14453.49 | 14494.99 | 14526.26 | 14562.06 | 14602.76 | 14634.26 | 14656.76
Cumulative %
Control Hours % | 0.4926% | 1.12% | 1.892% | 2.336% | 2.722% | 5.165% | 7.584% | 9.987% | 11.89% | 13.41% | 15.27% | 17.8% | 20.82% | 23.83% | 26.28% | 29.39% | 32.53% | 35.59% | 38.51% | 40.76% | 44.15% | 47.29% | 50.42% | 53.46% | 55.78% | 58.68% | 62.06% | 65.33% | 68.49% | 71.78% | 74.78% | 78.34% | 81.78% | 84.4% | 84.4% | 84.4% | 86.34% | 88.07% | 89.73% | 91.43% | 93.21% | 95.08% | 96.34% | 97.02% | 97.29% | 97.48% | 97.59% | 97.77% | 97.98% | 98.15% | 98.21% | 98.24% | 98.28% | 98.37% | 98.54% | 98.84% | 99.06% | 99.32% | 99.61% | 99.84% | 100%
Earned Hours % | 2015-05-29: 2.722%; 2015-06-05: 5.055%; 2015-06-12: 7.283%; 2015-06-19: 9.441%; 2015-06-26: 11.42%; 2015-07-03: 12.94%; 2015-07-10: 14.8%; 2015-07-17: 16.55%; 2015-07-24: 18.61%; 2015-07-31: 20.66%; 2015-08-07: 22.1%; 2015-08-14: 23.87%; 2015-08-21: 25.87%
Actual Hours % | 2015-05-01: 0.1453%; 2015-05-08: 0.4946%; 2015-05-15: 1.245%; 2015-05-22: 1.771%; 2015-05-29: 2.722%; 2015-06-05: 4.51%; 2015-06-12: 7.063%; 2015-06-19: 9.141%; 2015-06-26: 11.23%; 2015-07-03: 12.94%; 2015-07-10: 14.99%; 2015-07-17: 17.15%; 2015-07-24: 19.25%; 2015-07-31: 21.37%; 2015-08-07: 23.21%; 2015-08-14: 25.61%; 2015-08-21: 27.25%
Forecast Hours % | [16 empty] | 27.25% | 30.2% | 33.21% | 35.57% | 39.21% | 43.03% | 47.04% | 51.23% | 54.12% | 57.66% | 61.42% | 64.91% | 68.53% | 71.88% | 75.07% | 78.8% | 82.33% | 85.18% | 85.18% | 85.18% | 87.57% | 89.55% | 91.32% | 93.08% | 94.86% | 96.71% | 97.92% | 98.57% | 98.83% | 99.01% | 99.11% | 99.29% | 99.48% | 99.65% | 99.7% | 99.71% | 99.74% | 99.82% | 99.98% | 100.3% | 100.5% | 100.7% | 101% | 101.2% | 101.4%
Source Hours
Working Hours | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40
Baseline Hours (Cum) | 71.21 | 161.94 | 273.47 | 337.67 | 393.5 | 746.64 | 1096.36 | 1443.78 | 1718.85 | 1938.93 | 2207.25 | 2572.92 | 3009.85 | 3444.39 | 3799.63 | 4249.21 | 4702.15 | 5145.47 | 5566.84 | 5892.23 | 6381.95 | 6837.02 | 7289.02 | 7727.93 | 8064.39 | 8483.72 | 8971.69 | 9444.55 | 9901.87 | 10376.83 | 10809.9 | 11325.29 | 11822.08 | 12200.68 | 12200.68 | 12200.68 | 12481.83 | 12732.32 | 12972.1 | 13216.97 | 13474.22 | 13745.46 | 13927.51 | 14025.18 | 14064.8 | 14091.7 | 14108.1 | 14134.53 | 14163.9 | 14189.5 | 14198.4 | 14202.4 | 14208.07 | 14221.13 | 14245.13 | 14288.13 | 14320.6 | 14357.9 | 14400.1 | 14433.1 | 14456.5
MOC Hours (Cum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Hours | 21 | 50.5 | 108.5 | 76 | 137.5 | 258.5 | 369 | 300.5 | 302 | 246.75 | 296.5 | 312 | 304.25 | 306 | 266 | 347 | 237.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earned Hours (Cum) | 0 | 0 | 0 | 0 | 393.5 | 730.75 | 1052.81 | 1364.78 | 1650.63 | 1870.11 | 2139.13 | 2392.44 | 2690.51 | 2986.18 | 3194.27 | 3450.55 | 3739.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426.18 | 435.18 | 341.54 | 526.29 | 552 | 579.33 | 606.32 | 417.12 | 511.67 | 544.57 | 503.49 | 523.49 | 485.05 | 460.24 | 539.79 | 510.67 | 411.3 | 0 | 0 | 345.51 | 286.02 | 256.04 | 254.32 | 258.47 | 266.75 | 175.41 | 93.18 | 38.42 | 25.4 | 14.9 | 25.23 | 27.87 | 24.1 | 7.4 | 2.5 | 4.17 | 11.57 | 22.5 | 41.5 | 31.27 | 35.8 | 40.7 | 31.5 | 22.5
Control Budget: | 2015-05-01: 14456.5
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Control FTEs | 1.7803 | 2.2682 | 2.7883 | 2.0062 | 1.3957 | 8.8285 | 8.743 | 8.6855 | 6.8768 | 6.8775 | 6.708 | 9.1418 | 10.9233 | 10.8635 | 11.1012 | 11.2395 | 11.3235 | 11.083 | 10.5343 | 10.1684 | 12.243 | 11.3768 | 11.3 | 10.9727 | 10.5144 | 10.4832 | 12.1992 | 11.8215 | 11.433 | 11.874 | 10.8268 | 12.8847 | 12.4197 | 9.465 | 0 | 0 | 7.0287 | 6.2622 | 5.9945 | 6.1218 | 6.4313 | 6.781 | 5.6891 | 2.4418 | 0.9905 | 0.6725 | 0.41 | 0.82594 | 0.73425 | 0.64 | 0.2225 | 0.1 | 0.14175 | 0.3265 | 0.6 | 1.075 | 1.0147 | 0.9325 | 1.055 | 0.825 | 0.585
Actual FTEs | 0.525 | 1.2625 | 2.7125 | 2.375 | 3.4375 | 6.4625 | 9.225 | 7.5125 | 7.55 | 7.7109 | 7.4125 | 7.8 | 7.6063 | 7.65 | 8.3125 | 8.675 | 5.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast FTEs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.6545 | 10.8795 | 10.6731 | 13.1572 | 13.8 | 14.4833 | 15.158 | 13.035 | 12.7918 | 13.6142 | 12.5873 | 13.0873 | 12.1262 | 11.506 | 13.4947 | 12.7668 | 10.2825 | 0 | 0 | 8.6378 | 7.1505 | 6.401 | 6.358 | 6.4617 | 6.6688 | 5.4816 | 2.3295 | 0.9605 | 0.635 | 0.3725 | 0.78844 | 0.69675 | 0.6025 | 0.185 | 0.0625 | 0.10425 | 0.28925 | 0.5625 | 1.0375 | 0.97719 | 0.895 | 1.0175 | 0.7875 | 0.5625
FTEs = Full Time Equivalents
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Planned PF | bar: 2015-05-01 to 2016-06-24
Cumulative PF | #N/A | #N/A | #N/A | #N/A | 1 | 1.1208 | 1.0312 | 1.0328 | 1.0167 | 0.99993 | 0.98725 | 0.96518 | 0.96677 | 0.96671 | 0.95209 | 0.93208 | 0.94916 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Process (hidden)
XXX001.8E Client Project Phase 1A Flowlines | [61 empty] | Process
[5 empty] | 3 Part Curves as of : | 2015-08-21
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Control Hours | 27.7 | 73.87 | 120.03 | 138.5 | 138.5 | 249.88 | 357.84 | 463.5 | 481.5 | 495.9 | 504.5 | 514.5 | 524.5 | 534.5 | 542.5 | 558 | 573.5 | 578.5 | 583.5 | 587.5 | 596.5 | 601.5 | 626.38 | 664.5 | 695 | 733.12 | 776.46 | 816.58 | 857.9 | 879.9 | 899.5 | 939 | 973.5 | 977.5 | 977.5 | 977.5 | 977.5 | 977.63 | 978.3 | 978.97 | 979.63 | 980.3 | 980.83 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5
Earned Hours | #N/A | #N/A | #N/A | #N/A | 138.5 | 245.32 | 336.96 | 418.5 | 457.43 | 480.05 | 501.49 | 513.19 | 522.8 | 532.41 | 540.1 | 545.9 | 550.75 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Actual Hours | 21 | 63.5 | 114.5 | 123.5 | 138.5 | 214.5 | 303.5 | 367 | 394 | 401.25 | 435.75 | 462.25 | 482.5 | 485.5 | 497 | 512 | 545.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Forecast Hours | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 545.5 | 561.11 | 576.72 | 580.81 | 585.92 | 591.03 | 616.01 | 658.24 | 688.83 | 727.06 | 769.29 | 807.52 | 846.55 | 865.99 | 885.43 | 927.97 | 966.58 | 972.27 | 972.27 | 972.27 | 972.27 | 972.4 | 973.07 | 973.74 | 974.41 | 975.08 | 975.61 | 976.28 | 976.28 | 976.28 | 976.28 | 976.28 | 976.28 | 976.28 | 976.28 | 976.28 | 976.28 | 976.28 | 976.28 | 976.28 | 976.28 | 976.28 | 976.28 | 976.28 | 976.28
Cumulative %
Control Hours % | 2.822% | 7.526% | 12.23% | 14.11% | 14.11% | 25.46% | 36.46% | 47.22% | 49.06% | 50.52% | 51.4% | 52.42% | 53.44% | 54.46% | 55.27% | 56.85% | 58.43% | 58.94% | 59.45% | 59.86% | 60.77% | 61.28% | 63.82% | 67.7% | 70.81% | 74.69% | 79.11% | 83.2% | 87.41% | 89.65% | 91.65% | 95.67% | 99.18% | 99.59% | 99.59% | 99.59% | 99.59% | 99.61% | 99.67% | 99.74% | 99.81% | 99.88% | 99.93% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Earned Hours % | 2015-05-29: 14.11%; 2015-06-05: 24.99%; 2015-06-12: 34.33%; 2015-06-19: 42.64%; 2015-06-26: 46.61%; 2015-07-03: 48.91%; 2015-07-10: 51.09%; 2015-07-17: 52.29%; 2015-07-24: 53.27%; 2015-07-31: 54.24%; 2015-08-07: 55.03%; 2015-08-14: 55.62%; 2015-08-21: 56.11%
Actual Hours % | 2015-05-01: 2.14%; 2015-05-08: 6.47%; 2015-05-15: 11.67%; 2015-05-22: 12.58%; 2015-05-29: 14.11%; 2015-06-05: 21.85%; 2015-06-12: 30.92%; 2015-06-19: 37.39%; 2015-06-26: 40.14%; 2015-07-03: 40.88%; 2015-07-10: 44.4%; 2015-07-17: 47.1%; 2015-07-24: 49.16%; 2015-07-31: 49.47%; 2015-08-07: 50.64%; 2015-08-14: 52.17%; 2015-08-21: 55.58%
Forecast Hours % | [16 empty] | 55.58% | 57.17% | 58.76% | 59.18% | 59.7% | 60.22% | 62.76% | 67.06% | 70.18% | 74.08% | 78.38% | 82.27% | 86.25% | 88.23% | 90.21% | 94.55% | 98.48% | 99.06% | 99.06% | 99.06% | 99.06% | 99.07% | 99.14% | 99.21% | 99.28% | 99.35% | 99.4% | 99.47% | 99.47% | 99.47% | 99.47% | 99.47% | 99.47% | 99.47% | 99.47% | 99.47% | 99.47% | 99.47% | 99.47% | 99.47% | 99.47% | 99.47% | 99.47% | 99.47% | 99.47%
Source Hours
Working Hours | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40
Baseline Hours (Cum) | 27.7 | 73.87 | 120.03 | 138.5 | 138.5 | 249.88 | 357.84 | 463.5 | 481.5 | 495.9 | 504.5 | 514.5 | 524.5 | 534.5 | 542.5 | 558 | 573.5 | 578.5 | 583.5 | 587.5 | 596.5 | 601.5 | 626.38 | 664.5 | 695 | 733.12 | 776.46 | 816.58 | 857.9 | 879.9 | 899.5 | 939 | 973.5 | 977.5 | 977.5 | 977.5 | 977.5 | 977.63 | 978.3 | 978.97 | 979.63 | 980.3 | 980.83 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5 | 981.5
MOC Hours (Cum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Hours | 21 | 42.5 | 51 | 9 | 15 | 76 | 89 | 63.5 | 27 | 7.25 | 34.5 | 26.5 | 20.25 | 3 | 11.5 | 15 | 33.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earned Hours (Cum) | 0 | 0 | 0 | 0 | 138.5 | 245.32 | 336.96 | 418.5 | 457.43 | 480.05 | 501.49 | 513.19 | 522.8 | 532.41 | 540.1 | 545.9 | 550.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.61 | 15.61 | 4.09 | 5.11 | 5.11 | 24.98 | 42.23 | 30.59 | 38.23 | 42.23 | 38.23 | 39.03 | 19.44 | 19.44 | 42.54 | 38.61 | 5.69 | 0 | 0 | 0 | 0.13 | 0.67 | 0.67 | 0.67 | 0.67 | 0.53 | 0.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control Budget: | 2015-05-01: 981.5
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Control FTEs | 0.6925 | 1.1542 | 1.154 | 0.57719 | 0 | 2.7845 | 2.699 | 2.6415 | 0.45 | 0.45 | 0.215 | 0.25 | 0.25 | 0.25 | 0.25 | 0.3875 | 0.3875 | 0.125 | 0.125 | 0.125 | 0.225 | 0.125 | 0.622 | 0.953 | 0.95312 | 0.953 | 1.0835 | 1.003 | 1.033 | 0.55 | 0.49 | 0.9875 | 0.8625 | 0.1 | 0 | 0 | 0 | 0.00325 | 0.01675 | 0.01675 | 0.0165 | 0.01675 | 0.016563 | 0.01675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual FTEs | 0.525 | 1.0625 | 1.275 | 0.28125 | 0.375 | 1.9 | 2.225 | 1.5875 | 0.675 | 0.22656 | 0.8625 | 0.6625 | 0.50625 | 0.075 | 0.35938 | 0.375 | 0.8375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast FTEs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39025 | 0.39025 | 0.12781 | 0.12775 | 0.12775 | 0.6245 | 1.0558 | 0.95594 | 0.95575 | 1.0558 | 0.95575 | 0.97575 | 0.486 | 0.486 | 1.0635 | 0.96525 | 0.14225 | 0 | 0 | 0 | 0.00325 | 0.01675 | 0.01675 | 0.01675 | 0.01675 | 0.016563 | 0.01675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FTEs = Full Time Equivalents
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Planned PF | bar: 2015-05-01 to 2016-06-24
Cumulative PF | #N/A | #N/A | #N/A | #N/A | 1 | 1.1437 | 1.1102 | 1.1403 | 1.161 | 1.1964 | 1.1509 | 1.1102 | 1.0835 | 1.0966 | 1.0867 | 1.0662 | 1.0096 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Stress (hidden)
XXX001.8E Client Project Phase 1A Flowlines | [61 empty] | Stress
[5 empty] | 3 Part Curves as of : | 2015-08-21
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Control Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 150.5 | 213.63 | 276.75 | 339.88 | 403 | 453.5 | 516.63 | 579.75 | 624.2 | 656.2 | 681.8 | 713.8 | 745.8 | 777.8 | 816.84 | 866.44 | 916.04 | 965.64 | 1015.24 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045
Earned Hours | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 50 | 100 | 114.43 | 132.46 | 150.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Actual Hours | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 73 | 73 | 73 | 74 | 92 | 102 | 129 | 150 | 165 | 165 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Forecast Hours | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 165 | 229.93 | 294.86 | 346.8 | 411.73 | 476.66 | 541.59 | 606.52 | 638.71 | 670.71 | 702.71 | 734.71 | 766.71 | 798.71 | 841.27 | 890.87 | 940.47 | 990.07 | 990.07 | 990.07 | 1039.67 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51 | 1059.51
Cumulative %
Control Hours % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.785% | 9.569% | 14.4% | 20.44% | 26.48% | 32.52% | 38.56% | 43.4% | 49.44% | 55.48% | 59.73% | 62.79% | 65.24% | 68.31% | 71.37% | 74.43% | 78.17% | 82.91% | 87.66% | 92.41% | 97.15% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Earned Hours % | 2015-07-24: 4.785%; 2015-07-31: 9.569%; 2015-08-07: 10.95%; 2015-08-14: 12.68%; 2015-08-21: 14.4%
Actual Hours % | 2015-05-01: 0%; 2015-05-08: 0%; 2015-05-15: 0%; 2015-05-22: 0%; 2015-05-29: 0%; 2015-06-05: 0%; 2015-06-12: 3.636%; 2015-06-19: 6.986%; 2015-06-26: 6.986%; 2015-07-03: 6.986%; 2015-07-10: 7.081%; 2015-07-17: 8.804%; 2015-07-24: 9.761%; 2015-07-31: 12.34%; 2015-08-07: 14.35%; 2015-08-14: 15.79%; 2015-08-21: 15.79%
Forecast Hours % | [16 empty] | 15.79% | 22% | 28.22% | 33.19% | 39.4% | 45.61% | 51.83% | 58.04% | 61.12% | 64.18% | 67.24% | 70.31% | 73.37% | 76.43% | 80.5% | 85.25% | 90% | 94.74% | 94.74% | 94.74% | 99.49% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4% | 101.4%
Source Hours
Working Hours | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40
Baseline Hours (Cum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 150.5 | 213.63 | 276.75 | 339.88 | 403 | 453.5 | 516.63 | 579.75 | 624.2 | 656.2 | 681.8 | 713.8 | 745.8 | 777.8 | 816.84 | 866.44 | 916.04 | 965.64 | 1015.24 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045 | 1045
MOC Hours (Cum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Hours | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 35 | 0 | 0 | 1 | 18 | 10 | 27 | 21 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earned Hours (Cum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 114.43 | 132.46 | 150.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.93 | 64.93 | 51.94 | 64.93 | 64.93 | 64.93 | 64.93 | 32.19 | 32 | 32 | 32 | 32 | 32 | 42.56 | 49.6 | 49.6 | 49.6 | 0 | 0 | 49.6 | 19.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control Budget: | 2015-05-01: 1045
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Control FTEs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 1.25 | 1.5781 | 1.5782 | 1.578 | 1.5782 | 1.578 | 1.5781 | 1.5782 | 1.578 | 1.1113 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.976 | 1.24 | 1.24 | 1.24 | 1.24 | 0.744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual FTEs | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0.875 | 0 | 0 | 0.025 | 0.45 | 0.25 | 0.675 | 0.65625 | 0.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast FTEs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6233 | 1.6233 | 1.6231 | 1.6233 | 1.6233 | 1.6233 | 1.6233 | 1.0059 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 1.064 | 1.24 | 1.24 | 1.24 | 0 | 0 | 1.24 | 0.496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FTEs = Full Time Equivalents
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Planned PF | bar: 2015-05-01 to 2016-06-24
Cumulative PF | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.4902 | 0.77519 | 0.76287 | 0.80279 | 0.91212 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Structural (hidden)
XXX001.8E Client Project Phase 1A Flowlines | [61 empty] | Structural
[5 empty] | 3 Part Curves as of : | 2015-08-21
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Control Hours | 0 | 0 | 22.5 | 40.5 | 63 | 171.8 | 280.59 | 389.39 | 498.17 | 585.21 | 696.93 | 819.92 | 942.9 | 1064.82 | 1161.07 | 1281.4 | 1401.72 | 1522.03 | 1642.35 | 1738.6 | 1881.11 | 2019.17 | 2157.23 | 2295.28 | 2411.72 | 2559.78 | 2714.52 | 2860.37 | 3009.43 | 3163.28 | 3298.29 | 3448.36 | 3595.14 | 3738.71 | 3738.71 | 3738.71 | 3877.49 | 3994.19 | 4100.63 | 4207.07 | 4323.03 | 4453.26 | 4538.34 | 4573 | 4589 | 4589 | 4590 | 4594 | 4599 | 4599 | 4599 | 4599 | 4599 | 4599 | 4605 | 4615 | 4623 | 4629 | 4635 | 4644 | 4644
Earned Hours | #N/A | #N/A | #N/A | #N/A | 63 | 168.88 | 274.76 | 380.64 | 486.52 | 571.23 | 678.95 | 793.65 | 908.35 | 1021.97 | 1111.6 | 1223.62 | 1335.65 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Actual Hours | 0 | 0 | 0 | 27 | 63 | 120 | 224 | 303 | 414 | 538 | 668 | 788 | 900 | 1020 | 1134 | 1254 | 1374 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Forecast Hours | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1374 | 1500.37 | 1626.74 | 1727.84 | 1866.19 | 2007.53 | 2148.87 | 2298.21 | 2417.29 | 2568.63 | 2726.65 | 2875.79 | 3024.93 | 3174.07 | 3307.26 | 3458.71 | 3606.87 | 3755.03 | 3755.03 | 3755.03 | 3903.19 | 4024.49 | 4132.31 | 4240.13 | 4357.47 | 4489.09 | 4575.27 | 4611.32 | 4627.32 | 4627.32 | 4628.32 | 4632.32 | 4637.32 | 4637.32 | 4637.32 | 4637.32 | 4637.32 | 4637.32 | 4643.32 | 4653.32 | 4661.32 | 4667.32 | 4673.32 | 4682.32 | 4682.32
Cumulative %
Control Hours % | 0% | 0% | 0.4845% | 0.8721% | 1.357% | 3.699% | 6.042% | 8.385% | 10.73% | 12.6% | 15.01% | 17.66% | 20.3% | 22.93% | 25% | 27.59% | 30.18% | 32.77% | 35.36% | 37.44% | 40.51% | 43.48% | 46.45% | 49.42% | 51.93% | 55.12% | 58.45% | 61.59% | 64.8% | 68.12% | 71.02% | 74.25% | 77.41% | 80.51% | 80.51% | 80.51% | 83.49% | 86.01% | 88.3% | 90.59% | 93.09% | 95.89% | 97.72% | 98.47% | 98.82% | 98.82% | 98.84% | 98.92% | 99.03% | 99.03% | 99.03% | 99.03% | 99.03% | 99.03% | 99.16% | 99.38% | 99.55% | 99.68% | 99.81% | 100% | 100%
Earned Hours % | 2015-05-29: 1.357%; 2015-06-05: 3.637%; 2015-06-12: 5.916%; 2015-06-19: 8.196%; 2015-06-26: 10.48%; 2015-07-03: 12.3%; 2015-07-10: 14.62%; 2015-07-17: 17.09%; 2015-07-24: 19.56%; 2015-07-31: 22.01%; 2015-08-07: 23.94%; 2015-08-14: 26.35%; 2015-08-21: 28.76%
Actual Hours % | 2015-05-01: 0%; 2015-05-08: 0%; 2015-05-15: 0%; 2015-05-22: 0.5814%; 2015-05-29: 1.357%; 2015-06-05: 2.584%; 2015-06-12: 4.823%; 2015-06-19: 6.525%; 2015-06-26: 8.915%; 2015-07-03: 11.58%; 2015-07-10: 14.38%; 2015-07-17: 16.97%; 2015-07-24: 19.38%; 2015-07-31: 21.96%; 2015-08-07: 24.42%; 2015-08-14: 27%; 2015-08-21: 29.59%
Forecast Hours % | [16 empty] | 29.59% | 32.31% | 35.03% | 37.21% | 40.18% | 43.23% | 46.27% | 49.49% | 52.05% | 55.31% | 58.71% | 61.92% | 65.14% | 68.35% | 71.22% | 74.48% | 77.67% | 80.86% | 80.86% | 80.86% | 84.05% | 86.66% | 88.98% | 91.3% | 93.83% | 96.66% | 98.52% | 99.3% | 99.64% | 99.64% | 99.66% | 99.75% | 99.86% | 99.86% | 99.86% | 99.86% | 99.86% | 99.86% | 99.99% | 100.2% | 100.4% | 100.5% | 100.6% | 100.8% | 100.8%
Source Hours
Working Hours | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40
Baseline Hours (Cum) | 0 | 0 | 22.5 | 40.5 | 63 | 171.8 | 280.59 | 389.39 | 498.17 | 585.21 | 696.93 | 819.92 | 942.9 | 1064.82 | 1161.07 | 1281.4 | 1401.72 | 1522.03 | 1642.35 | 1738.6 | 1881.11 | 2019.17 | 2157.23 | 2295.28 | 2411.72 | 2559.78 | 2714.52 | 2860.37 | 3009.43 | 3163.28 | 3298.29 | 3448.36 | 3595.14 | 3738.71 | 3738.71 | 3738.71 | 3877.49 | 3994.19 | 4100.63 | 4207.07 | 4323.03 | 4453.26 | 4538.34 | 4573 | 4589 | 4589 | 4590 | 4594 | 4599 | 4599 | 4599 | 4599 | 4599 | 4599 | 4605 | 4615 | 4623 | 4629 | 4635 | 4644 | 4644
MOC Hours (Cum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Hours | 0 | 0 | 0 | 27 | 36 | 57 | 104 | 79 | 111 | 124 | 130 | 120 | 112 | 120 | 114 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earned Hours (Cum) | 0 | 0 | 0 | 0 | 63 | 168.88 | 274.76 | 380.64 | 486.52 | 571.23 | 678.95 | 793.65 | 908.35 | 1021.97 | 1111.6 | 1223.62 | 1335.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126.37 | 126.37 | 101.1 | 138.35 | 141.34 | 141.34 | 149.34 | 119.08 | 151.34 | 158.02 | 149.14 | 149.14 | 149.14 | 133.19 | 151.45 | 148.16 | 148.16 | 0 | 0 | 148.16 | 121.3 | 107.82 | 107.82 | 117.34 | 131.62 | 86.18 | 36.05 | 16 | 0 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 6 | 10 | 8 | 6 | 6 | 9 | 0
Control Budget: | 2015-05-01: 4644
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Control FTEs | 0 | 0 | 0.5625 | 0.5625 | 0.5625 | 2.72 | 2.7198 | 2.72 | 2.7195 | 2.72 | 2.793 | 3.0748 | 3.0745 | 3.048 | 3.0078 | 3.0083 | 3.008 | 3.0077 | 3.008 | 3.0078 | 3.5627 | 3.4515 | 3.4515 | 3.4512 | 3.6388 | 3.7015 | 3.8685 | 3.6462 | 3.7265 | 3.8462 | 3.3753 | 3.7518 | 3.6695 | 3.5893 | 0 | 0 | 3.4695 | 2.9175 | 2.661 | 2.661 | 2.899 | 3.2558 | 2.6587 | 0.8665 | 0.4 | 0 | 0.025 | 0.125 | 0.125 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.25 | 0.25 | 0.15 | 0.15 | 0.225 | 0
Actual FTEs | 0 | 0 | 0 | 0.84375 | 0.9 | 1.425 | 2.6 | 1.975 | 2.775 | 3.875 | 3.25 | 3 | 2.8 | 3 | 3.5625 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast FTEs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1593 | 3.1593 | 3.1594 | 3.4587 | 3.5335 | 3.5335 | 3.7335 | 3.7213 | 3.7835 | 3.9505 | 3.7285 | 3.7285 | 3.7285 | 3.3297 | 3.7862 | 3.704 | 3.704 | 0 | 0 | 3.704 | 3.0325 | 2.6955 | 2.6955 | 2.9335 | 3.2905 | 2.6931 | 0.90125 | 0.4 | 0 | 0.025 | 0.125 | 0.125 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.25 | 0.25 | 0.15 | 0.15 | 0.225 | 0
FTEs = Full Time Equivalents
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Planned PF | bar: 2015-05-01 to 2016-06-24
Cumulative PF | #N/A | #N/A | #N/A | #N/A | 1 | 1.4073 | 1.2266 | 1.2562 | 1.1752 | 1.0618 | 1.0164 | 1.0072 | 1.0093 | 1.0019 | 0.98025 | 0.97577 | 0.97209 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Pipeline (hidden)
XXX001.8E Client Project Phase 1A Flowlines | [61 empty] | Pipeline
[5 empty] | 3 Part Curves as of : | 2015-08-21
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Control Hours | 34.94 | 70.93 | 106.94 | 134.67 | 168 | 264.3 | 360.59 | 456.89 | 568.52 | 657.82 | 769.16 | 976.41 | 1207.74 | 1437.75 | 1620.15 | 1848.15 | 2076.15 | 2304.16 | 2510.22 | 2663.37 | 2903.31 | 3126.6 | 3351.21 | 3561.95 | 3712.87 | 3901.52 | 4143.91 | 4388.8 | 4606.7 | 4847.21 | 5071.07 | 5338.29 | 5599.2 | 5795.47 | 5795.47 | 5795.47 | 5932.84 | 6061.5 | 6189.17 | 6321.93 | 6457.56 | 6592.9 | 6685.34 | 6742.68 | 6765.1 | 6790.5 | 6804.4 | 6825.63 | 6848.5 | 6872.6 | 6880 | 6882.5 | 6886.67 | 6898.23 | 6914.73 | 6946.23 | 6969.5 | 6999.3 | 7034 | 7056.5 | 7079
Earned Hours | #N/A | #N/A | #N/A | #N/A | 168 | 253.86 | 339.71 | 425.56 | 527.91 | 609.1 | 710.28 | 819.83 | 931.56 | 1041.97 | 1128.69 | 1237.09 | 1378.82 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Actual Hours | 0 | 0 | 57.5 | 97 | 168 | 261 | 369 | 448 | 574 | 667.5 | 776.5 | 905 | 1052 | 1190.5 | 1296.5 | 1456 | 1522 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Forecast Hours | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1522 | 1718.73 | 1915.46 | 2072.84 | 2354.85 | 2658.18 | 2962.82 | 3273.7 | 3488.83 | 3755.14 | 4044.67 | 4317.5 | 4609.53 | 4883.86 | 5143.35 | 5429.99 | 5698.73 | 5901.02 | 5901.02 | 5901.02 | 6043.21 | 6182.4 | 6324.39 | 6465.77 | 6606.23 | 6740.69 | 6829.39 | 6885.85 | 6908.27 | 6933.67 | 6947.57 | 6968.8 | 6991.67 | 7015.77 | 7023.17 | 7025.67 | 7029.84 | 7041.41 | 7057.91 | 7089.41 | 7112.68 | 7142.48 | 7177.18 | 7199.68 | 7222.18
Cumulative %
Control Hours % | 0.4936% | 1.002% | 1.511% | 1.902% | 2.373% | 3.734% | 5.094% | 6.454% | 8.031% | 9.293% | 10.87% | 13.79% | 17.06% | 20.31% | 22.89% | 26.11% | 29.33% | 32.55% | 35.46% | 37.62% | 41.01% | 44.17% | 47.34% | 50.32% | 52.45% | 55.11% | 58.54% | 62% | 65.08% | 68.47% | 71.64% | 75.41% | 79.1% | 81.87% | 81.87% | 81.87% | 83.81% | 85.63% | 87.43% | 89.31% | 91.22% | 93.13% | 94.44% | 95.25% | 95.57% | 95.92% | 96.12% | 96.42% | 96.74% | 97.08% | 97.19% | 97.22% | 97.28% | 97.45% | 97.68% | 98.12% | 98.45% | 98.87% | 99.36% | 99.68% | 100%
Earned Hours % | 2015-05-29: 2.373%; 2015-06-05: 3.586%; 2015-06-12: 4.799%; 2015-06-19: 6.012%; 2015-06-26: 7.457%; 2015-07-03: 8.604%; 2015-07-10: 10.03%; 2015-07-17: 11.58%; 2015-07-24: 13.16%; 2015-07-31: 14.72%; 2015-08-07: 15.94%; 2015-08-14: 17.48%; 2015-08-21: 19.48%
Actual Hours % | 2015-05-01: 0%; 2015-05-08: 0%; 2015-05-15: 0.8123%; 2015-05-22: 1.37%; 2015-05-29: 2.373%; 2015-06-05: 3.687%; 2015-06-12: 5.213%; 2015-06-19: 6.329%; 2015-06-26: 8.108%; 2015-07-03: 9.429%; 2015-07-10: 10.97%; 2015-07-17: 12.78%; 2015-07-24: 14.86%; 2015-07-31: 16.82%; 2015-08-07: 18.31%; 2015-08-14: 20.57%; 2015-08-21: 21.5%
Forecast Hours % | [16 empty] | 21.5% | 24.28% | 27.06% | 29.28% | 33.27% | 37.55% | 41.85% | 46.25% | 49.28% | 53.05% | 57.14% | 60.99% | 65.12% | 68.99% | 72.66% | 76.71% | 80.5% | 83.36% | 83.36% | 83.36% | 85.37% | 87.33% | 89.34% | 91.34% | 93.32% | 95.22% | 96.47% | 97.27% | 97.59% | 97.95% | 98.14% | 98.44% | 98.77% | 99.11% | 99.21% | 99.25% | 99.31% | 99.47% | 99.7% | 100.1% | 100.5% | 100.9% | 101.4% | 101.7% | 102%
Source Hours
Working Hours | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40
Baseline Hours (Cum) | 34.94 | 70.93 | 106.94 | 134.67 | 168 | 264.3 | 360.59 | 456.89 | 568.52 | 657.82 | 769.16 | 976.41 | 1207.74 | 1437.75 | 1620.15 | 1848.15 | 2076.15 | 2304.16 | 2510.22 | 2663.37 | 2903.31 | 3126.6 | 3351.21 | 3561.95 | 3712.87 | 3901.52 | 4143.91 | 4388.8 | 4606.7 | 4847.21 | 5071.07 | 5338.29 | 5599.2 | 5795.47 | 5795.47 | 5795.47 | 5932.84 | 6061.5 | 6189.17 | 6321.93 | 6457.56 | 6592.9 | 6685.34 | 6742.68 | 6765.1 | 6790.5 | 6804.4 | 6825.63 | 6848.5 | 6872.6 | 6880 | 6882.5 | 6886.67 | 6898.23 | 6914.73 | 6946.23 | 6969.5 | 6999.3 | 7034 | 7056.5 | 7079
MOC Hours (Cum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Hours | 0 | 0 | 57.5 | 39.5 | 71 | 93 | 108 | 79 | 126 | 93.5 | 109 | 128.5 | 147 | 138.5 | 106 | 159.5 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earned Hours (Cum) | 0 | 0 | 0 | 0 | 168 | 253.86 | 339.71 | 425.56 | 527.91 | 609.1 | 710.28 | 819.83 | 931.56 | 1041.97 | 1128.69 | 1237.09 | 1378.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196.73 | 196.73 | 157.38 | 282.01 | 303.33 | 304.64 | 310.88 | 215.13 | 266.31 | 289.53 | 272.83 | 292.03 | 274.33 | 259.49 | 286.64 | 268.74 | 202.29 | 0 | 0 | 142.19 | 139.19 | 141.99 | 141.38 | 140.46 | 134.46 | 88.7 | 56.46 | 22.42 | 25.4 | 13.9 | 21.23 | 22.87 | 24.1 | 7.4 | 2.5 | 4.17 | 11.57 | 16.5 | 31.5 | 23.27 | 29.8 | 34.7 | 22.5 | 22.5
Control Budget: | 2015-05-01: 7079
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Control FTEs | 0.8735 | 0.89975 | 0.90025 | 0.86656 | 0.83325 | 2.4075 | 2.4072 | 2.4075 | 2.7908 | 2.7906 | 2.7835 | 5.1813 | 5.7832 | 5.7502 | 5.7 | 5.7 | 5.7 | 5.7002 | 5.1515 | 4.7859 | 5.9985 | 5.5823 | 5.6152 | 5.2685 | 4.7163 | 4.7163 | 6.0597 | 6.1223 | 5.4475 | 6.0128 | 5.5965 | 6.6805 | 6.5227 | 4.9068 | 0 | 0 | 3.4342 | 3.2165 | 3.1918 | 3.319 | 3.3908 | 3.3835 | 2.8888 | 1.4335 | 0.5605 | 0.635 | 0.3475 | 0.66344 | 0.57175 | 0.6025 | 0.185 | 0.0625 | 0.10425 | 0.289 | 0.4125 | 0.7875 | 0.72719 | 0.745 | 0.8675 | 0.5625 | 0.5625
Actual FTEs | 0 | 0 | 1.4375 | 1.2344 | 1.775 | 2.325 | 2.7 | 1.975 | 3.15 | 2.9219 | 2.725 | 3.2125 | 3.675 | 3.4625 | 3.3125 | 3.9875 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast FTEs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9183 | 4.9183 | 4.9181 | 7.0503 | 7.5833 | 7.616 | 7.772 | 6.7228 | 6.6578 | 7.2382 | 6.8208 | 7.3008 | 6.8582 | 6.4873 | 7.166 | 6.7185 | 5.0573 | 0 | 0 | 3.5547 | 3.4798 | 3.5498 | 3.5345 | 3.5115 | 3.3615 | 2.7719 | 1.4115 | 0.5605 | 0.635 | 0.3475 | 0.66344 | 0.57175 | 0.6025 | 0.185 | 0.0625 | 0.10425 | 0.28925 | 0.4125 | 0.7875 | 0.72719 | 0.745 | 0.8675 | 0.5625 | 0.5625
FTEs = Full Time Equivalents
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Planned PF | bar: 2015-05-01 to 2016-06-24
Cumulative PF | #N/A | #N/A | #N/A | #N/A | 1 | 0.97264 | 0.92062 | 0.94991 | 0.9197 | 0.91251 | 0.91472 | 0.90589 | 0.88551 | 0.87524 | 0.87057 | 0.84965 | 0.90593 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Civil (hidden)
XXX001.8E Client Project Phase 1A Flowlines | [61 empty] | Civil
[5 empty] | 3 Part Curves as of : | 2015-08-21
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Control Hours | 8.57 | 17.14 | 24 | 24 | 24 | 55.66 | 87.34 | 119 | 150.66 | 176 | 207.66 | 228.09 | 245.71 | 263.32 | 277.41 | 295.03 | 316.03 | 337.9 | 359.77 | 377.26 | 407.4 | 428 | 443 | 458 | 467 | 474.5 | 485 | 490 | 495 | 499 | 499 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503
Earned Hours | #N/A | #N/A | #N/A | #N/A | 24 | 54.89 | 85.78 | 116.67 | 147.56 | 172.28 | 203.16 | 212.72 | 216.95 | 221.17 | 224.55 | 228.78 | 233 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Actual Hours | 0 | 8 | 8 | 8.5 | 24 | 52.5 | 80 | 123 | 156.5 | 175.5 | 195.5 | 204.5 | 212.5 | 220.5 | 228.5 | 235.5 | 242.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Forecast Hours | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 242.5 | 259.48 | 285.46 | 308.04 | 338.37 | 370.1 | 407.98 | 441.36 | 457.04 | 475.27 | 492.5 | 498.23 | 503.96 | 508.54 | 508.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54 | 512.54
Cumulative %
Control Hours % | 1.704% | 3.408% | 4.771% | 4.771% | 4.771% | 11.07% | 17.36% | 23.66% | 29.95% | 34.99% | 41.28% | 45.35% | 48.85% | 52.35% | 55.15% | 58.65% | 62.83% | 67.18% | 71.52% | 75% | 80.99% | 85.09% | 88.07% | 91.05% | 92.84% | 94.33% | 96.42% | 97.42% | 98.41% | 99.2% | 99.2% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Earned Hours % | 2015-05-29: 4.771%; 2015-06-05: 10.91%; 2015-06-12: 17.05%; 2015-06-19: 23.19%; 2015-06-26: 29.34%; 2015-07-03: 34.25%; 2015-07-10: 40.39%; 2015-07-17: 42.29%; 2015-07-24: 43.13%; 2015-07-31: 43.97%; 2015-08-07: 44.64%; 2015-08-14: 45.48%; 2015-08-21: 46.32%
Actual Hours % | 2015-05-01: 0%; 2015-05-08: 1.59%; 2015-05-15: 1.59%; 2015-05-22: 1.69%; 2015-05-29: 4.771%; 2015-06-05: 10.44%; 2015-06-12: 15.9%; 2015-06-19: 24.45%; 2015-06-26: 31.11%; 2015-07-03: 34.89%; 2015-07-10: 38.87%; 2015-07-17: 40.66%; 2015-07-24: 42.25%; 2015-07-31: 43.84%; 2015-08-07: 45.43%; 2015-08-14: 46.82%; 2015-08-21: 48.21%
Forecast Hours % | [16 empty] | 48.21% | 51.59% | 56.75% | 61.24% | 67.27% | 73.58% | 81.11% | 87.75% | 90.86% | 94.49% | 97.91% | 99.05% | 100.2% | 101.1% | 101.1% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9% | 101.9%
Source Hours
Working Hours | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 40 | 40
Baseline Hours (Cum) | 8.57 | 17.14 | 24 | 24 | 24 | 55.66 | 87.34 | 119 | 150.66 | 176 | 207.66 | 228.09 | 245.71 | 263.32 | 277.41 | 295.03 | 316.03 | 337.9 | 359.77 | 377.26 | 407.4 | 428 | 443 | 458 | 467 | 474.5 | 485 | 490 | 495 | 499 | 499 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503 | 503
MOC Hours (Cum) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Hours | 0 | 8 | 0 | 0.5 | 15.5 | 28.5 | 27.5 | 43 | 33.5 | 19 | 20 | 9 | 8 | 8 | 8 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earned Hours (Cum) | 0 | 0 | 0 | 0 | 24 | 54.89 | 85.78 | 116.67 | 147.56 | 172.28 | 203.16 | 212.72 | 216.95 | 221.17 | 224.55 | 228.78 | 233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.98 | 25.98 | 22.58 | 30.33 | 31.73 | 37.88 | 33.38 | 15.68 | 18.23 | 17.23 | 5.73 | 5.73 | 4.58 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Control Budget: | 2015-05-01: 503
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Control FTEs | 0.21425 | 0.21425 | 0.1715 | 0 | 0 | 0.7915 | 0.792 | 0.7915 | 0.7915 | 0.79188 | 0.7915 | 0.51075 | 0.4405 | 0.44025 | 0.44031 | 0.4405 | 0.525 | 0.54675 | 0.54675 | 0.54656 | 0.7535 | 0.515 | 0.375 | 0.375 | 0.28125 | 0.1875 | 0.2625 | 0.125 | 0.125 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual FTEs | 0 | 0.2 | 0 | 0.015625 | 0.3875 | 0.7125 | 0.6875 | 1.075 | 0.8375 | 0.59375 | 0.5 | 0.225 | 0.2 | 0.2 | 0.25 | 0.175 | 0.175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Forecast FTEs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4245 | 0.6495 | 0.70563 | 0.75825 | 0.79325 | 0.947 | 0.8345 | 0.49 | 0.45575 | 0.43075 | 0.14325 | 0.14325 | 0.1145 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FTEs = Full Time Equivalents
Reporting Period (End) | time axis 2015-05-01 to 2016-06-24
Planned PF | bar: 2015-05-01 to 2016-06-24
Cumulative PF | #N/A | #N/A | #N/A | #N/A | 1 | 1.0455 | 1.0722 | 0.94854 | 0.94288 | 0.98165 | 1.0392 | 1.0402 | 1.0209 | 1.003 | 0.98271 | 0.97146 | 0.96082 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A