## P6 Dump
Activity ID | Activity ID | Activity Name | Duration | Budgeted Hours | Earned Hours | % Complete | Start | Finish | Total Float | Baseline Finish | Previous Month End | Month Variance | Comments
EXECUTE Flowlines | EXECUTE Flowlines
KEY MILESTONES | KEY MILESTONES
FL-KM1010 | FL-KM1010 | Kick-Off EXECUTE Flowlines Phase | 0 | 0 | 0 | 0% | 21-Jul-14 A |  |  |  |  | 0
FL-KM1160 | FL-KM1160 | 60% 3D Model Review - Flowlines (90% Civil) - Delayed (CN-010) | 1 | 56 | 56 | 100% | 08-Oct-14 A | 08-Oct-14 A |  | 2014-08-25 | 2014-10-08 | 0
FL-KM1200 | FL-KM1200 | Interim 3D Model Review - Flowlines - Added (CN-018) | 1 | 0 | 0 | 0% | 10-Dec-14 A | 10-Dec-14 A |  |  | 2014-12-10 | 0
FL-KM1170 | FL-KM1170 | 90% 3D Model Review - Flowlines (100% Civil) - Delayed (CN-018) | 1 | 48 | 0 | 0% | 2015-02-05 | 2015-02-05 | 232 | 2014-10-22 | 2015-01-15 | -15
FL-KM1030 | FL-KM1030 | EXECUTE Flowlines Complete | 0 | 0 | 0 | 0% |  | 2015-06-15 | 183 | 2015-09-29 | 2015-06-15 | 0
FL-KM1020 | FL-KM1020 | Flowlines POs Issued (Pipe, Valves & Fittings) | 0 | 0 | 0 | 0% |  | 2015-06-22 | 178 | 2015-05-21 | 2015-06-22 | 0
FL-KM1050 | FL-KM1050 | Structural POs Issued | 0 | 0 | 0 | 0% |  | 2015-07-23 | 156 | 2015-06-29 | 2015-07-23 | 0
FL-KM1190 | FL-KM1190 | Flowlines Final Vendor Data | 0 | 0 | 0 | 0% |  | 2015-09-18 | 117 |  | 2015-09-18 | 0
FL-KM1180 | FL-KM1180 | Flowlines Materials Received at Site | 0 | 0 | 0 | 0% |  | 2016-03-14 | 0 | 2015-12-28 | 2016-03-02 | -8
PROJECT MANAGEMENT & SERVICES | PROJECT MANAGEMENT & SERVICES
Project Management | Project Management
General | General
FL-PM1000 | FL-PM1000 | Project Management EXECUTE Flowlines General Activities | 200 | 864 | 430.08 | 49.78% | 21-Jul-14 A | 2015-05-15 | 203 | 2015-08-26 | 2015-05-15 | 0
FL-PM1020 | FL-PM1020 | Project Engineering EXECUTE Flowlines General Activities | 200 | 1296 | 580.61 | 44.8% | 21-Jul-14 A | 2015-05-15 | 203 | 2015-08-26 | 2015-05-15 | 0
FL-PM1100 | FL-PM1100 | Project Administration EXECUTE Flowlines General Activities - Reduced (CN-012) | 167 | 816 | 386.01 | 47.31% | 08-Sep-14 A | 2015-05-15 | 203 | 2015-09-10 | 2015-05-15 | 0
FL-PM1180 | FL-PM1180 | EAS EXECUTE Flowlines General Activities - Reduced (CN-012) | 157 | 184 | 80.87 | 43.95% | 22-Sep-14 A | 2015-05-15 | 203 | 2015-09-10 | 2015-05-15 | 0
FL-PM1120 | FL-PM1120 | Flowlines Site Visits | 80 | 120 | 36 | 30% | 03-Nov-14 A | 2015-03-09 | 211 | 2014-12-12 | 2015-03-09 | 0
Close Out | Close Out
FL-PM1200 | FL-PM1200 | EXECUTE Flowlines Close Out Engineering - Increased (CN-022) | 20 | 170 | 0 | 0% | 2015-04-15 | 2015-05-12 | 186 |  | 2015-05-12 | 0
FL-PM1050 | FL-PM1050 | EXECUTE Flowlines Close Out PMT - Increased (CN-022) | 20 | 295 | 0 | 0% | 2015-05-19 | 2015-06-15 | 183 | 2015-09-29 | 2015-06-15 | 0
Change Management | Change Management
FL-PM1060 | FL-PM1060 | PMT LOE Additional Activities (CN-024) General Activities | 100 | 540 | 0 | 0% | 2015-01-12 | 2015-06-03 | 191 | 2014-10-16 | 2015-05-20 | -10
Quality Assurance | Quality Assurance
General | General
FL-QA1000 | FL-QA1000 | Quality Assurance EXECUTE Flowlines General Activities | 250 | 152 | 68.1 | 44.8% | 21-Jul-14 A | 2015-05-15 | 203 | 2015-09-10 | 2015-05-15 | 0
FL-QA1100 | FL-QA1100 | HSE EXECUTE Flowlines General Activities | 100 | 84 | 3.36 | 4% | 17-Nov-14 A | 2015-05-14 | 204 |  | 2015-05-15 | 0
FL-QA1010 | FL-QA1010 | External Quality Audit 1 - Budget Transfer (CN-022) | 10 | 15 | 15 | 100% | 01-Dec-14 A | 12-Dec-14 A |  |  | 2014-12-12 | 0
FL-QA1020 | FL-QA1020 | External Quality Audit 2 - Budget Transfer (CN-022) | 15 | 15 | 15 | 100% | 08-Dec-14 A | 19-Dec-14 A |  |  | 2015-01-09 | 5
FL-QA1030 | FL-QA1030 | External Quality Audit 3 - Budget Transfer (CN-022) | 15 | 15 | 1.5 | 10% | 08-Dec-14 A | 2015-01-30 | 236 |  | 2015-01-09 | -15
FL-QA1040 | FL-QA1040 | External Quality Audit 4 - Budget Transfer (CN-022) | 15 | 15 | 0 | 0% | 2015-01-12 | 2015-01-30 | 236 |  | 2015-01-30 | 0
FL-QA1080 | FL-QA1080 | Performance Feedback Survey and Report - Budget Transfer (CN-022) | 10 | 20 | 0 | 0% | 2015-02-02 | 2015-02-13 | 236 |  | 2015-02-13 | 0
FL-QA1060 | FL-QA1060 | Internal Quality Assurance Audit - Budget Transfer (CN-022) | 10 | 50 | 0 | 0% | 2015-02-17 | 2015-03-02 | 236 |  | 2015-03-02 | 0
Change Management | Change Management
Project Controls | Project Controls
General | General
FL-PC1000 | FL-PC1000 | Project Controls EXECUTE Flowlines General Activities | 270 | 2160 | 896 | 41.48% | 21-Jul-14 A | 2015-05-15 | 203 | 2015-08-26 | 2015-05-15 | 0
FL-PC1040 | FL-PC1040 | Estimating EXECUTE Flowlines General Activities | 141 | 70 | 13.25 | 18.93% | 02-Sep-14 A | 2015-05-15 | 203 | 2015-09-10 | 2015-05-15 | 0
FL-PC1010 | FL-PC1010 | Project Baseline Package (Flowlines) | 10 | 12 | 12 | 100% | 20-Oct-14 A | 31-Oct-14 A |  | 2014-08-01 | 2014-10-31 | 0
Key Quantities Updates | Key Quantities Updates
FL-PC1030 | FL-PC1030 | Key Quantities Update (60% Model IFI Flowlines) | 15 | 50 | 50 | 100% | 01-Dec-14 A | 18-Dec-14 A |  | 2014-12-17 | 2014-12-18 | 0
FL-PC1050 | FL-PC1050 | Key Quantities Update (IFC Flowlines) | 20 | 50 | 0 | 0% | 2015-04-15 | 2015-05-12 | 186 | 2015-09-15 | 2015-03-11 | -43
Change Management | Change Management
FL-PC1060 | FL-PC1060 | Flowline Elevation Change (CN-009) | 10 | 8 | 8 | 100% | 03-Nov-14 A | 14-Nov-14 A |  |  | 2014-11-14 | 0
FL-PC1070 | FL-PC1070 | Pad 104 and 105 Valve Station (CN-001) | 10 | 8 | 8 | 100% | 15-Dec-14 A | 19-Dec-14 A |  |  | 2015-01-09 | 5
FL-PC1080 | FL-PC1080 | Reduction of Block and Bleed Valves (CN-014) | 10 | 8 | 8 | 100% | 15-Dec-14 A | 19-Dec-14 A |  |  | 2015-01-09 | 5
FL-PC1090 | FL-PC1090 | Top of Steel Changes - TIC Estimate (CN-018) | 20 | 20 | 20 | 100% | 05-Jan-15 A | 09-Jan-15 A |  |  | 2015-01-23 | 10
Document Controls | Document Controls
General | General
FL-DC1000 | FL-DC1000 | Document Control EXECUTE Flowlines General Activities | 250 | 1080 | 483.84 | 44.8% | 21-Jul-14 A | 2015-05-15 | 203 | 2015-08-26 | 2015-05-15 | 0
Change Management | Change Management
FL-PM1190 | FL-PM1190 | PMT LOE Addition (CN-024) General Activities | 100 | 80 | 0 | 0% | 2015-01-12 | 2015-06-03 | 191 |  | 2015-06-09 | 4
ENGINEERING & DESIGN | ENGINEERING & DESIGN
Process | Process
General | General
FL-PR1000 | FL-PR1000 | Process Engineering EXECUTE Flowlines General Activities | 116 | 170.5 | 117.69 | 69.03% | 25-Aug-14 A | 2015-03-05 | 213 | 2015-02-04 | 2015-02-04 | -20
P&IDs | P&IDs
FL-PR1010 | FL-PR1010 | Flowlines P&IDs & LDT - IFC | 25 | 259 | 0 | 0% | 2015-02-02 | 2015-03-09 | 201 | 2015-01-09 | 2015-02-13 | -15
Change Management | Change Management
FL-PR1030 | FL-PR1030 | Flowlines P&IDs & LDT Update (CN-021) | 55 | 130 | 39 | 30% | 01-Dec-14 A | 2015-01-30 | 201 |  | 2015-01-16 | -10
FL-PR1060 | FL-PR1060 | Reduction of Block and Bleed Valves (CN-014) | 20 | 38 | 38 | 100% | 01-Dec-14 A | 12-Dec-14 A |  |  | 2014-12-12 | 0
FL-PR1040 | FL-PR1040 | Pad 104 and 105 Valve Station (CN-001) | 10 | 20 | 2 | 10% | 08-Dec-14 A | 2015-01-16 | 286 |  | 2015-01-09 | -5
FL-PR1050 | FL-PR1050 | Condensate Accumulation Study (CN-016) | 10 | 35 | 3.5 | 10% | 08-Dec-14 A | 2015-01-23 | 281 |  | 2015-01-16 | -5
FL-PR1070 | FL-PR1070 | Battery Limit Conditions for JF3 CPF Option (CN-026) | 8 | 75 | 75 | 100% | 08-Dec-14 A | 17-Dec-14 A |  |  | 2014-12-17 | 0
Mechanical | Mechanical
General | General
Stress | Stress
FL-ME1080 | FL-ME1080 | Flowlines Stress Analysis (CN-013 Budget Tranfer to 3rd Party) | 69 | 9.5 | 9.5 | 100% | 08-Sep-14 A | 2015-01-23 | 157 | 2014-08-15 | 2014-12-19 | -15
Lists | Lists
Piping | Piping
General | General
FL-PI1040 | FL-PI1040 | Piping Design EXECUTE Flowlines General Activities - Reduced (CN-020) | 172 | 141 | 111 | 78.72% | 21-Jul-14 A | 2015-04-07 | 211 | 2015-05-01 | 2015-04-07 | 0
Specs | Specs
FL-PI1080 | FL-PI1080 | Piping Standards & Details - Reduced (CN-020) | 53 | 60 | 60 | 100% | 21-Jul-14 A | 31-Oct-14 A |  | 2014-08-15 | 2014-10-31 | 0
Plan Drawings | Plan Drawings
MTOs | MTOs
ISOs | ISOs
EWPs | EWPs
Model Development (Blowcases) - On Hold | Model Development (Blowcases) - On Hold
FL-PI1280 | FL-PI1280 | 60% Piping Model Development (Blowcases) - Reduced (CN-020) | 112 | 42.5 | 42.5 | 100% | 21-Jul-14 A | 17-Oct-14 A |  | 2014-11-05 | 2014-10-17 | 0
Structural | Structural
General | General
FL-CS1040 | FL-CS1040 | Structural EXECUTE Flowlines General Activities | 190 | 199.5 | 117.6 | 58.95% | 21-Jul-14 A | 2015-05-01 | 193 | 2015-05-01 | 2015-05-01 | 0
Model Development (Flowlines) | Model Development (Flowlines)
FL-CS1110 | FL-CS1110 | 60% Structural Model Development (Flowlines) | 53 | 387.5 | 387.5 | 100% | 21-Jul-14 A | 07-Oct-14 A |  | 2014-08-15 | 2014-10-07 | 0
FL-CS1120 | FL-CS1120 | 90% Structural Model Development (Flowlines) | 38 | 517 | 439.45 | 85% | 08-Oct-14 A | 2015-02-03 | 155 | 2014-10-14 | 2015-01-13 | -15
Piling & Steel Drawings | Piling & Steel Drawings
FL-CS1400 | FL-CS1400 | Flowlines Piling Drawings - IFR (Execute) | 79 | 877 | 789.3 | 90% | 21-Jul-14 A | 2015-01-30 | 94 | 2014-10-15 | 2015-01-30 | 0
FL-CS1410 | FL-CS1410 | Flowlines Pipe Support Drawings - IFR (Execute) | 79 | 945 | 850.5 | 90% | 21-Jul-14 A | 2015-01-30 | 94 | 2014-10-15 | 2015-01-30 | 0
FL-CS1440 | FL-CS1440 | Flowlines Valve Access Platform Drawings - IFR (Execute) | 25 | 341 | 68.2 | 20% | 15-Dec-14 A | 2015-01-30 | 94 | 2014-12-10 | 2015-01-30 | 0
FL-CS1420 | FL-CS1420 | Road Crossing Drawings - IFR (Execute) | 20 | 40 | 4 | 10% | 05-Jan-15 A | 2015-01-30 | 216 | 2014-10-29 | 2015-01-30 | 0
FL-CS1430 | FL-CS1430 | Animal Crossing Drawings - IFR (Execute) | 20 | 40 | 4 | 10% | 05-Jan-15 A | 2015-01-30 | 216 | 2014-10-29 | 2015-01-30 | 0
FL-CS1510 | FL-CS1510 | Flowlines Piling Drawings - IFC - Reduced (CN-020) | 25 | 362 | 0 | 0% | 2015-02-02 | 2015-03-09 | 152 | 2014-12-10 | 2015-03-09 | 0
FL-CS1530 | FL-CS1530 | Flowlines Pipe Support Drawings - IFC | 25 | 430 | 0 | 0% | 2015-02-02 | 2015-03-09 | 152 | 2014-12-10 | 2015-03-09 | 0
FL-CS1560 | FL-CS1560 | Flowlines Valve Access Platform Drawings - IFC | 25 | 152 | 0 | 0% | 2015-02-02 | 2015-03-09 | 152 | 2015-02-19 | 2015-03-30 | 15
FL-CS1580 | FL-CS1580 | Flowlines Piling Drawings - Client Review | 10 | 0 | 0 | 0% | 2015-02-03 | 2015-02-17 | 156 | 2014-10-30 | 2015-02-17 | 0
FL-CS1600 | FL-CS1600 | Flowlines Pipe Support Drawings - Client Review | 10 | 0 | 0 | 0% | 2015-02-03 | 2015-02-17 | 156 | 2014-10-30 | 2015-02-17 | 0
FL-CS1610 | FL-CS1610 | Road Crossing Drawings - Client Review | 10 | 0 | 0 | 0% | 2015-02-03 | 2015-02-17 | 216 | 2014-11-13 | 2015-02-17 | 0
FL-CS1620 | FL-CS1620 | Animal Crossing Drawings - Client Review | 10 | 0 | 0 | 0% | 2015-02-03 | 2015-02-17 | 216 | 2014-11-13 | 2015-02-17 | 0
FL-CS1630 | FL-CS1630 | Flowlines Valve Access Platform Drawings - Client Review | 10 | 0 | 0 | 0% | 2015-02-03 | 2015-02-17 | 156 | 2015-01-08 | 2015-02-17 | 0
FL-CS1540 | FL-CS1540 | Road Crossing Drawings - IFC | 25 | 18 | 0 | 0% | 2015-03-10 | 2015-04-14 | 186 | 2014-11-28 | 2015-03-30 | -10
FL-CS1550 | FL-CS1550 | Animal Crossing Drawings - IFC | 25 | 18 | 0 | 0% | 2015-03-10 | 2015-04-14 | 186 | 2014-11-28 | 2015-03-30 | -10
FL-CS1920 | FL-CS1920 | Flowlines Structural Calculation Reports - IFC | 25 | 105 | 0 | 0% | 2015-03-10 | 2015-04-14 | 186 | 2015-02-19 | 2015-04-14 | 0
FL-CS1460 | FL-CS1460 | Structural Engineering EWPs (Flowlines) - IFR (Execute) | 10 | 65 | 0 | 0% | 2015-03-31 | 2015-04-14 | 186 | 2015-03-05 | 2015-04-14 | 0
FL-CS1590 | FL-CS1590 | Structural Engineering EWPs (Flowlines) - Client Review | 10 | 0 | 0 | 0% | 2015-04-15 | 2015-04-28 | 186 | 2015-03-19 | 2015-04-28 | 0
FL-CS1520 | FL-CS1520 | Structural Engineering EWPs (Flowlines) - IFC | 10 | 15 | 0 | 0% | 2015-04-29 | 2015-05-12 | 186 | 2015-04-02 | 2015-05-12 | 0
MTOs | MTOs
FL-CS1080 | FL-CS1080 | Structural Key Quantities Update (IFR Flowlines) | 15 | 40 | 40 | 100% | 06-Nov-14 A | 26-Nov-14 A |  | 2014-08-29 | 2014-11-26 | 0
FL-CS2190 | FL-CS2190 | Structural Key Quantities Update (IFC Flowlines) | 10 | 40 | 0 | 0% | 2015-03-31 | 2015-04-14 | 186 | 2014-10-28 | 2015-01-27 | -53
Supply & Fabricate Pile Caps (FL-S101) | Supply & Fabricate Pile Caps (FL-S101)
Structural Steel for Flowlines (FL-S102) | Structural Steel for Flowlines (FL-S102)
Platforms & Skids Fabrication (FL-S103) | Platforms & Skids Fabrication (FL-S103)
FL-S101.R1 | FL-S101.R1 | Structural Steel for Flowlines MRQ - IFR (Execute) | 10 | 45 | 0 | 0% | 2015-02-02 | 2015-02-13 | 94 |  | 2015-02-13 | 0
FL-S101.R2 | FL-S101.R2 | Structural Steel for Flowlines MRQ - Client Review | 10 | 0 | 0 | 0% | 2015-02-18 | 2015-03-03 | 94 |  | 2015-03-03 | 0
FL-S101.R3 | FL-S101.R3 | Structural Steel for Flowlines MRQ - IFQ | 10 | 9 | 0 | 0% | 2015-03-05 | 2015-03-18 | 94 |  | 2015-03-18 | 0
Change Management | Change Management
FL-CS1140 | FL-CS1140 | North Access Road and Landfill Access Road (CN-007 from Early EXECUTE) | 106 | 20 | 20 | 100% | 21-Jul-14 A | 19-Sep-14 A |  | 2014-12-18 | 2014-09-19 | 0
FL-CS1160 | FL-CS1160 | Flowlines Valve Station Removal (CN-005) | 3 | 10 | 10 | 100% | 06-Oct-14 A | 08-Oct-14 A |  |  | 2014-10-08 | 0
FL-CS1170 | FL-CS1170 | Pad 104 and 105 Valve Station (CN-001) | 10 | 42 | 42 | 100% | 03-Nov-14 A | 14-Nov-14 A |  |  | 2014-11-14 | 0
FL-CS1180 | FL-CS1180 | Road Crossing at 7-2 Booster Station (CN-004) | 20 | 25 | 25 | 100% | 17-Nov-14 A | 28-Nov-14 A |  |  | 2014-11-28 | 0
FL-CS1190 | FL-CS1190 | Top of Steel Changes - Model (CN-018) | 47 | 160 | 136 | 85% | 17-Nov-14 A | 2015-02-03 | 274 |  | 2015-01-15 | -13
FL-CS2200 | FL-CS2200 | Top of Steel Changes - Drawings (CN-018) | 70 | 280 | 140 | 50% | 17-Nov-14 A | 2015-03-09 | 251 |  | 2015-03-09 | 0
FL-CS1200 | FL-CS1200 | Pipe Support Change - Model (CN-007) | 47 | 200 | 170 | 85% | 17-Nov-14 A | 2015-02-03 | 274 |  | 2015-01-15 | -13
FL-CS2210 | FL-CS2210 | Pipe Support Change - Drawings (CN-007) | 70 | 342 | 171 | 50% | 17-Nov-14 A | 2015-03-09 | 251 |  | 2015-03-09 | 0
FL-CS1150 | FL-CS1150 | Flowline ORI Requirements (CN-003) | 10 | 6 | 0 | 0% | 2015-05-26 | 2015-06-08 | 99 |  | 2015-01-23 | -93
Electrical | Electrical
General | General
FL-EL1000 | FL-EL1000 | Electrical EXECUTE Flowlines General Activities - Reduced | 39 | 36 | 36 | 100% | 22-Sep-14 A | 14-Nov-14 A |  | 2015-09-17 | 2014-11-14 | 0
Lists | Lists
Drawings | Drawings
MTOs | MTOs
Instrumentation | Instrumentation
Index | Index
Flowlines | Flowlines
General | General
FL-FL1000 | FL-FL1000 | Flowlines EXECUTE General Activities | 115 | 304.5 | 296.56 | 97.39% | 21-Jul-14 A | 2015-01-14 | 248 | 2015-01-14 | 2015-01-14 | 0
FL-FL1010 | FL-FL1010 | Flowlines Material Specification | 10 | 15 | 15 | 100% | 08-Sep-14 A | 14-Nov-14 A |  | 2014-08-01 | 2014-11-14 | 0
FL-FL1410 | FL-FL1410 | Flowlines ABSA Application | 10 | 20 | 0 | 0% | 2015-03-10 | 2015-03-23 | 201 | 2015-01-23 | 2015-03-02 | -15
Drawings | Drawings
FL-FL1020 | FL-FL1020 | Flowlines General Drawings - IFR (Execute) | 117 | 170.25 | 120.88 | 71% | 21-Jul-14 A | 2015-01-16 | 104 | 2014-08-15 | 2015-01-09 | -5
FL-FL1690 | FL-FL1690 | Flowlines General Arrangement Drawings - IFR - Reduced (CN-018) | 73 | 586.5 | 586.5 | 100% | 21-Jul-14 A | 14-Nov-14 A |  | 2014-11-26 | 2014-11-14 | 0
FL-FL2060 | FL-FL2060 | Flowlines Plan and Profile Drawings - IFR (Execute) | 120 | 503.75 | 277.07 | 55% | 21-Jul-14 A | 2015-01-23 | 206 |  | 2015-01-16 | -5
FL-FL2070 | FL-FL2070 | Flowlines ROW Sections Drawings - IFR (Execute) | 117 | 87.5 | 78.75 | 90% | 21-Jul-14 A | 2015-01-16 | 104 |  | 2015-01-09 | -5
FL-FL2080 | FL-FL2080 | Flowlines Loop Details Drawings - IFR (Execute) | 73 | 127.75 | 127.75 | 100% | 21-Jul-14 A | 17-Dec-14 A |  |  | 2014-12-17 | 0
FL-FL2100 | FL-FL2100 | Flowlines Typical Drawings - IFR (Execute) | 73 | 76.75 | 76.75 | 100% | 21-Jul-14 A | 19-Dec-14 A |  |  | 2014-12-19 | 0
FL-FL2120 | FL-FL2120 | Top of Steel Development | 73 | 72.75 | 72.75 | 100% | 21-Jul-14 A | 21-Nov-14 A |  |  | 2014-11-21 | 0
FL-FL2090 | FL-FL2090 | Flowlines Sections and Details Drawings - IFR (Execute) | 35 | 570.75 | 570.75 | 100% | 17-Nov-14 A | 16-Dec-14 A |  |  | 2014-12-16 | 0
FL-FL2110 | FL-FL2110 | Flowlines Bend Schedules - IFR (Execute) | 35 | 22 | 22 | 100% | 17-Nov-14 A | 16-Dec-14 A |  |  | 2014-12-16 | 0
FL-FL2190 | FL-FL2190 | Flowlines General Arrangement Drawings - IFC | 50 | 1190 | 249.9 | 21% | 15-Dec-14 A | 2015-03-09 | 162 |  | 2015-03-09 | 0
FL-FL2160 | FL-FL2160 | Flowlines Sections and Details Drawings - Client Review | 9 | 0 | 0 | 0% | 17-Dec-14 A | 2015-01-12 | 240 |  | 2015-01-13 | 1
FL-FL2180 | FL-FL2180 | Flowlines Bend Schedules - Client Review | 9 | 0 | 0 | 0% | 17-Dec-14 A | 2015-01-12 | 226 |  | 2015-01-13 | 1
FL-FL2200 | FL-FL2200 | Flowlines General Arrangement Drawings - Client Review | 9 | 0 | 0 | 0% | 17-Dec-14 A | 2015-01-12 | 181 |  | 2015-01-13 | 1
FL-FL2150 | FL-FL2150 | Flowlines Loop Details Drawings - Client Review | 8 | 0 | 0 | 0% | 18-Dec-14 A | 2015-01-12 | 240 |  | 2015-01-14 | 2
FL-FL2170 | FL-FL2170 | Flowlines Typical Drawings - Client Review | 10 | 0 | 0 | 0% | 05-Jan-15 A | 2015-01-16 | 220 |  | 2015-01-19 | 1
FL-FL2230 | FL-FL2230 | Flowlines Loop Details Drawings - IFC | 40 | 125 | 0 | 0% | 2015-01-12 | 2015-03-09 | 211 |  | 2015-03-09 | 0
FL-FL2240 | FL-FL2240 | Flowlines Sections and Details Drawings - IFC | 45 | 578 | 0 | 0% | 2015-01-12 | 2015-03-16 | 206 |  | 2015-03-16 | 0
FL-FL2260 | FL-FL2260 | Flowlines Bend Schedules - IFC | 23 | 10 | 0 | 0% | 2015-01-14 | 2015-02-13 | 226 |  | 2015-02-17 | 1
FL-FL1290 | FL-FL1290 | Flowlines General Drawings - IFC | 35 | 151 | 0 | 0% | 2015-01-19 | 2015-03-09 | 211 | 2014-12-02 | 2015-03-09 | 0
FL-FL2220 | FL-FL2220 | Flowlines ROW Sections Drawings - IFC | 40 | 120 | 0 | 0% | 2015-01-19 | 2015-03-16 | 206 |  | 2015-03-16 | 0
FL-FL1240 | FL-FL1240 | Flowlines General Drawings - Client Review | 10 | 0 | 0 | 0% | 2015-01-20 | 2015-02-02 | 225 | 2014-09-02 | 2015-01-26 | -5
FL-FL2140 | FL-FL2140 | Flowlines ROW Sections Drawings - Client Review | 10 | 0 | 0 | 0% | 2015-01-20 | 2015-02-02 | 225 |  | 2015-01-26 | -5
FL-FL2250 | FL-FL2250 | Flowlines Typical Drawings - IFC | 25 | 75 | 0 | 0% | 2015-01-20 | 2015-02-24 | 220 |  | 2015-02-25 | 1
FL-FL2210 | FL-FL2210 | Flowlines Plan and Profile Drawings - IFC | 35 | 510 | 0 | 0% | 2015-01-26 | 2015-03-16 | 206 |  | 2015-03-09 | -5
FL-FL2130 | FL-FL2130 | Flowlines Plan and Profile Drawings - Client Review | 10 | 0 | 0 | 0% | 2015-01-27 | 2015-02-09 | 220 |  | 2015-02-02 | -5
FL-PI1300 | FL-PI1300 | Location Specific Plan Drawings (Blowcases) - IFR (Execute) - Budget Transfer (CN-020) | 20 | 140 | 0 | 0% | 2015-02-23 | 2015-03-20 | 187 | 2015-03-16 | 2015-01-23 | -39
FL-PI1310 | FL-PI1310 | Location Specific Plan Drawings (Blowcases) - Client Review - Transfer (CN-020) | 10 | 0 | 0 | 0% | 2015-03-23 | 2015-04-06 | 187 | 2015-03-30 | 2015-02-06 | -39
FL-PI1320 | FL-PI1320 | Location Specific Plan Drawings (Blowcases) - IFC - Budget Transfer (CN-020) | 20 | 70 | 0 | 0% | 2015-03-23 | 2015-04-20 | 187 | 2015-04-15 | 2015-02-23 | -39
FL-PI1330 | FL-PI1330 | Location Specific ISOs (Blowcases) - IFC - Budget Transfer (CN-020) | 15 | 108 | 0 | 0% | 2015-04-21 | 2015-05-11 | 187 | 2015-05-13 | 2015-03-16 | -39
Lists | Lists
FL-FL1030 | FL-FL1030 | Flowlines Lists - IFR (Execute) | 87 | 25 | 25 | 100% | 21-Jul-14 A | 09-Jan-15 A |  | 2014-08-01 | 2014-12-18 | -6
FL-FL1420 | FL-FL1420 | Flowlines Lists - Client Review | 10 | 0 | 0 | 0% | 2015-01-13 | 2015-01-26 | 209 | 2014-08-19 | 2015-01-16 | -6
FL-FL1430 | FL-FL1430 | Flowlines Lists - IFC | 30 | 180 | 0 | 0% | 2015-01-28 | 2015-03-11 | 209 | 2014-12-02 | 2015-03-03 | -6
MTOs | MTOs
FL-FL1300 | FL-FL1300 | Flowlines Key Quantities Update (IFR Flowlines) | 8 | 30 | 30 | 100% | 24-Nov-14 A | 18-Dec-14 A |  | 2014-08-29 | 2014-12-18 | 0
FL-FL1670 | FL-FL1670 | Flowlines Key Quantities Update (IFC Flowlines) | 10 | 30 | 0 | 0% | 2015-03-03 | 2015-03-16 | 206 | 2014-10-28 | 2015-02-10 | -23
EWPs | EWPs
FL-FL1310 | FL-FL1310 | Flowlines EWPs - IFR | 15 | 60 | 0 | 0% | 2015-02-24 | 2015-03-16 | 206 | 2014-12-16 | 2015-03-23 | 5
FL-FL1700 | FL-FL1700 | Flowlines EWPs - Client Review | 10 | 0 | 0 | 0% | 2015-03-17 | 2015-03-30 | 206 | 2015-01-13 | 2015-04-07 | 5
FL-FL1400 | FL-FL1400 | Flowlines EWPs - IFC | 10 | 60 | 0 | 0% | 2015-03-31 | 2015-04-14 | 206 | 2015-01-27 | 2015-04-21 | 5
Model Development (Flowlines) | Model Development (Flowlines)
FL-FL1330 | FL-FL1330 | 60% Flowlines Model Development | 34 | 60 | 60 | 100% | 18-Aug-14 A | 07-Oct-14 A |  | 2014-08-15 | 2014-10-07 | 0
FL-FL1340 | FL-FL1340 | 90% Flowlines Model Development | 53 | 50 | 29 | 58% | 10-Nov-14 A | 2015-02-03 | 204 | 2014-10-14 | 2015-01-13 | -15
Manual Valves (FL-L820) | Manual Valves (FL-L820)
FL-L820.R1 | FL-L820.R1 | Manual Valves (Flowlines) MRQ - IFR (Execute) | 11 | 16 | 16 | 100% | 08-Sep-14 A | 22-Sep-14 A |  | 2014-09-23 | 2014-09-22 | 0
FL-L820.R2 | FL-L820.R2 | Manual Valves (Flowlines) MRQ - Client Review | 10 | 0 | 0 | 0% | 23-Sep-14 A | 21-Oct-14 A |  | 2014-10-08 | 2014-10-21 | 0
FL-L820.R3 | FL-L820.R3 | Manual Valves (Flowlines) MRQ - IFQ | 10 | 5 | 5 | 100% | 27-Oct-14 A | 10-Nov-14 A |  | 2014-10-24 | 2014-11-10 | 0
High Pressure Valves (FL-L821) | High Pressure Valves (FL-L821)
FL-L821.R1 | FL-L821.R1 | High Pressure Valves (Flowlines) MRQ - IFR (Execute) | 5 | 1 | 1 | 100% | 21-Jul-14 A | 25-Jul-14 A |  | 2014-07-25 | 2014-07-25 | 0
FL-L821.R2 | FL-L821.R2 | High Pressure Valves (Flowlines) MRQ - Client Review | 15 | 0 | 0 | 0% | 28-Jul-14 A | 18-Aug-14 A |  | 2014-08-12 | 2014-08-18 | 0
FL-L821.R3 | FL-L821.R3 | High Pressure Valves (Flowlines) MRQ - IFQ | 4 | 5 | 5 | 100% | 19-Aug-14 A | 22-Aug-14 A |  | 2014-08-27 | 2014-08-22 | 0
FL-L821.R4 | FL-L821.R4 | High Pressure Valves (Flowlines) MRQ - Re-IFQ | 15 | 0 | 0 | 0% | 15-Sep-14 A | 17-Sep-14 A |  |  | 2014-09-17 | 0
CSA High Grade Steam Line Pipe (FL-L831) | CSA High Grade Steam Line Pipe (FL-L831)
FL-L831.R1 | FL-L831.R1 | CSA High Grade Steam Line Pipe MRQ - IFR (Execute) | 34 | 12.75 | 12.75 | 100% | 21-Jul-14 A | 08-Sep-14 A |  | 2014-08-25 | 2014-09-08 | 0
FL-L831.R2 | FL-L831.R2 | CSA High Grade Steam Line Pipe MRQ - Client Review | 11 | 0 | 0 | 0% | 09-Sep-14 A | 23-Sep-14 A |  | 2014-09-10 | 2014-09-23 | 0
FL-L831.R3 | FL-L831.R3 | CSA High Grade Steam Line Pipe MRQ - IFQ | 10 | 5 | 5 | 100% | 24-Sep-14 A | 14-Nov-14 A |  | 2014-09-25 | 2014-11-14 | 0
ERW Line Pipe (FL-L832) | ERW Line Pipe (FL-L832)
FL-L832.R1 | FL-L832.R1 | ERW Line Pipe MRQ - IFR (Execute) | 40 | 12.75 | 12.75 | 100% | 21-Jul-14 A | 16-Sep-14 A |  | 2014-08-25 | 2014-09-16 | 0
FL-L832.R2 | FL-L832.R2 | ERW Line Pipe MRQ - Client Review | 10 | 0 | 0 | 0% | 17-Sep-14 A | 30-Sep-14 A |  | 2014-09-10 | 2014-09-30 | 0
FL-L832.R3 | FL-L832.R3 | ERW Line Pipe MRQ - IFQ | 10 | 5 | 5 | 100% | 01-Oct-14 A | 25-Nov-14 A |  | 2014-09-25 | 2014-11-25 | 0 | Re-issued Rev. C
ASME Pipe & Fittings (FL-L833) - Added PI-0077 (CN TBD) | ASME Pipe & Fittings (FL-L833) - Added PI-0077 (CN TBD)
FL-L833.R1 | FL-L833.R1 | ASME Pipe & Fittings MRQ - IFR (Execute) | 10 | 0 | 0 | 0% | 17-Nov-14 A | 28-Nov-14 A |  |  | 2014-11-28 | 0 | Rev.A
FL-L833.R2 | FL-L833.R2 | ASME Pipe & Fittings MRQ - Client Review | 21 | 0 | 0 | 0% | 01-Dec-14 A | 15-Dec-14 A |  |  | 2014-12-15 | 0
FL-L833.R3 | FL-L833.R3 | ASME Pipe & Fittings MRQ - IFQ | 10 | 0 | 0 | 0% | 16-Dec-14 A | 2015-01-23 | 65 |  | 2015-01-12 | -9
CSA High Grade Steam Fittings and Flanges (FL-L840) | CSA High Grade Steam Fittings and Flanges (FL-L840)
FL-L840.R1 | FL-L840.R1 | CSA High Grade Steam Fittings and Flanges - MRQ - IFR (Execute) | 10 | 16 | 16 | 100% | 06-Oct-14 A | 27-Nov-14 A |  | 2014-10-29 | 2014-11-27 | 0
FL-L840.R2 | FL-L840.R2 | CSA High Grade Steam Fittings and Flanges - MRQ - Client Review | 9 | 0 | 0 | 0% | 28-Nov-14 A | 10-Dec-14 A |  | 2014-11-13 | 2014-12-10 | 0
FL-L840.R3 | FL-L840.R3 | CSA High Grade Steam Fittings and Flanges - MRQ - IFQ | 10 | 5 | 4.5 | 90% | 11-Dec-14 A | 2015-01-20 | 116 | 2014-11-28 | 2015-01-09 | -7
CSA Grade 359 Fittings and Flanges (FL-L841) | CSA Grade 359 Fittings and Flanges (FL-L841)
FL-L841.R1 | FL-L841.R1 | CSA Grade 359 Fittings and Flanges - MRQ - IFR (Execute) | 10 | 16 | 16 | 100% | 10-Nov-14 A | 16-Dec-14 A |  | 2014-10-29 | 2014-12-16 | 0 | Postponed - Low Priority
FL-L841.R2 | FL-L841.R2 | CSA Grade 359 Fittings and Flanges - MRQ - Client Review | 9 | 0 | 0 | 0% | 17-Dec-14 A | 2015-01-12 | 162 | 2014-11-13 | 2015-01-13 | 1
FL-L841.R3 | FL-L841.R3 | CSA Grade 359 Fittings and Flanges - MRQ - IFQ | 11 | 5 | 0 | 0% | 2015-01-14 | 2015-01-28 | 162 | 2014-11-28 | 2015-01-28 | 0
ERW Induction Bends (FL-L842) | ERW Induction Bends (FL-L842)
FL-L842.R1 | FL-L842.R1 | ERW Induction Bends MRQ - IFR (Execute) | 10 | 16 | 0 | 0% | 2015-01-19 | 2015-01-30 | 126 | 2014-12-17 | 2015-01-30 | 0
FL-L842.R2 | FL-L842.R2 | ERW Induction Bends MRQ - Client Review | 10 | 0 | 0 | 0% | 2015-02-03 | 2015-02-17 | 126 | 2015-01-15 | 2015-02-17 | 0
FL-L842.R3 | FL-L842.R3 | ERW Induction Bends MRQ - IFQ | 10 | 5 | 0 | 0% | 2015-02-19 | 2015-03-04 | 126 | 2015-01-30 | 2015-03-04 | 0
Pre-Insulated Pipe Supports (FL-L850) | Pre-Insulated Pipe Supports (FL-L850)
FL-L850.R1 | FL-L850.R1 | Pre-Insulated Pipe Supports MRQ - IFR (Execute) | 10 | 16 | 16 | 100% | 17-Nov-14 A | 09-Jan-15 A |  | 2014-10-07 | 2014-12-19 | -5 | Waiting for Shoe Info
FL-L850.R2 | FL-L850.R2 | Pre-Insulated Pipe Supports MRQ - Client Review | 2 | 0 | 0 | 0% | 12-Jan-15 A | 13-Jan-15 A |  | 2014-10-23 | 2015-01-19 | 4
FL-L850.R3 | FL-L850.R3 | Pre-Insulated Pipe Supports MRQ - IFQ | 10 | 5 | 0 | 0% | 2015-01-13 | 2015-01-26 | 83 | 2014-11-07 | 2015-02-03 | 6
Change Management | Change Management
FL-FL2010 | FL-FL2010 | North Access Road and Landfill Access Road (Early EXECUTE CN-007) | 106 | 80 | 80 | 100% | 21-Jul-14 A | 19-Sep-14 A |  | 2014-12-18 | 2014-09-19 | 0
FL-FL2050 | FL-FL2050 | Flowlines Valve Station Removal (CN-005) | 3 | 20 | 20 | 100% | 06-Oct-14 A | 08-Oct-14 A |  |  | 2014-10-08 | 0
FL-FL2270 | FL-FL2270 | Pad 104 and 105 Valve Station (CN-001) | 10 | 134 | 134 | 100% | 03-Nov-14 A | 14-Nov-14 A |  |  | 2014-11-14 | 0
FL-FL2040 | FL-FL2040 | High Pressure Valve MR Transfer (CN-008) | 40 | 28.5 | 6.75 | 23.68% | 10-Nov-14 A | 2015-01-30 | 5 |  | 2015-01-16 | -10
FL-FL2280 | FL-FL2280 | Future Tie-In Design Study (CN-017) | 20 | 54 | 54 | 100% | 17-Nov-14 A | 12-Dec-14 A |  |  | 2014-12-12 | 0
FL-FL2290 | FL-FL2290 | Reduction of Block and Bleed Valves (CN-014) | 20 | 42 | 42 | 100% | 17-Nov-14 A | 12-Dec-14 A |  |  | 2014-12-12 | 0
FL-FL2300 | FL-FL2300 | Top of Steel Changes - Adjustment (CN-018) | 20 | 60 | 60 | 100% | 17-Nov-14 A | 10-Dec-14 A |  |  | 2014-12-10 | 0
FL-FL2310 | FL-FL2310 | Top of Steel Changes - Model (CN-018) | 30 | 270 | 270 | 100% | 17-Nov-14 A | 10-Dec-14 A |  |  | 2014-12-10 | 0
FL-FL2330 | FL-FL2330 | Top of Steel Changes - General Arrangement Drawings (CN-018) | 30 | 1309 | 1309 | 100% | 17-Nov-14 A | 16-Dec-14 A |  |  | 2014-12-16 | 0
FL-FL2340 | FL-FL2340 | Pipe Support Change (CN-007) | 20 | 125 | 125 | 100% | 17-Nov-14 A | 10-Dec-14 A |  |  | 2014-12-10 | 0
FL-FL2320 | FL-FL2320 | Top of Steel Changes - Plan and Profile Drawings (CN-018) | 15 | 204 | 20.4 | 10% | 15-Dec-14 A | 2015-01-23 | 281 |  | 2015-01-16 | -5
FL-FL2030 | FL-FL2030 | Flowline ORI Requirements (CN-003) | 80 | 18 | 0 | 0% | 2015-01-26 | 2015-05-20 | 134 |  | 2015-05-05 | -10
Civil Earthworks | Civil Earthworks
General | General
FL-CE1000 | FL-CE1000 | Civil Earthworks EXECUTE Flowlines General Activities | 115 | 534.5 | 474.08 | 88.7% | 21-Jul-14 A | 2015-01-28 | 238 | 2015-01-14 | 2015-01-14 | -10
FL-CE1320 | FL-CE1320 | Proposed Legal Boundary Plan - Re-IFU | 10 | 7 | 0 | 0% | 2015-02-02 | 2015-02-13 | 216 | 2014-10-15 | 2015-01-30 | -10
EWPs | EWPs
FL-CE1290 | FL-CE1290 | Bulk Earthworks EWP - IFR (Execute) | 10 | 51 | 0 | 0% | 2015-01-19 | 2015-01-30 | 214 | 2014-11-13 | 2015-01-16 | -10
FL-CE1400 | FL-CE1400 | Bulk Earthworks EWP - Client Review | 10 | 0 | 0 | 0% | 2015-02-03 | 2015-02-17 | 214 | 2014-11-28 | 2015-02-02 | -10
FL-CE1310 | FL-CE1310 | Bulk Earthworks EWP - IFC | 10 | 9 | 0 | 0% | 2015-02-19 | 2015-03-04 | 214 | 2014-12-15 | 2015-02-18 | -10
Wellpads | Wellpads
FL-CE1720 | FL-CE1720 | Civil Wellpads Drawings - Client Review | 43 | 0 | 0 | 0% | 21-Jul-14 A | 29-Aug-14 A |  | 2014-08-01 | 2014-08-29 | 0
FL-CE1770 | FL-CE1770 | Civil Wellpads MTO Update | 20 | 48 | 33.6 | 70% | 08-Sep-14 A | 2015-01-30 | 236 | 2014-09-30 | 2015-01-16 | -10
FL-CE1750 | FL-CE1750 | Civil Wellpads Drawings - IFC | 36 | 236 | 236 | 100% | 27-Oct-14 A | 17-Dec-14 A |  | 2014-09-16 | 2014-12-17 | 0
FL-CE1780 | FL-CE1780 | Wellpads Calculations Report | 25 | 17 | 3.4 | 20% | 01-Dec-14 A | 2015-01-30 | 226 | 2014-10-15 | 2015-01-16 | -10
Civil Model Development (Wellpads) | Civil Model Development (Wellpads)
FL-CE1740 | FL-CE1740 | 90% Civil 3D Model (Wellpads) | 53 | 50 | 50 | 100% | 21-Jul-14 A | 07-Oct-14 A |  | 2014-08-15 | 2014-10-07 | 0
Clearing and Grubbing (Removed CN-015) | Clearing and Grubbing (Removed CN-015)
FL-CE1110 | FL-CE1110 | Civil Clearing and Grubbing Drawings - IFR (Execute) - Reduced (CN-015) | 63 | 132.75 | 132.75 | 100% | 21-Jul-14 A | 03-Oct-14 A |  | 2014-09-17 | 2014-10-03 | 0
Access Roads and FL Corridor | Access Roads and FL Corridor
FL-CE1480 | FL-CE1480 | Civil Flowline Corridor Drawings - IFR (Execute) | 43 | 402 | 402 | 100% | 21-Jul-14 A | 10-Sep-14 A |  | 2014-08-01 | 2014-09-10 | 0
FL-CE1650 | FL-CE1650 | Access Roads & FL Corridor MTO Update | 30 | 68 | 47.6 | 70% | 08-Sep-14 A | 2015-01-30 | 226 | 2014-09-30 | 2015-01-16 | -10
FL-CE1540 | FL-CE1540 | Civil Flowline Corridor Drawings - Client Review | 10 | 0 | 0 | 0% | 10-Sep-14 A | 23-Sep-14 A |  | 2014-08-19 | 2014-09-23 | 0
FL-CE1670 | FL-CE1670 | Acess Roads & Flowline Corridor Calculations | 60 | 232 | 139.2 | 60% | 22-Sep-14 A | 2015-01-30 | 226 | 2014-10-29 | 2015-01-16 | -10
FL-CE1600 | FL-CE1600 | Civil Flowline Corridor Drawings - IFC | 35 | 483 | 386.4 | 80% | 03-Nov-14 A | 2015-01-30 | 214 | 2014-10-15 | 2015-01-16 | -10
Civil Model Development (Corridor) | Civil Model Development (Corridor)
FL-CE1590 | FL-CE1590 | 90% Civil 3D Model (Corridor) | 53 | 106 | 106 | 100% | 21-Jul-14 A | 07-Oct-14 A |  | 2014-08-15 | 2014-10-07 | 0
Road Signage | Road Signage
FL-CE1800 | FL-CE1800 | Civil Road Signage Drawings - IFR (Execute) | 27 | 162 | 162 | 100% | 11-Sep-14 A | 24-Oct-14 A |  | 2014-11-05 | 2014-10-24 | 0
FL-CE1820 | FL-CE1820 | Civil Road Signage Drawings - Client Review | 10 | 0 | 0 | 0% | 27-Oct-14 A | 07-Nov-14 A |  | 2014-11-20 | 2014-11-07 | 0
FL-CE1850 | FL-CE1850 | Civil Road Signage Drawings - IFC | 29 | 99 | 59.4 | 60% | 11-Nov-14 A | 2015-01-23 | 209 | 2014-12-04 | 2015-01-09 | -10
FL-CE1810 | FL-CE1810 | Signage EWP - IFR (Execute) | 10 | 7 | 0 | 0% | 2015-01-26 | 2015-02-06 | 209 | 2014-12-18 | 2015-01-23 | -10
FL-CE1840 | FL-CE1840 | Signage EWP - Client Review | 10 | 0 | 0 | 0% | 2015-02-10 | 2015-02-24 | 209 | 2015-01-16 | 2015-02-09 | -10
FL-CE1870 | FL-CE1870 | Signage EWP - IFC | 10 | 3 | 0 | 0% | 2015-02-26 | 2015-03-11 | 209 | 2015-01-30 | 2015-02-25 | -10
Tank Containment (Removed CN-019) | Tank Containment (Removed CN-019)
Change Management | Change Management
FL-CE2060 | FL-CE2060 | North Access Road and Landfill Access Road (CN-007 from Early EXECUTE) | 106 | 513 | 513 | 100% | 21-Jul-14 A | 19-Dec-14 A |  | 2014-12-18 | 2014-12-19 | 0
FL-CE2070 | FL-CE2070 | CPF South Access Road Shift (CN-002) | 29 | 177 | 177 | 100% | 22-Sep-14 A | 09-Jan-15 A |  |  | 2015-01-09 | 0
FL-CE2080 | FL-CE2080 | Pad 104 and 105 Valve Station (CN-001) | 10 | 70 | 70 | 100% | 03-Nov-14 A | 14-Nov-14 A |  |  | 2014-11-14 | 0
FL-CE2090 | FL-CE2090 | Road Crossing at 7-2 Booster Station (CN-004) | 10 | 24 | 24 | 100% | 17-Nov-14 A | 28-Nov-14 A |  |  | 2014-11-28 | 0
FL-CE2100 | FL-CE2100 | Top of Steel Changes - Model (CN-018) | 30 | 125 | 100 | 80% | 17-Nov-14 A | 2015-02-03 | 274 |  | 2015-01-09 | -17
PROCUREMENT | PROCUREMENT
General | General
Structural | Structural
Structural Steel for Flowlines (FL-S101) | Structural Steel for Flowlines (FL-S101)
FL-S101.00 | FL-S101.00 | Structural Steel for Flowlines - MR Release to Client Eng | 5 | 0 | 0 | 0% | 2015-03-20 | 2015-03-26 | 94 | 2014-12-15 | 2015-03-26 | 0
FL-S101.01 | FL-S101.01 | Structural Steel for Flowlines - MR Release to Client Proc - Prepare MRQ Package | 5 | 0 | 0 | 0% | 2015-03-27 | 2015-04-02 | 94 | 2015-01-05 | 2015-04-02 | 0
FL-S101.02 | FL-S101.02 | Structural Steel for Flowlines - RFP Approval & Issue to Vendors | 15 | 0 | 0 | 0% | 2015-04-06 | 2015-04-24 | 94 | 2015-01-26 | 2015-04-24 | 0
FL-S101.03 | FL-S101.03 | Structural Steel for Flowlines - Proposal Received by Client Proc | 5 | 0 | 0 | 0% | 2015-04-27 | 2015-05-01 | 94 | 2015-02-02 | 2015-05-01 | 0
FL-S101.04 | FL-S101.04 | Structural Steel for Flowlines - Commercial Bid Evaluation by Client Proc | 25 | 0 | 0 | 0% | 2015-05-04 | 2015-06-08 | 94 | 2015-03-10 | 2015-06-08 | 0
FL-S101.05 | FL-S101.05 | Structural Steel for Flowlines - Technical Bid Evaluation | 15 | 18 | 0 | 0% | 2015-05-04 | 2015-05-25 | 94 | 2015-02-24 | 2015-05-25 | 0
FL-S101.06 | FL-S101.06 | Structural Steel for Flowlines - Review Technical Bid Evaluation by Client Eng | 5 | 0 | 0 | 0% | 2015-05-26 | 2015-06-01 | 94 | 2015-03-03 | 2015-06-01 | 0
FL-S101.07 | FL-S101.07 | Structural Steel for Flowlines - Prepare & Issue MRP | 10 | 18 | 0 | 0% | 2015-06-02 | 2015-06-15 | 94 | 2015-03-17 | 2015-06-15 | 0
FL-S101.08 | FL-S101.08 | Structural Steel for Flowlines - LOR Preparation & Approval | 7 | 0 | 0 | 0% | 2015-06-09 | 2015-06-17 | 94 | 2015-03-19 | 2015-06-17 | 0
FL-S101.09 | FL-S101.09 | Structural Steel for Flowlines - MRP Review by Client Eng | 5 | 0 | 0 | 0% | 2015-06-18 | 2015-06-24 | 94 | 2015-03-24 | 2015-06-24 | 0
FL-S101.10 | FL-S101.10 | Structural Steel for Flowlines - MRP Release to Client Proc - Prepare PO | 20 | 0 | 0 | 0% | 2015-06-25 | 2015-07-23 | 94 | 2015-04-22 | 2015-07-23 | 0
FL-S101.11 | FL-S101.11 | Structural Steel for Flowlines - Issue PO | 0 | 0 | 0 | 0% |  | 2015-07-23 | 94 | 2015-04-22 | 2015-07-23 | 0
FL-S101.20 | FL-S101.20 | Structural Steel for Flowlines - Manufacturing & Delivery | 70 | 0 | 0 | 0% | 2015-07-24 | 2015-10-29 | 97 | 2015-06-17 | 2015-10-29 | 0
FL-S101.30 | FL-S101.30 | Structural Steel for Flowlines - First Submission of Shop Drawings | 10 | 0 | 0 | 0% | 2015-07-24 | 2015-08-06 | 126 | 2015-05-06 | 2015-08-06 | 0
FL-S101.40 | FL-S101.40 | Structural Steel for Flowlines - Shop Drawings Review | 10 | 0 | 0 | 0% | 2015-08-07 | 2015-08-20 | 117 | 2015-05-21 | 2015-08-20 | 0
FL-S101.50 | FL-S101.50 | Structural Steel for Flowlines - Vendor Revising Drawings | 10 | 0 | 0 | 0% | 2015-08-21 | 2015-09-03 | 127 | 2015-06-04 | 2015-09-03 | 0
FL-S101.60 | FL-S101.60 | Structural Steel for Flowlines - Code 1/2 Shop Drawings | 10 | 0 | 0 | 0% | 2015-09-04 | 2015-09-18 | 117 | 2015-06-18 | 2015-09-18 | 0
Flowlines | Flowlines
Manual Valves (FL-L820) | Manual Valves (FL-L820)
FL-L820.00 | FL-L820.00 | Manual Valves (Flowlines) - MR Release to Client Eng | 1 | 0 | 0 | 0% | 11-Nov-14 A | 17-Nov-14 A |  | 2014-11-03 | 2014-11-17 | 0
FL-L820.01 | FL-L820.01 | Manual Valves (Flowlines) - MR Release to Client Proc - Prepare MRQ Package | 5 | 0 | 0 | 0% | 18-Nov-14 A | 24-Nov-14 A |  | 2014-11-10 | 2014-11-24 | 0
FL-L820.02 | FL-L820.02 | Manual Valves (Flowlines) - RFP Approval & Issue to Vendors | 15 | 0 | 0 | 0% | 25-Nov-14 A | 15-Dec-14 A |  | 2014-12-01 | 2014-12-15 | 0
FL-L820.03 | FL-L820.03 | Manual Valves (Flowlines) - Proposal Received by Client Proc | 1 | 0 | 0 | 0% | 16-Dec-14 A | 16-Dec-14 A |  | 2014-12-08 | 2014-12-16 | 0
FL-L820.04 | FL-L820.04 | Manual Valves (Flowlines) - Commercial Bid Evaluation by Client Proc | 22 | 0 | 0 | 0% | 17-Dec-14 A | 2015-01-29 | 62 | 2015-01-26 | 2015-01-29 | 0
FL-L820.05 | FL-L820.05 | Manual Valves (Flowlines) - Technical Bid Evaluation | 12 | 16 | 12 | 75% | 17-Dec-14 A | 2015-01-16 | 58 | 2015-01-12 | 2015-01-15 | -1
FL-L820.06 | FL-L820.06 | Manual Valves (Flowlines) - Review Technical Bid Evaluation by Client Eng | 5 | 0 | 0 | 0% | 2015-01-19 | 2015-01-23 | 58 | 2015-01-19 | 2015-01-22 | -1
FL-L820.07 | FL-L820.07 | Manual Valves (Flowlines) - Prepare & Issue MRP | 10 | 5 | 0 | 0% | 2015-01-26 | 2015-02-06 | 58 | 2015-02-02 | 2015-02-05 | -1
FL-L820.08 | FL-L820.08 | Manual Valves (Flowlines) - LOR Preparation & Approval | 7 | 0 | 0 | 0% | 2015-02-02 | 2015-02-10 | 61 | 2015-02-04 | 2015-02-09 | -1
FL-L820.09 | FL-L820.09 | Manual Valves (Flowlines) - MRP Review by Client Eng | 5 | 0 | 0 | 0% | 2015-02-09 | 2015-02-13 | 58 | 2015-02-09 | 2015-02-12 | -1
FL-L820.10 | FL-L820.10 | Manual Valves (Flowlines) - MRP Release to Client Proc - Prepare PO | 10 | 0 | 0 | 0% | 2015-02-17 | 2015-03-02 | 58 | 2015-02-24 | 2015-02-27 | -1
FL-L820.11 | FL-L820.11 | Manual Valves (Flowlines) - Issue PO | 0 | 0 | 0 | 0% |  | 2015-03-02 | 58 | 2015-02-24 | 2015-02-27 | -1
FL-L820.20 | FL-L820.20 | Manual Valves (Flowlines) - Manufacturing & Delivery | 210 | 0 | 0 | 0% | 2015-03-03 | 2015-12-21 | 60 | 2015-12-15 | 2015-12-18 | -1
FL-L820.30 | FL-L820.30 | Manual Valves (Flowlines) - First Submission of Vendor Data | 10 | 0 | 0 | 0% | 2015-03-03 | 2015-03-16 | 229 | 2015-03-10 | 2015-03-13 | -1
FL-L820.40 | FL-L820.40 | Manual Valves (Flowlines) - Vendor Data Review | 10 | 5 | 0 | 0% | 2015-03-17 | 2015-03-30 | 216 | 2015-03-24 | 2015-03-27 | -1
FL-L820.50 | FL-L820.50 | Manual Valves (Flowlines) - Vendor Revising Data | 10 | 0 | 0 | 0% | 2015-03-31 | 2015-04-13 | 230 | 2015-04-07 | 2015-04-10 | -1
FL-L820.60 | FL-L820.60 | Manual Valves (Flowlines) - Final Vendor Data | 10 | 0 | 0 | 0% | 2015-04-14 | 2015-04-27 | 217 | 2015-04-21 | 2015-04-24 | -1
High Pressure Valves - WP and FL (FL-L821) | High Pressure Valves - WP and FL (FL-L821)
FL-L821.00 | FL-L821.00 | High Pressure Valves (Flowlines) - MR Release to Client Eng | 1 | 0 | 0 | 0% | 18-Sep-14 A | 18-Sep-14 A |  | 2014-09-05 | 2014-09-18 | 0
FL-L821.01 | FL-L821.01 | High Pressure Valves (Flowlines) - MR Release to Client Proc - Prepare MRQ Package | 15 | 0 | 0 | 0% | 19-Sep-14 A | 09-Oct-14 A |  | 2014-09-12 | 2014-10-09 | 0
FL-L821.02 | FL-L821.02 | High Pressure Valves (Flowlines) - RFP Approval & Issue to Vendors | 15 | 0 | 0 | 0% | 10-Oct-14 A | 31-Oct-14 A |  | 2014-10-03 | 2014-10-31 | 0
FL-L821.03 | FL-L821.03 | High Pressure Valves (Flowlines) - Proposal Received by Client Proc | 5 | 0 | 0 | 0% | 03-Nov-14 A | 05-Nov-14 A |  | 2014-10-10 | 2014-11-05 | 0
FL-L821.04 | FL-L821.04 | High Pressure Valves (Flowlines) - Commercial Bid Evaluation by Client Proc | 25 | 0 | 0 | 0% | 10-Nov-14 A | 2015-01-23 | 8 | 2014-11-17 | 2015-01-09 | -10
FL-L821.05 | FL-L821.05 | High Pressure Valves (Flowlines) - Technical Bid Evaluation | 15 | 16 | 12 | 75% | 10-Nov-14 A | 2015-01-16 | 0 | 2014-11-03 | 2014-12-19 | -10 | Waiting for quotes on valves changes
FL-L821.06 | FL-L821.06 | High Pressure Valves (Flowlines) - Review Technical Bid Evaluation by Client Eng | 5 | 0 | 0 | 0% | 2015-01-19 | 2015-01-23 | 0 | 2014-11-10 | 2015-01-09 | -10
FL-L821.07 | FL-L821.07 | High Pressure Valves (Flowlines) - Prepare & Issue MRP | 10 | 5 | 0 | 0% | 2015-01-26 | 2015-02-06 | 0 | 2014-11-24 | 2015-01-23 | -10
FL-L821.08 | FL-L821.08 | High Pressure Valves (Flowlines) - LOR Preparation & Approval | 7 | 0 | 0 | 0% | 2015-02-02 | 2015-02-10 | 3 | 2014-11-26 | 2015-01-27 | -10
FL-L821.09 | FL-L821.09 | High Pressure Valves (Flowlines) - MRP Review by Client Eng | 5 | 0 | 0 | 0% | 2015-02-09 | 2015-02-13 | 0 | 2014-12-01 | 2015-01-30 | -10
FL-L821.10 | FL-L821.10 | High Pressure Valves (Flowlines) - MRP Release to Client Proc - Prepare PO | 10 | 0 | 0 | 0% | 2015-02-17 | 2015-03-02 | 0 | 2014-12-15 | 2015-02-13 | -10
FL-L821.11 | FL-L821.11 | High Pressure Valves (Flowlines) - Issue PO | 0 | 0 | 0 | 0% |  | 2015-03-02 | 0 | 2014-12-15 | 2015-02-13 | -10
FL-L821.20 | FL-L821.20 | High Pressure Valves (Flowlines) - Manufacturing & Delivery | 270 | 0 | 0 | 0% | 2015-03-03 | 2016-03-14 | 0 | 2015-12-28 | 2016-02-26 | -11
FL-L821.30 | FL-L821.30 | High Pressure Valves (Flowlines) - First Submission of Vendor Data | 10 | 0 | 0 | 0% | 2015-03-03 | 2015-03-16 | 229 | 2014-12-29 | 2015-02-27 | -11
FL-L821.40 | FL-L821.40 | High Pressure Valves (Flowlines) - Vendor Data Review | 10 | 5 | 0 | 0% | 2015-03-17 | 2015-03-30 | 216 | 2015-01-16 | 2015-03-13 | -11
FL-L821.50 | FL-L821.50 | High Pressure Valves (Flowlines) - Vendor Revising Data | 10 | 0 | 0 | 0% | 2015-03-31 | 2015-04-13 | 230 | 2015-01-30 | 2015-03-27 | -11
FL-L821.60 | FL-L821.60 | High Pressure Valves (Flowlines) - Final Vendor Data | 10 | 0 | 0 | 0% | 2015-04-14 | 2015-04-27 | 217 | 2015-02-13 | 2015-04-13 | -10
CSA High Grade Steam Line Pipe (FL-L831) | CSA High Grade Steam Line Pipe (FL-L831)
FL-L831.00 | FL-L831.00 | CSA High Grade Steam Line Pipe - MR Release to Client Eng | 5 | 0 | 0 | 0% | 17-Nov-14 A | 21-Nov-14 A |  | 2014-10-03 | 2014-11-21 | 0
FL-L831.01 | FL-L831.01 | CSA High Grade Steam Line Pipe - MR Release to Client Proc - Prepare MRQ Package | 5 | 0 | 0 | 0% | 24-Nov-14 A | 18-Dec-14 A |  | 2014-10-10 | 2014-12-17 | -1
FL-L831.02 | FL-L831.02 | CSA High Grade Steam Line Pipe - RFP Approval & Issue to Vendors | 15 | 0 | 0 | 0% | 19-Dec-14 A | 2015-01-22 | 45 | 2014-11-03 | 2015-01-21 | -1
FL-L831.03 | FL-L831.03 | CSA High Grade Steam Line Pipe - Proposal Received by Client Proc | 4 | 0 | 0 | 0% | 2015-01-23 | 2015-01-28 | 45 | 2014-11-10 | 2015-01-27 | -1
FL-L831.04 | FL-L831.04 | CSA High Grade Steam Line Pipe - Commercial Bid Evaluation by Client Proc | 25 | 0 | 0 | 0% | 2015-01-29 | 2015-03-05 | 48 | 2014-12-15 | 2015-03-04 | -1
FL-L831.05 | FL-L831.05 | CSA High Grade Steam Line Pipe - Technical Bid Evaluation | 15 | 16 | 0 | 0% | 2015-01-29 | 2015-02-19 | 45 | 2014-12-01 | 2015-02-18 | -1
FL-L831.06 | FL-L831.06 | CSA High Grade Steam Line Pipe - Review Technical Bid Evaluation by Client Eng | 5 | 0 | 0 | 0% | 2015-02-20 | 2015-02-26 | 45 | 2014-12-08 | 2015-02-25 | -1
FL-L831.07 | FL-L831.07 | CSA High Grade Steam Line Pipe - Prepare & Issue MRP | 10 | 5 | 0 | 0% | 2015-02-27 | 2015-03-12 | 45 | 2015-01-05 | 2015-03-11 | -1
FL-L831.08 | FL-L831.08 | CSA High Grade Steam Line Pipe - LOR Preparation & Approval | 7 | 0 | 0 | 0% | 2015-03-06 | 2015-03-16 | 48 | 2015-01-07 | 2015-03-13 | -1
FL-L831.09 | FL-L831.09 | CSA High Grade Steam Line Pipe - MRP Review by Client Eng | 5 | 0 | 0 | 0% | 2015-03-13 | 2015-03-19 | 45 | 2015-01-12 | 2015-03-18 | -1
FL-L831.10 | FL-L831.10 | CSA High Grade Steam Line Pipe - MRP Release to Client Proc - Prepare PO | 10 | 0 | 0 | 0% | 2015-03-20 | 2015-04-02 | 45 | 2015-01-26 | 2015-04-01 | -1
FL-L831.11 | FL-L831.11 | CSA High Grade Steam Line Pipe - Issue PO | 0 | 0 | 0 | 0% |  | 2015-04-02 | 45 | 2015-01-26 | 2015-04-01 | -1
FL-L831.20 | FL-L831.20 | CSA High Grade Steam Line Pipe - Manufacturing & Delivery | 200 | 0 | 0 | 0% | 2015-04-03 | 2016-01-07 | 47 | 2015-11-02 | 2016-01-06 | -1
FL-L831.30 | FL-L831.30 | CSA High Grade Steam Line Pipe - First Submission of Vendor Data | 10 | 0 | 0 | 0% | 2015-04-03 | 2015-04-16 | 206 | 2015-02-09 | 2015-04-15 | -1
FL-L831.40 | FL-L831.40 | CSA High Grade Steam Line Pipe - Vendor Data Review | 10 | 5 | 0 | 0% | 2015-04-17 | 2015-04-30 | 194 | 2015-02-24 | 2015-04-29 | -1
FL-L831.50 | FL-L831.50 | CSA High Grade Steam Line Pipe - Vendor Revising Data | 10 | 0 | 0 | 0% | 2015-05-01 | 2015-05-14 | 207 | 2015-03-10 | 2015-05-13 | -1
FL-L831.60 | FL-L831.60 | CSA High Grade Steam Line Pipe - Final Vendor Data | 10 | 0 | 0 | 0% | 2015-05-15 | 2015-05-29 | 194 | 2015-03-24 | 2015-05-28 | -1
ERW Line Pipe (FL-L832) | ERW Line Pipe (FL-L832)
FL-L832.00 | FL-L832.00 | ERW Line Pipe - MR Release to Client Eng | 5 | 0 | 0 | 0% | 26-Nov-14 A | 01-Dec-14 A |  | 2014-10-03 | 2014-12-01 | 0
FL-L832.01 | FL-L832.01 | ERW Line Pipe - MR Release to Client Proc - Prepare MRQ Package | 5 | 0 | 0 | 0% | 02-Dec-14 A | 18-Dec-14 A |  | 2014-10-10 | 2014-12-17 | -1
FL-L832.02 | FL-L832.02 | ERW Line Pipe - RFP Approval & Issue to Vendors | 15 | 0 | 0 | 0% | 19-Dec-14 A | 2015-01-22 | 6 | 2014-11-03 | 2015-01-21 | -1
FL-L832.03 | FL-L832.03 | ERW Line Pipe - Proposal Received by Client Proc | 4 | 0 | 0 | 0% | 2015-01-23 | 2015-01-28 | 6 | 2014-11-10 | 2015-01-27 | -1
FL-L832.04 | FL-L832.04 | ERW Line Pipe - Commercial Bid Evaluation by Client Proc | 25 | 0 | 0 | 0% | 2015-01-29 | 2015-03-05 | 9 | 2014-12-15 | 2015-03-04 | -1
FL-L832.05 | FL-L832.05 | ERW Line Pipe - Technical Bid Evaluation | 15 | 16 | 0 | 0% | 2015-01-29 | 2015-02-19 | 6 | 2014-12-01 | 2015-02-18 | -1
FL-L832.06 | FL-L832.06 | ERW Line Pipe - Review Technical Bid Evaluation by Client Eng | 5 | 0 | 0 | 0% | 2015-02-20 | 2015-02-26 | 6 | 2014-12-08 | 2015-02-25 | -1
FL-L832.07 | FL-L832.07 | ERW Line Pipe - Prepare & Issue MRP | 10 | 5 | 0 | 0% | 2015-02-27 | 2015-03-12 | 6 | 2015-01-05 | 2015-03-11 | -1
FL-L832.08 | FL-L832.08 | ERW Line Pipe - LOR Preparation & Approval | 7 | 0 | 0 | 0% | 2015-03-06 | 2015-03-16 | 9 | 2015-01-07 | 2015-03-13 | -1
FL-L832.09 | FL-L832.09 | ERW Line Pipe - MRP Review by Client Eng | 5 | 0 | 0 | 0% | 2015-03-13 | 2015-03-19 | 6 | 2015-01-12 | 2015-03-18 | -1
FL-L832.10 | FL-L832.10 | ERW Line Pipe - MRP Release to Client Proc - Prepare PO | 10 | 0 | 0 | 0% | 2015-03-20 | 2015-04-02 | 6 | 2015-01-26 | 2015-04-01 | -1
FL-L832.11 | FL-L832.11 | ERW Line Pipe - Issue PO | 0 | 0 | 0 | 0% |  | 2015-04-02 | 6 | 2015-01-26 | 2015-04-01 | -1
FL-L832.20 | FL-L832.20 | ERW Line Pipe - Manufacturing & Delivery | 180 | 0 | 0 | 0% | 2015-04-03 | 2015-12-10 | 7 | 2015-11-02 | 2015-12-09 | -1
FL-L832.30 | FL-L832.30 | ERW Line Pipe - First Submission of Vendor Data | 10 | 0 | 0 | 0% | 2015-04-03 | 2015-04-16 | 206 | 2015-02-09 | 2015-04-15 | -1
FL-L832.40 | FL-L832.40 | ERW Line Pipe - Vendor Data Review | 10 | 5 | 0 | 0% | 2015-04-17 | 2015-04-30 | 194 | 2015-02-24 | 2015-04-29 | -1
FL-L832.50 | FL-L832.50 | ERW Line Pipe - Vendor Revising Data | 10 | 0 | 0 | 0% | 2015-05-01 | 2015-05-14 | 207 | 2015-03-10 | 2015-05-13 | -1
FL-L832.60 | FL-L832.60 | ERW Line Pipe - Final Vendor Data | 10 | 0 | 0 | 0% | 2015-05-15 | 2015-05-29 | 194 | 2015-03-24 | 2015-05-28 | -1
ASME Pipe & Fittings (FL-L833) - Added PI-0077 (CN TBD) | ASME Pipe & Fittings (FL-L833) - Added PI-0077 (CN TBD)
FL-L833.00 | FL-L833.00 | ASME Pipe & Fittings - MR Release to Client Eng | 5 | 0 | 0 | 0% | 2015-01-27 | 2015-02-02 | 65 |  | 2015-01-20 | -9
FL-L833.01 | FL-L833.01 | ASME Pipe & Fittings - MR Release to Client Proc - Prepare MRQ Package | 5 | 0 | 0 | 0% | 2015-02-03 | 2015-02-09 | 65 |  | 2015-01-27 | -9
FL-L833.02 | FL-L833.02 | ASME Pipe & Fittings - RFP Approval & Issue to Vendors | 15 | 0 | 0 | 0% | 2015-02-10 | 2015-03-03 | 65 |  | 2015-02-18 | -9
FL-L833.03 | FL-L833.03 | ASME Pipe & Fittings - Proposal Received by Client Proc | 5 | 0 | 0 | 0% | 2015-03-04 | 2015-03-10 | 65 |  | 2015-02-25 | -9
FL-L833.04 | FL-L833.04 | ASME Pipe & Fittings - Commercial Bid Evaluation by Client Proc | 25 | 0 | 0 | 0% | 2015-03-11 | 2015-04-15 | 78 |  | 2015-04-01 | -9
FL-L833.05 | FL-L833.05 | ASME Pipe & Fittings - Technical Bid Evaluation | 15 | 0 | 0 | 0% | 2015-03-11 | 2015-03-31 | 65 |  | 2015-03-18 | -9
FL-L833.06 | FL-L833.06 | ASME Pipe & Fittings - Review Technical Bid Evaluation by Client Eng | 5 | 0 | 0 | 0% | 2015-04-01 | 2015-04-08 | 65 |  | 2015-03-25 | -9
FL-L833.07 | FL-L833.07 | ASME Pipe & Fittings - Prepare & Issue MRP | 10 | 0 | 0 | 0% | 2015-04-09 | 2015-04-22 | 65 |  | 2015-04-09 | -9
FL-L833.08 | FL-L833.08 | ASME Pipe & Fittings - LOR Preparation & Approval | 7 | 0 | 0 | 0% | 2015-04-16 | 2015-04-24 | 78 |  | 2015-04-13 | -9
FL-L833.09 | FL-L833.09 | ASME Pipe & Fittings - MRP Review by Client Eng | 5 | 0 | 0 | 0% | 2015-04-23 | 2015-04-29 | 65 |  | 2015-04-16 | -9
FL-L833.10 | FL-L833.10 | ASME Pipe & Fittings - MRP Release to Client Proc - Prepare PO | 10 | 0 | 0 | 0% | 2015-04-30 | 2015-05-13 | 65 |  | 2015-04-30 | -9
FL-L833.11 | FL-L833.11 | ASME Pipe & Fittings - Issue PO | 0 | 0 | 0 | 0% |  | 2015-05-13 | 65 |  | 2015-04-30 | -9
FL-L833.20 | FL-L833.20 | ASME Pipe & Fittings - Manufacturing & Delivery | 150 | 0 | 0 | 0% | 2015-05-14 | 2015-12-09 | 68 |  | 2015-11-26 | -9
FL-L833.30 | FL-L833.30 | ASME Pipe & Fittings - First Submission of Vendor Data | 10 | 0 | 0 | 0% | 2015-05-14 | 2015-05-27 | 177 |  | 2015-05-14 | -9
FL-L833.40 | FL-L833.40 | ASME Pipe & Fittings - Vendor Data Review | 10 | 0 | 0 | 0% | 2015-05-28 | 2015-06-10 | 166 |  | 2015-05-29 | -8
FL-L833.50 | FL-L833.50 | ASME Pipe & Fittings - Vendor Revising Data | 10 | 0 | 0 | 0% | 2015-06-11 | 2015-06-24 | 178 |  | 2015-06-12 | -8
FL-L833.60 | FL-L833.60 | ASME Pipe & Fittings - Final Vendor Data | 10 | 0 | 0 | 0% | 2015-06-25 | 2015-07-09 | 166 |  | 2015-06-26 | -8
CSA High Grade Steam Fittings and Flanges (FL-L840) | CSA High Grade Steam Fittings and Flanges (FL-L840)
FL-L840.00 | FL-L840.00 | CSA High Grade Steam Fittings and Flanges - MR Release to Client Eng | 5 | 0 | 0 | 0% | 2015-01-22 | 2015-01-28 | 116 | 2014-12-08 | 2015-01-19 | -7
FL-L840.01 | FL-L840.01 | CSA High Grade Steam Fittings and Flanges - MR Release to Client Proc - Prepare MRQ Package | 5 | 0 | 0 | 0% | 2015-01-29 | 2015-02-04 | 116 | 2014-12-15 | 2015-01-26 | -7
FL-L840.02 | FL-L840.02 | CSA High Grade Steam Fittings and Flanges - RFP Approval & Issue to Vendors | 15 | 0 | 0 | 0% | 2015-02-05 | 2015-02-26 | 116 | 2015-01-19 | 2015-02-17 | -7
FL-L840.03 | FL-L840.03 | CSA High Grade Steam Fittings and Flanges - Proposal Received by Client Proc | 5 | 0 | 0 | 0% | 2015-02-27 | 2015-03-05 | 116 | 2015-01-26 | 2015-02-24 | -7
FL-L840.04 | FL-L840.04 | CSA High Grade Steam Fittings and Flanges - Commercial Bid Evaluation by Client Proc | 25 | 0 | 0 | 0% | 2015-03-06 | 2015-04-10 | 119 | 2015-03-03 | 2015-03-31 | -7
FL-L840.05 | FL-L840.05 | CSA High Grade Steam Fittings and Flanges - Technical Bid Evaluation | 15 | 16 | 0 | 0% | 2015-03-06 | 2015-03-26 | 116 | 2015-02-17 | 2015-03-17 | -7
FL-L840.06 | FL-L840.06 | CSA High Grade Steam Fittings and Flanges - Review Technical Bid Evaluation by Client Eng | 5 | 0 | 0 | 0% | 2015-03-27 | 2015-04-02 | 116 | 2015-02-24 | 2015-03-24 | -7
FL-L840.07 | FL-L840.07 | CSA High Grade Steam Fittings and Flanges - Prepare & Issue MRP | 10 | 5 | 0 | 0% | 2015-04-06 | 2015-04-17 | 116 | 2015-03-10 | 2015-04-08 | -7
FL-L840.08 | FL-L840.08 | CSA High Grade Steam Fittings and Flanges - LOR Preparation & Approval | 7 | 0 | 0 | 0% | 2015-04-13 | 2015-04-21 | 119 | 2015-03-12 | 2015-04-10 | -7
FL-L840.09 | FL-L840.09 | CSA High Grade Steam Fittings and Flanges - MRP Review by Client Eng | 5 | 0 | 0 | 0% | 2015-04-20 | 2015-04-24 | 116 | 2015-03-17 | 2015-04-15 | -7
FL-L840.10 | FL-L840.10 | CSA High Grade Steam Fittings and Flanges - MRP Release to Client Proc - Prepare PO | 10 | 0 | 0 | 0% | 2015-04-27 | 2015-05-08 | 116 | 2015-03-31 | 2015-04-29 | -7
FL-L840.11 | FL-L840.11 | CSA High Grade Steam Fittings and Flanges - Issue PO | 0 | 0 | 0 | 0% |  | 2015-05-08 | 116 | 2015-03-31 | 2015-04-29 | -7
FL-L840.20 | FL-L840.20 | CSA High Grade Steam Fittings and Flanges - Manufacturing & Delivery | 100 | 0 | 0 | 0% | 2015-05-11 | 2015-09-25 | 121 | 2015-08-18 | 2015-09-16 | -7
FL-L840.30 | FL-L840.30 | CSA High Grade Steam Fittings and Flanges - First Submission of Vendor Data | 10 | 0 | 0 | 0% | 2015-05-11 | 2015-05-22 | 180 | 2015-04-14 | 2015-05-13 | -7
FL-L840.40 | FL-L840.40 | CSA High Grade Steam Fittings and Flanges - Vendor Data Review | 10 | 0 | 0 | 0% | 2015-05-25 | 2015-06-05 | 169 | 2015-04-28 | 2015-05-28 | -6
FL-L840.50 | FL-L840.50 | CSA High Grade Steam Fittings and Flanges - Vendor Revising Data | 10 | 0 | 0 | 0% | 2015-06-08 | 2015-06-19 | 181 | 2015-05-12 | 2015-06-11 | -6
FL-L840.60 | FL-L840.60 | CSA High Grade Steam Fittings and Flanges - Final Vendor Data | 10 | 0 | 0 | 0% | 2015-06-22 | 2015-07-06 | 169 | 2015-05-27 | 2015-06-25 | -6
CSA Grade 359 Fittings and Flanges (FL-L841) | CSA Grade 359 Fittings and Flanges (FL-L841)
FL-L841.00 | FL-L841.00 | CSA Grade 359 Fittings and Flanges - MR Release to Client Eng | 5 | 0 | 0 | 0% | 2015-01-30 | 2015-02-05 | 162 | 2014-12-08 | 2015-02-05 | 0
FL-L841.01 | FL-L841.01 | CSA Grade 359 Fittings and Flanges - MR Release to Client Proc - Prepare MRQ Package | 5 | 0 | 0 | 0% | 2015-02-06 | 2015-02-12 | 162 | 2014-12-15 | 2015-02-12 | 0
FL-L841.02 | FL-L841.02 | CSA Grade 359 Fittings and Flanges - RFP Approval & Issue to Vendors | 15 | 0 | 0 | 0% | 2015-02-13 | 2015-03-06 | 162 | 2015-01-19 | 2015-03-06 | 0
FL-L841.03 | FL-L841.03 | CSA Grade 359 Fittings and Flanges - Proposal Received by Client Proc | 5 | 0 | 0 | 0% | 2015-03-09 | 2015-03-13 | 162 | 2015-01-26 | 2015-03-13 | 0
FL-L841.04 | FL-L841.04 | CSA Grade 359 Fittings and Flanges - Commercial Bid Evaluation by Client Proc | 25 | 0 | 0 | 0% | 2015-03-16 | 2015-04-20 | 165 | 2015-03-03 | 2015-04-20 | 0
FL-L841.05 | FL-L841.05 | CSA Grade 359 Fittings and Flanges - Technical Bid Evaluation | 15 | 16 | 0 | 0% | 2015-03-16 | 2015-04-06 | 162 | 2015-02-17 | 2015-04-06 | 0
FL-L841.06 | FL-L841.06 | CSA Grade 359 Fittings and Flanges - Review Technical Bid Evaluation by Client Eng | 5 | 0 | 0 | 0% | 2015-04-07 | 2015-04-13 | 162 | 2015-02-24 | 2015-04-13 | 0
FL-L841.07 | FL-L841.07 | CSA Grade 359 Fittings and Flanges - Prepare & Issue MRP | 10 | 5 | 0 | 0% | 2015-04-14 | 2015-04-27 | 162 | 2015-03-10 | 2015-04-27 | 0
FL-L841.08 | FL-L841.08 | CSA Grade 359 Fittings and Flanges - LOR Preparation & Approval | 7 | 0 | 0 | 0% | 2015-04-21 | 2015-04-29 | 165 | 2015-03-12 | 2015-04-29 | 0
FL-L841.09 | FL-L841.09 | CSA Grade 359 Fittings and Flanges - MRP Review by Client Eng | 5 | 0 | 0 | 0% | 2015-04-28 | 2015-05-04 | 162 | 2015-03-17 | 2015-05-04 | 0
FL-L841.10 | FL-L841.10 | CSA Grade 359 Fittings and Flanges - MRP Release to Client Proc - Prepare PO | 10 | 0 | 0 | 0% | 2015-05-05 | 2015-05-19 | 162 | 2015-03-31 | 2015-05-19 | 0
FL-L841.11 | FL-L841.11 | CSA Grade 359 Fittings and Flanges - Issue PO | 0 | 0 | 0 | 0% |  | 2015-05-19 | 162 | 2015-03-31 | 2015-05-19 | 0
FL-L841.20 | FL-L841.20 | CSA Grade 359 Fittings and Flanges - Manufacturing & Delivery | 40 | 0 | 0 | 0% | 2015-05-20 | 2015-07-14 | 174 | 2015-05-26 | 2015-07-14 | 0
FL-L841.30 | FL-L841.30 | CSA Grade 359 Fittings and Flanges - First Submission of Vendor Data | 10 | 0 | 0 | 0% | 2015-05-20 | 2015-06-02 | 173 | 2015-04-14 | 2015-06-02 | 0
FL-L841.40 | FL-L841.40 | CSA Grade 359 Fittings and Flanges - Vendor Data Review | 10 | 0 | 0 | 0% | 2015-06-03 | 2015-06-16 | 162 | 2015-04-28 | 2015-06-16 | 0
FL-L841.50 | FL-L841.50 | CSA Grade 359 Fittings and Flanges - Vendor Revising Data | 10 | 0 | 0 | 0% | 2015-06-17 | 2015-06-30 | 174 | 2015-05-12 | 2015-06-30 | 0
FL-L841.60 | FL-L841.60 | CSA Grade 359 Fittings and Flanges - Final Vendor Data | 10 | 0 | 0 | 0% | 2015-07-02 | 2015-07-15 | 162 | 2015-05-27 | 2015-07-15 | 0
ERW Induction Bends (FL-L842) | ERW Induction Bends (FL-L842)
FL-L842.00 | FL-L842.00 | ERW Induction Bends - MR Release to Client Eng | 5 | 0 | 0 | 0% | 2015-03-06 | 2015-03-12 | 126 | 2015-02-09 | 2015-03-12 | 0
FL-L842.01 | FL-L842.01 | ERW Induction Bends - MR Release to Client Proc - Prepare MRQ Package | 5 | 0 | 0 | 0% | 2015-03-13 | 2015-03-19 | 126 | 2015-02-17 | 2015-03-19 | 0
FL-L842.02 | FL-L842.02 | ERW Induction Bends - RFP Approval & Issue to Vendors | 15 | 0 | 0 | 0% | 2015-03-20 | 2015-04-10 | 126 | 2015-03-10 | 2015-04-10 | 0
FL-L842.03 | FL-L842.03 | ERW Induction Bends - Proposal Received by Client Proc | 5 | 0 | 0 | 0% | 2015-04-13 | 2015-04-17 | 126 | 2015-03-17 | 2015-04-17 | 0
FL-L842.04 | FL-L842.04 | ERW Induction Bends - Commercial Bid Evaluation by Client Proc | 25 | 0 | 0 | 0% | 2015-04-20 | 2015-05-25 | 139 | 2015-04-22 | 2015-05-25 | 0
FL-L842.05 | FL-L842.05 | ERW Induction Bends - Technical Bid Evaluation | 15 | 16 | 0 | 0% | 2015-04-20 | 2015-05-08 | 126 | 2015-04-08 | 2015-05-08 | 0
FL-L842.06 | FL-L842.06 | ERW Induction Bends - Review Technical Bid Evaluation by Client Eng | 5 | 0 | 0 | 0% | 2015-05-11 | 2015-05-15 | 126 | 2015-04-15 | 2015-05-15 | 0
FL-L842.07 | FL-L842.07 | ERW Induction Bends - Prepare & Issue MRP | 10 | 5 | 0 | 0% | 2015-05-19 | 2015-06-01 | 126 | 2015-04-29 | 2015-06-01 | 0
FL-L842.08 | FL-L842.08 | ERW Induction Bends - LOR Preparation & Approval | 7 | 0 | 0 | 0% | 2015-05-26 | 2015-06-03 | 139 | 2015-05-01 | 2015-06-03 | 0
FL-L842.09 | FL-L842.09 | ERW Induction Bends - MRP Review by Client Eng | 5 | 0 | 0 | 0% | 2015-06-02 | 2015-06-08 | 126 | 2015-05-06 | 2015-06-08 | 0
FL-L842.10 | FL-L842.10 | ERW Induction Bends - MRP Release to Client Proc - Prepare PO | 10 | 0 | 0 | 0% | 2015-06-09 | 2015-06-22 | 126 | 2015-05-21 | 2015-06-22 | 0
FL-L842.11 | FL-L842.11 | ERW Induction Bends - Issue PO | 0 | 0 | 0 | 0% |  | 2015-06-22 | 126 | 2015-05-21 | 2015-06-22 | 0
FL-L842.30 | FL-L842.30 | ERW Induction Bends - First Submission of Vendor Data | 10 | 0 | 0 | 0% | 2015-06-23 | 2015-07-06 | 149 | 2015-06-04 | 2015-07-06 | 0
FL-L842.40 | FL-L842.40 | ERW Induction Bends - Vendor Data Review | 10 | 0 | 0 | 0% | 2015-07-07 | 2015-07-20 | 139 | 2015-06-18 | 2015-07-20 | 0
FL-L842.50 | FL-L842.50 | ERW Induction Bends - Vendor Revising Data | 10 | 0 | 0 | 0% | 2015-07-21 | 2015-08-03 | 150 | 2015-07-02 | 2015-08-03 | 0
FL-L842.60 | FL-L842.60 | ERW Induction Bends - Final Vendor Data | 10 | 0 | 0 | 0% | 2015-08-04 | 2015-08-17 | 140 | 2015-07-16 | 2015-08-17 | 0
FL-L842.20 | FL-L842.20 | ERW Induction Bends - Manufacturing & Delivery | 60 | 0 | 0 | 0% | 2015-12-11 | 2016-03-03 | 7 | 2015-11-05 | 2016-03-02 | -1
Pre-Insulated Pipe Supports (FL-L850) | Pre-Insulated Pipe Supports (FL-L850)
FL-L850.00 | FL-L850.00 | Pre-Insulated Pipe Supports - MR Release to Client Eng | 5 | 0 | 0 | 0% | 2015-01-28 | 2015-02-03 | 83 | 2014-11-17 | 2015-02-11 | 6
FL-L850.01 | FL-L850.01 | Pre-Insulated Pipe Supports - MR Release to Client Proc - Prepare MRQ Package | 5 | 0 | 0 | 0% | 2015-02-04 | 2015-02-10 | 83 | 2014-11-24 | 2015-02-19 | 6
FL-L850.02 | FL-L850.02 | Pre-Insulated Pipe Supports - RFP Approval & Issue to Vendors | 15 | 0 | 0 | 0% | 2015-02-11 | 2015-03-04 | 83 | 2014-12-15 | 2015-03-12 | 6
FL-L850.03 | FL-L850.03 | Pre-Insulated Pipe Supports - Proposal Received by Client Proc | 5 | 0 | 0 | 0% | 2015-03-05 | 2015-03-11 | 83 | 2015-01-05 | 2015-03-19 | 6
FL-L850.04 | FL-L850.04 | Pre-Insulated Pipe Supports - Commercial Bid Evaluation by Client Proc | 25 | 0 | 0 | 0% | 2015-03-12 | 2015-04-16 | 86 | 2015-02-09 | 2015-04-24 | 6
FL-L850.05 | FL-L850.05 | Pre-Insulated Pipe Supports - Technical Bid Evaluation | 15 | 16 | 0 | 0% | 2015-03-12 | 2015-04-01 | 83 | 2015-01-26 | 2015-04-10 | 6
FL-L850.06 | FL-L850.06 | Pre-Insulated Pipe Supports - Review Technical Bid Evaluation by Client Eng | 5 | 0 | 0 | 0% | 2015-04-02 | 2015-04-09 | 83 | 2015-02-02 | 2015-04-17 | 6
FL-L850.07 | FL-L850.07 | Pre-Insulated Pipe Supports - Prepare & Issue MRP | 10 | 5 | 0 | 0% | 2015-04-10 | 2015-04-23 | 83 | 2015-02-17 | 2015-05-01 | 6
FL-L850.08 | FL-L850.08 | Pre-Insulated Pipe Supports - LOR Preparation & Approval | 7 | 0 | 0 | 0% | 2015-04-17 | 2015-04-27 | 86 | 2015-02-19 | 2015-05-05 | 6
FL-L850.09 | FL-L850.09 | Pre-Insulated Pipe Supports - MRP Review by Client Eng | 5 | 0 | 0 | 0% | 2015-04-24 | 2015-04-30 | 83 | 2015-02-24 | 2015-05-08 | 6
FL-L850.10 | FL-L850.10 | Pre-Insulated Pipe Supports - MRP Release to Client Proc - Prepare PO | 10 | 0 | 0 | 0% | 2015-05-01 | 2015-05-14 | 83 | 2015-03-10 | 2015-05-25 | 6
FL-L850.11 | FL-L850.11 | Pre-Insulated Pipe Supports - Issue PO | 0 | 0 | 0 | 0% |  | 2015-05-14 | 83 | 2015-03-10 | 2015-05-25 | 6
FL-L850.20 | FL-L850.20 | Pre-Insulated Pipe Supports - Manufacturing & Delivery | 130 | 0 | 0 | 0% | 2015-05-15 | 2015-11-12 | 87 | 2015-09-08 | 2015-11-23 | 7
FL-L850.30 | FL-L850.30 | Pre-Insulated Pipe Supports - First Submission of Vendor Data | 10 | 0 | 0 | 0% | 2015-05-15 | 2015-05-28 | 176 | 2015-03-24 | 2015-06-08 | 7
FL-L850.40 | FL-L850.40 | Pre-Insulated Pipe Supports - Vendor Data Review | 10 | 5 | 0 | 0% | 2015-05-29 | 2015-06-11 | 165 | 2015-04-08 | 2015-06-22 | 7
FL-L850.50 | FL-L850.50 | Pre-Insulated Pipe Supports - Vendor Revising Data | 10 | 0 | 0 | 0% | 2015-06-12 | 2015-06-25 | 177 | 2015-04-22 | 2015-07-06 | 7
FL-L850.60 | FL-L850.60 | Pre-Insulated Pipe Supports - Final Vendor Data | 10 | 0 | 0 | 0% | 2015-06-26 | 2015-07-10 | 165 | 2015-05-06 | 2015-07-20 | 6

## Procurement Plan
|  | Step | .R1 | .R2 | .R3 | .00 | .01 | .02 | .03 | .04 | .05 | .06 | .07 | .08 | .09 | .10 | .11 | .20 | .30 | .40 | .60
MR # | Description | Finish Dates | MR IFR | MR Review | MR IFQ | MR Release | MRQ Package | RFP Approval | Proposal Received | CBE | TBE | TBE Review | MRP | LOR | MRP Review | MRP Release | Award PO | Manufacturing & Delivery | Vendor Data 1st Submision | Vendor Data Review | Vendor Data Final Code 1
FL-L820 | Manual Valves (Flowlines) | Baseline | 2014-09-23 | 2014-10-08 | 2014-10-24 | 2014-11-03 | 2014-11-10 | 2014-12-01 | 2014-12-08 | 2015-01-26 | 2015-01-12 | 2015-01-19 | 2015-02-02 | 2015-02-04 | 2015-02-09 | 2015-02-24 | 2015-02-24 | 2015-12-15 | 2015-03-10 | 2015-03-24 | 2015-04-21
|  | Previous Month | 2014-09-22 | 2014-10-21 | 2014-11-10 | 2014-11-17 | 2014-11-24 | 2014-12-15 | 2014-12-16 | 2015-01-29 | 2015-01-15 | 2015-01-22 | 2015-02-05 | 2015-02-09 | 2015-02-12 | 2015-02-27 | 2015-02-27 | 2015-12-18 | 2015-03-13 | 2015-03-27 | 2015-04-24
|  | Forecast/Actual | 22-Sep-14 A | 21-Oct-14 A | 10-Nov-14 A | 17-Nov-14 A | 24-Nov-14 A | 15-Dec-14 A | 16-Dec-14 A | 2015-01-29 | 2015-01-16 | 2015-01-23 | 2015-02-06 | 2015-02-10 | 2015-02-13 | 2015-03-02 | 2015-03-02 | 2015-12-21 | 2015-03-16 | 2015-03-30 | 2015-04-27
|  | Month Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1
|  | Comments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL-L821 | High Pressure Valves (Flowlines) | Baseline | 2014-07-25 | 2014-08-12 | 2014-08-27 | 2014-09-05 | 2014-09-12 | 2014-10-03 | 2014-10-10 | 2014-11-17 | 2014-11-03 | 2014-11-10 | 2014-11-24 | 2014-11-26 | 2014-12-01 | 2014-12-15 | 2014-12-15 | 2015-12-28 | 2014-12-29 | 2015-01-16 | 2015-02-13
|  | Previous Month | 2014-07-25 | 2014-08-18 | 2014-08-22 | 2014-09-18 | 2014-10-09 | 2014-10-31 | 2014-11-05 | 2015-01-09 | 2014-12-19 | 2015-01-09 | 2015-01-23 | 2015-01-27 | 2015-01-30 | 2015-02-13 | 2015-02-13 | 2016-02-26 | 2015-02-27 | 2015-03-13 | 2015-04-13
|  | Forecast/Actual | 25-Jul-14 A | 18-Aug-14 A | 22-Aug-14 A | 18-Sep-14 A | 09-Oct-14 A | 31-Oct-14 A | 05-Nov-14 A | 2015-01-23 | 2015-01-16 | 2015-01-23 | 2015-02-06 | 2015-02-10 | 2015-02-13 | 2015-03-02 | 2015-03-02 | 2016-03-14 | 2015-03-16 | 2015-03-30 | 2015-04-27
|  | Month Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10 | -10 | -10 | -10 | -10 | -10 | -10 | -10 | -11 | -11 | -11 | -10
|  | Notes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Waiting for quotes on valves changes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL-L831 | CSA High Grade Steam Line Pipe | Baseline | 2014-08-25 | 2014-09-10 | 2014-09-25 | 2014-10-03 | 2014-10-10 | 2014-11-03 | 2014-11-10 | 2014-12-15 | 2014-12-01 | 2014-12-08 | 2015-01-05 | 2015-01-07 | 2015-01-12 | 2015-01-26 | 2015-01-26 | 2015-11-02 | 2015-02-09 | 2015-02-24 | 2015-03-24
|  | Previous Month | 2014-09-08 | 2014-09-23 | 2014-11-14 | 2014-11-21 | 2014-12-17 | 2015-01-21 | 2015-01-27 | 2015-03-04 | 2015-02-18 | 2015-02-25 | 2015-03-11 | 2015-03-13 | 2015-03-18 | 2015-04-01 | 2015-04-01 | 2016-01-06 | 2015-04-15 | 2015-04-29 | 2015-05-28
|  | Forecast/Actual | 08-Sep-14 A | 23-Sep-14 A | 14-Nov-14 A | 21-Nov-14 A | 18-Dec-14 A | 2015-01-22 | 2015-01-28 | 2015-03-05 | 2015-02-19 | 2015-02-26 | 2015-03-12 | 2015-03-16 | 2015-03-19 | 2015-04-02 | 2015-04-02 | 2016-01-07 | 2015-04-16 | 2015-04-30 | 2015-05-29
|  | Month Variance | 0 | 0 | 0 | 0 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1
|  | Notes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL-L832 | ERW Line Pipe | Baseline | 2014-08-25 | 2014-09-10 | 2014-09-25 | 2014-10-03 | 2014-10-10 | 2014-11-03 | 2014-11-10 | 2014-12-15 | 2014-12-01 | 2014-12-08 | 2015-01-05 | 2015-01-07 | 2015-01-12 | 2015-01-26 | 2015-01-26 | 2015-11-02 | 2015-02-09 | 2015-02-24 | 2015-03-24
|  | Previous Month | 2014-09-16 | 2014-09-30 | 2014-11-25 | 2014-12-01 | 2014-12-17 | 2015-01-21 | 2015-01-27 | 2015-03-04 | 2015-02-18 | 2015-02-25 | 2015-03-11 | 2015-03-13 | 2015-03-18 | 2015-04-01 | 2015-04-01 | 2015-12-09 | 2015-04-15 | 2015-04-29 | 2015-05-28
|  | Forecast/Actual | 16-Sep-14 A | 30-Sep-14 A | 25-Nov-14 A | 01-Dec-14 A | 18-Dec-14 A | 2015-01-22 | 2015-01-28 | 2015-03-05 | 2015-02-19 | 2015-02-26 | 2015-03-12 | 2015-03-16 | 2015-03-19 | 2015-04-02 | 2015-04-02 | 2015-12-10 | 2015-04-16 | 2015-04-30 | 2015-05-29
|  | Month Variance | 0 | 0 | 0 | 0 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1
|  | Notes | 0 | 0 | Re-issued Rev. C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL-L840 | CSA High Grade Steam Fittings and Flanges | Baseline | 2014-10-29 | 2014-11-13 | 2014-11-28 | 2014-12-08 | 2014-12-15 | 2015-01-19 | 2015-01-26 | 2015-03-03 | 2015-02-17 | 2015-02-24 | 2015-03-10 | 2015-03-12 | 2015-03-17 | 2015-03-31 | 2015-03-31 | 2015-08-18 | 2015-04-14 | 2015-04-28 | 2015-05-27
|  | Previous Month | 2014-11-27 | 2014-12-10 | 2015-01-09 | 2015-01-19 | 2015-01-26 | 2015-02-17 | 2015-02-24 | 2015-03-31 | 2015-03-17 | 2015-03-24 | 2015-04-08 | 2015-04-10 | 2015-04-15 | 2015-04-29 | 2015-04-29 | 2015-09-16 | 2015-05-13 | 2015-05-28 | 2015-06-25
|  | Forecast/Actual | 27-Nov-14 A | 10-Dec-14 A | 2015-01-20 | 2015-01-28 | 2015-02-04 | 2015-02-26 | 2015-03-05 | 2015-04-10 | 2015-03-26 | 2015-04-02 | 2015-04-17 | 2015-04-21 | 2015-04-24 | 2015-05-08 | 2015-05-08 | 2015-09-25 | 2015-05-22 | 2015-06-05 | 2015-07-06
|  | Month Variance | 0 | 0 | -7 | -7 | -7 | -7 | -7 | -7 | -7 | -7 | -7 | -7 | -7 | -7 | -7 | -7 | -7 | -6 | -6
|  | Notes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL-L841 | CSA Grade 359 Fittings and Flanges | Baseline | 2014-10-29 | 2014-11-13 | 2014-11-28 | 2014-12-08 | 2014-12-15 | 2015-01-19 | 2015-01-26 | 2015-03-03 | 2015-02-17 | 2015-02-24 | 2015-03-10 | 2015-03-12 | 2015-03-17 | 2015-03-31 | 2015-03-31 | 2015-05-26 | 2015-04-14 | 2015-04-28 | 2015-05-27
|  | Previous Month | 2014-12-16 | 2015-01-13 | 2015-01-28 | 2015-02-05 | 2015-02-12 | 2015-03-06 | 2015-03-13 | 2015-04-20 | 2015-04-06 | 2015-04-13 | 2015-04-27 | 2015-04-29 | 2015-05-04 | 2015-05-19 | 2015-05-19 | 2015-07-14 | 2015-06-02 | 2015-06-16 | 2015-07-15
|  | Forecast/Actual | 16-Dec-14 A | 2015-01-12 | 2015-01-28 | 2015-02-05 | 2015-02-12 | 2015-03-06 | 2015-03-13 | 2015-04-20 | 2015-04-06 | 2015-04-13 | 2015-04-27 | 2015-04-29 | 2015-05-04 | 2015-05-19 | 2015-05-19 | 2015-07-14 | 2015-06-02 | 2015-06-16 | 2015-07-15
|  | Month Variance | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Notes | Postponed - Low Priority | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL-L842 | ERW Induction Bends | Baseline | 2014-12-17 | 2015-01-15 | 2015-01-30 | 2015-02-09 | 2015-02-17 | 2015-03-10 | 2015-03-17 | 2015-04-22 | 2015-04-08 | 2015-04-15 | 2015-04-29 | 2015-05-01 | 2015-05-06 | 2015-05-21 | 2015-05-21 | 2015-11-05 | 2015-06-04 | 2015-06-18 | 2015-07-16
|  | Previous Month | 2015-01-30 | 2015-02-17 | 2015-03-04 | 2015-03-12 | 2015-03-19 | 2015-04-10 | 2015-04-17 | 2015-05-25 | 2015-05-08 | 2015-05-15 | 2015-06-01 | 2015-06-03 | 2015-06-08 | 2015-06-22 | 2015-06-22 | 2016-03-02 | 2015-07-06 | 2015-07-20 | 2015-08-17
|  | Forecast/Actual | 2015-01-30 | 2015-02-17 | 2015-03-04 | 2015-03-12 | 2015-03-19 | 2015-04-10 | 2015-04-17 | 2015-05-25 | 2015-05-08 | 2015-05-15 | 2015-06-01 | 2015-06-03 | 2015-06-08 | 2015-06-22 | 2015-06-22 | 2016-03-03 | 2015-07-06 | 2015-07-20 | 2015-08-17
|  | Month Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0
|  | Notes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL-L850 | Pre-Insulated Pipe Supports | Baseline | 2014-10-07 | 2014-10-23 | 2014-11-07 | 2014-11-17 | 2014-11-24 | 2014-12-15 | 2015-01-05 | 2015-02-09 | 2015-01-26 | 2015-02-02 | 2015-02-17 | 2015-02-19 | 2015-02-24 | 2015-03-10 | 2015-03-10 | 2015-09-08 | 2015-03-24 | 2015-04-08 | 2015-05-06
|  | Previous Month | 2014-12-19 | 2015-01-19 | 2015-02-03 | 2015-02-11 | 2015-02-19 | 2015-03-12 | 2015-03-19 | 2015-04-24 | 2015-04-10 | 2015-04-17 | 2015-05-01 | 2015-05-05 | 2015-05-08 | 2015-05-25 | 2015-05-25 | 2015-11-23 | 2015-06-08 | 2015-06-22 | 2015-07-20
|  | Forecast/Actual | 09-Jan-15 A | 13-Jan-15 A | 2015-01-26 | 2015-02-03 | 2015-02-10 | 2015-03-04 | 2015-03-11 | 2015-04-16 | 2015-04-01 | 2015-04-09 | 2015-04-23 | 2015-04-27 | 2015-04-30 | 2015-05-14 | 2015-05-14 | 2015-11-12 | 2015-05-28 | 2015-06-11 | 2015-07-10
|  | Month Variance | -5 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 6
|  | Notes | Waiting for Shoe Info | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL-L833 | ASME Pipe & Fittings | Baseline | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Previous Month | 2014-11-28 | 2014-12-15 | 2015-01-12 | 2015-01-20 | 2015-01-27 | 2015-02-18 | 2015-02-25 | 2015-04-01 | 2015-03-18 | 2015-03-25 | 2015-04-09 | 2015-04-13 | 2015-04-16 | 2015-04-30 | 2015-04-30 | 2015-11-26 | 2015-05-14 | 2015-05-29 | 2015-06-26
|  | Forecast/Actual | 28-Nov-14 A | 15-Dec-14 A | 2015-01-23 | 2015-02-02 | 2015-02-09 | 2015-03-03 | 2015-03-10 | 2015-04-15 | 2015-03-31 | 2015-04-08 | 2015-04-22 | 2015-04-24 | 2015-04-29 | 2015-05-13 | 2015-05-13 | 2015-12-09 | 2015-05-27 | 2015-06-10 | 2015-07-09
|  | Month Variance | 0 | 0 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -8 | -8
|  | Notes | Rev.A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FL-S101 | Structural Steel for Flowlines | Baseline | 0 | 0 | 0 | 2014-12-15 | 2015-01-05 | 2015-01-26 | 2015-02-02 | 2015-03-10 | 2015-02-24 | 2015-03-03 | 2015-03-17 | 2015-03-19 | 2015-03-24 | 2015-04-22 | 2015-04-22 | 2015-06-17 | 2015-05-06 | 2015-05-21 | 2015-06-18
|  | Previous Month | 2015-02-13 | 2015-03-03 | 2015-03-18 | 2015-03-26 | 2015-04-02 | 2015-04-24 | 2015-05-01 | 2015-06-08 | 2015-05-25 | 2015-06-01 | 2015-06-15 | 2015-06-17 | 2015-06-24 | 2015-07-23 | 2015-07-23 | 2015-10-29 | 2015-08-06 | 2015-08-20 | 2015-09-18
|  | Forecast/Actual | 2015-02-13 | 2015-03-03 | 2015-03-18 | 2015-03-26 | 2015-04-02 | 2015-04-24 | 2015-05-01 | 2015-06-08 | 2015-05-25 | 2015-06-01 | 2015-06-15 | 2015-06-17 | 2015-06-24 | 2015-07-23 | 2015-07-23 | 2015-10-29 | 2015-08-06 | 2015-08-20 | 2015-09-18
|  | Month Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Notes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
MR IFR = VLOOKUP(CONCATENATE([MR #],D1),'P6 Dump'!$A1:N500,11,FALSE)
MR IFR = VLOOKUP(CONCATENATE([MR #, row above],D1),'P6 Dump'!$A1:N500,12,FALSE)
MR Review = VLOOKUP(CONCATENATE([MR #],E1),'P6 Dump'!$A1:N500,11,FALSE)
MR Review = VLOOKUP(CONCATENATE([MR #, row above],E1),'P6 Dump'!$A1:N500,12,FALSE)
MR IFQ = VLOOKUP(CONCATENATE([MR #],F1),'P6 Dump'!$A1:N500,11,FALSE)
MR IFQ = VLOOKUP(CONCATENATE([MR #, row above],F1),'P6 Dump'!$A1:N500,12,FALSE)
MR Release = VLOOKUP(CONCATENATE([MR #],G1),'P6 Dump'!$A1:N500,11,FALSE)
MR Release = VLOOKUP(CONCATENATE([MR #, row above],G1),'P6 Dump'!$A1:N500,12,FALSE)
MRQ Package = VLOOKUP(CONCATENATE([MR #],H1),'P6 Dump'!$A1:N500,11,FALSE)
MRQ Package = VLOOKUP(CONCATENATE([MR #, row above],H1),'P6 Dump'!$A1:N500,12,FALSE)
RFP Approval = VLOOKUP(CONCATENATE([MR #],I1),'P6 Dump'!$A1:N500,11,FALSE)
RFP Approval = VLOOKUP(CONCATENATE([MR #, row above],I1),'P6 Dump'!$A1:N500,12,FALSE)
Proposal Received = VLOOKUP(CONCATENATE([MR #],J1),'P6 Dump'!$A1:N500,11,FALSE)
Proposal Received = VLOOKUP(CONCATENATE([MR #, row above],J1),'P6 Dump'!$A1:N500,12,FALSE)
CBE = VLOOKUP(CONCATENATE([MR #],K1),'P6 Dump'!$A1:N500,11,FALSE)
CBE = VLOOKUP(CONCATENATE([MR #, row above],K1),'P6 Dump'!$A1:N500,12,FALSE)
TBE = VLOOKUP(CONCATENATE([MR #],L1),'P6 Dump'!$A1:N500,11,FALSE)
TBE = VLOOKUP(CONCATENATE([MR #, row above],L1),'P6 Dump'!$A1:N500,12,FALSE)
TBE Review = VLOOKUP(CONCATENATE([MR #],M1),'P6 Dump'!$A1:N500,11,FALSE)
TBE Review = VLOOKUP(CONCATENATE([MR #, row above],M1),'P6 Dump'!$A1:N500,12,FALSE)
MRP = VLOOKUP(CONCATENATE([MR #],N1),'P6 Dump'!$A1:N500,11,FALSE)
MRP = VLOOKUP(CONCATENATE([MR #, row above],N1),'P6 Dump'!$A1:N500,12,FALSE)
LOR = VLOOKUP(CONCATENATE([MR #],O1),'P6 Dump'!$A1:N500,11,FALSE)
LOR = VLOOKUP(CONCATENATE([MR #, row above],O1),'P6 Dump'!$A1:N500,12,FALSE)
MRP Review = VLOOKUP(CONCATENATE([MR #],P1),'P6 Dump'!$A1:N500,11,FALSE)
MRP Review = VLOOKUP(CONCATENATE([MR #, row above],P1),'P6 Dump'!$A1:N500,12,FALSE)
MRP Release = VLOOKUP(CONCATENATE([MR #],Q1),'P6 Dump'!$A1:N500,11,FALSE)
MRP Release = VLOOKUP(CONCATENATE([MR #, row above],Q1),'P6 Dump'!$A1:N500,12,FALSE)
Award PO = VLOOKUP(CONCATENATE([MR #],R1),'P6 Dump'!$A1:N500,11,FALSE)
Award PO = VLOOKUP(CONCATENATE([MR #, row above],R1),'P6 Dump'!$A1:N500,12,FALSE)
Manufacturing & Delivery = VLOOKUP(CONCATENATE([MR #],S1),'P6 Dump'!$A1:N500,11,FALSE)
Manufacturing & Delivery = VLOOKUP(CONCATENATE([MR #, row above],S1),'P6 Dump'!$A1:N500,12,FALSE)
Vendor Data 1st Submision = VLOOKUP(CONCATENATE([MR #],T1),'P6 Dump'!$A1:N500,11,FALSE)
Vendor Data 1st Submision = VLOOKUP(CONCATENATE([MR #, row above],T1),'P6 Dump'!$A1:N500,12,FALSE)
Vendor Data Review = VLOOKUP(CONCATENATE([MR #],U1),'P6 Dump'!$A1:N500,11,FALSE)
Vendor Data Review = VLOOKUP(CONCATENATE([MR #, row above],U1),'P6 Dump'!$A1:N500,12,FALSE)
Vendor Data Final Code 1 = VLOOKUP(CONCATENATE([MR #],V1),'P6 Dump'!$A1:N500,11,FALSE)
Vendor Data Final Code 1 = VLOOKUP(CONCATENATE([MR #, row above],V1),'P6 Dump'!$A1:N500,12,FALSE)

## MR#
FL-L820 | Manual Valves (Flowlines)
FL-L821 | High Pressure Valves (Flowlines)
FL-L831 | CSA High Grade Steam Line Pipe
FL-L832 | ERW Line Pipe
FL-L833 | ASME Pipe & Fittings
FL-L840 | CSA High Grade Steam Fittings and Flanges
FL-L841 | CSA Grade 359 Fittings and Flanges
FL-L842 | ERW Induction Bends
FL-L850 | Pre-Insulated Pipe Supports
FL-S101 | Structural Steel for Flowlines